## Instructions
Worksheet definitions and DCE Instructions
WORKBOOK TABS
The "Tabs" listed below contain data used to develop the building estimates and in many cases are linked together. A description for each workbook (tab) is defined below:
ADJUSTMENT (TAB) | This will typically not change and is based on estimators experience, accuracy and availability of site information and previous experience.
INPUT TAB: | This tab allows the user to change parameters of the estimate. Any changes made will be reflected in various elements in the cost estimate.
1 | Enter the year of the estimate.
2 | Verify/change yearly escalation rates.
3 | Verify/change waste density rate
4 | Update exchange rate, US to AU.
5 | Update ANSTO labor rates
6 | Update ANSTO waste disposal rates.
7 | Update equipment costs and quantities. Specify whether costs are US or AU dollars, cell D85. Specify cost year, cell E86.
8 | Update consumable costs and quantities.
9 | Review building specific data and modify as needed.
10 | The base estimates are based on a crew size of 12. The crew size can modified for each building by changing the number of crews under the building specific inputs. A smaller building may a require a smaller crew size and vice versa. This will require estimators judgement.
COMPARISON TAB: | This tab is for "Information only". It compares the Cost Estimate prepared by CAA to the 2018 PT&C DCE.
WBS SUMMARY TAB | This tab contains the Work Breakdown Structure for each of the five areas into the 7 sections as requested by ANSTO.
BUILDING TABS | This is the build up of the building specific cost estimate. It includes the undistributed costs, such as staffing and equipment and material, and the activity costs. The activity costs are determined by the building square meters and the unit rates determined from previous estimates.
1 | Review cells highlighted in green and adjust as necessary.
2 | Insert building area
3 | Insert project duration. This is not a calculated duration, it is estimator's judgement.
4 | Insert length of asbestos pipe, if any.
5 | Insert number of crews adjustment, see 10 above.
SUMMARY 2026 $ TAB | This is a breakdown of the averages obtained from CAA Cost estimating data from other estimates. It is updated into 2026 AUD. Protected worksheet and no action needed. This worksheet should not be altered or change in any way.
HIDDEN TABS: | There are a number of hidden tabs which have site specific data for other DCE prepared by the estimators. The data in these tabs are linked to the overall cost estimate. These are protected worksheets. These should not be altered or change in any way.
HOW TO MAKE CHANGESS AND USE THE CAA WORKBOOK
The five buildings in this workbook B17, 18, 54, 56, 70, and BXX (BXX is generic example for use and practice) are considered the “Master File”. The DCE for each of these buildings share the same data from the “adjustments” and “Input tab”. If you change any data in these tabs, it has the potential to impact one or more of the other buildings. For example hourly labor rates are defined in the input tab and are used to determine management cost for all five building in the master file. Changing hourly rate will change all five cost estimates. Listed below are methods you can use to prepare a DCE for a new structure or building.
A. Adjust or change data in the "Master File" - B17, 18, 54, 56, & 70
This approach will basically change the existing CAA DCE. ANSTO may chose to change generic global data such as labor rates. This will change the DC for each of the 5 building (6 if you include Building XX.)
1 | Using the input tab as shown above, change parameters as needed. Again, it should be noted that changing data on the input tab in most cases will change the cost estimate for each of the five buildings originally estimated.
2 | Change parameters on the "Building Tab" to reflect attributes of the structure as needed. Note: Changes in the building tab will only impact the ones applicable for the building selected and not the other structures.
B. Prepare DCE for a 5 or 6 Structures at one time using the Master File as a template
This approach is recommended and allows ANSTO to use the existing Master File building work sheets to update 5 (or six if using Building XX) DCEs at one time.
1 | Select 5 (or 6) new structures for DCEs. Collect specific data for those structures..
2 | Change the workbook building names in the Master File to reflect the structures you will be estimating and save it under a new unique file name. Do not change the CAA Master file since this will serve as a "template" future estimates.
3 | Using the input tab (as shown above), change parameters as needed for each of the structure capturing unique attributes.. Again, it should be noted that changing data on the input tab in most cases will change the cost estimate for each of the structures being estimated.
4 | Review and change parameters on the "Building Tab" as needed. Note: Changing data in a building tab will not impact other 4 or 5 building in the new master file.
C. Using the Master File to add just one structure without impacting completed estimates of other structures.
This approach should be used if you want to just update one structure as a stand alone DCE. The five buildings in this workbook B17, 18, 54, 56, & 70 are considered the “Master File”. The DCE for each of these buildings share the same data from the “adjustments” and “Input tab”. If you change any data in these tabs, it has the potential to impact one or more of the other buildings. For example hourly labor rates are defined in the input tab and are used to determine management cost for all five building in the master file. Changing hourly rate will change all five cost estimates. To prepare an independent DCE and not impact the master file, follow the steps below.
How to add a new structure:
1. First determine which of the five buildings most closely resemble the building you want to Estimate.
2. Delete 4 of the five building tabs, keeping only the one that most closely resembles the one being estimated as shown below.
3. Rename the revised file and also rename the workbook tab to identify the structure (i.e. BXX) and save the file under a new name (i.e. BXX DCE). This allows you to prepare a building/structure without impacting the original master file.
4. Using the new file and spreadsheets you can change building specific data to most resemble the building being decommissioned.
Note: This approach ensures you still have all of the links necessary to revise and change parameters specific to the new structure being estimated.

## Adjustments
Class of Structure | Description | Adjustment | NOTE the adjustment factors, C2 - C4 should be adjusted based on estimator experience or experience gained from previously completed decommissioning projecs.
B1 | Lab/Rad | 50%
C1 | Industrial/Rad | 0
D1 | Non-Indust/Rad | -50%
D2 | Non-Indust/Non-Rad | -50%
NOTE: Class is extracted from the Project Time and Cost 2018 DCE
Productivity Loss Factors |  | Resp. | Rad/ |  | Protective
| Height | Protection | ALARA |  | Clothing |  | Breaks
| 15% | 38% | 15% |  | 23% |  | 8.33%
|  |  |  | Summary |  | Summary
All factors | 0.15 | 0.38 | 0.15 | 0.68 | 0.23 | 2.0664 | 0.0833 | 2.2385
All except Height |  | 0.38 | 0.15 | 0.53 | 0.23 | 1.8819 | 0.0833 | 2.0387
PCs, Rad and Respirator only |  | 0.38 | 0.15 | 0.53 | 0.23 | 1.8819 |  | 1.8819
All except Resp. | 0.15 |  | 0.15 | 0.3 | 0.23 | 1.599 | 0.0833 | 1.7322
Height, PCs and Rad only | 0.15 |  | 0.15 | 0.3 | 0.23 | 1.599 |  | 1.599
PCs, Rad and Break only |  |  | 0.15 | 0.15 | 0.23 | 1.4145 | 0.0833 | 1.5323
PCs and Rad only |  |  | 0.15 | 0.15 | 0.23 | 1.4145 |  | 1.4145
Height and Breaks only | 0.15 |  |  | 0.15 |  | 1.15 | 0.0833 | 1.2458
Height only | 0.15 |  |  | 0.15 |  | 1.15 | 0 | 1.15
Breaks only |  |  |  | 0 |  | 1 | 0.0833 | 1.0833
NOTE: Source: AIF/NESP-036
1. The adjustment factors applies are the estimators judgement for a class 4 estimate. If this were a bottoms up estimate the below productivity loss factors would be applied on a line item basis.
2. The base estimate used to develop the ANSTO estimates are considered to be for facilities designated as C1. A designation of B1 would require an increase in costs, in this case a 50% increase. This increase falls within the adjustments identified in the PLF table.
3. Since the base estimates are considered for C1 buildings, D1 and D2 facilities would require less effort. Estimators judgement was used to arrive at these adjustment factors.

## Inputs
Items highlighted in green can be adjusted as needed.
Year of Estimate: | 2026 | 160.8%
| From | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
Escalation | To | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026
|  | 60.81% | 58.01% | 53.53% | 48.63% | 46.06% | 42.56% | 39.1% | 37.03% | 35.3% | 32.71% | 30.22% | 28.16% | 27.08% | 23.55% | 15.91% | 9.761% | 6.399% | 3% | na | na | na | na | na | na | na | na | na | na
2008 | 100% | 100% | 60.81%
2009 | 1.77% | 101.8% | 58.01%
2010 | 2.92% | 104.7% | 53.53%
2011 | 3.3% | 108.2% | 48.63%
2012 | 1.76% | 110.1% | 46.06%
2013 | 2.45% | 112.8% | 42.56%
2014 | 2.49% | 115.6% | 39.1%
2015 | 1.51% | 117.4% | 37.03%
2016 | 1.28% | 118.9% | 35.3%
2017 | 1.95% | 121.2% | 32.71%
2018 | 1.91% | 123.5% | 30.22%
2019 | 1.61% | 125.5% | 28.16%
2020 | 0.85% | 126.5% | 27.08%
2021 | 2.86% | 130.2% | 23.55%
2022 | 6.59% | 138.7% | 15.91%
2023 | 5.6% | 146.5% | 9.761%
2024 | 3.16% | 151.1% | 6.399%
2025 | 3.3% | 156.1% | 3%
2026 | 3% | 160.8% | 0%
2027 | 2.684% | 165.1% | -2.614%
2028 | 2.684% | 169.6% | -5.159%
2029 | 2.684% | 174.1% | -7.638%
2030 | 2.684% | 178.8% | -10.05%
2031 | 2.684% | 183.6% | -12.4%
2032 | 2.684% | 188.5% | -14.69%
2033 | 2.684% | 193.6% | -16.92%
2034 | 2.684% | 198.8% | -19.09%
2035 | 2.684% | 204.1% | -21.21%
2036 | 2.684% | 209.6% | -23.27%
Waste Density | 100 | lbs/cuft
Exchange rate | 2025-10-16 12:11 | 1.54
| Rates |  | Actuals | Actuals | +4.8% (3.4% EBA +1.4% Band Level) | +4.8% (3.4% EBA +1.4% Band Level)
ANSTO LABOR RATES |  |  | Jul-Apr26 | May-Jun26. +3.4%
| CLASS | Band | FY26 |  | FY27 (Forecast) | FY28
(Forecast)
Resource Type | (SAP Name) | (EA name) | $/hour | $/hour | $/hour | $/hour
| CLASS1 | Band 1 | 45.99 | 47.55 | 48.2 | 50.51
| CLASS2 | Band 2 | 52.44 | 54.22 | 54.96 | 57.6
| CLASS3 | Band 3 | 63.63 | 65.79 | 66.68 | 69.88
| CLASS4 | Band 4 | 74.65 | 77.19 | 78.23 | 81.99
Decom Technician / Safety SME | CLASS5 | Band 5 | 86.32 | 89.25 | 90.46 | 94.8
Project Manager / Waste Management | CLASS6 | Band 6 | 104.63 | 108.19 | 109.65 | 114.91
Senior Project Manager / Characterization SME | CLASS7 | Band 7 | 123.09 | 127.28 | 129 | 135.19
Portfolio Manager | CLASS8 | Band 8 | 152.68 | 157.87 | 160.01 | 167.69
| CLASS9 | Band 9 | 186.99 | 193.35 | 193.35 | 199.92
| CLAS10 | Band 10 | 240.73 | 248.91 | 248.91 | 257.37
Waste Disposal rates
| 300 | Industrial Wastes
| 500 | Hazardous Waste
| 90 | /hr | Contaminated Waste Cleaning
| 0 | Low Level Solid Waste (Stored)
| 0 | Intermediate Level Solid waste
|  |  | US | dollars
|  | B1 | Rate Year | 2009 | 58.01% | C1 |  |  | D1 |  |  | D2
Equipment |  | Quantity | Rate | Equipment |  | Quantity | Equipment |  | Quantity | Equipment |  | Quantity
HEPA filter systems |  | 2 | 3598.14 | HEPA filter systems |  | 2 | HEPA filter systems |  | 2 | HEPA filter systems |  | 0
Replacement filters |  | 24 | 581.07 | Replacement filters |  | 24 | Replacement filters |  | 24 | Replacement filters |  | 0
Respirator |  | 12 | 259 | Respirator |  | 12 | Respirator |  | 12 | Respirator |  | 0
Rad/Vac wet-dry high eff. vacuum |  | 1 | 3879 | Rad/Vac wet-dry high eff. vacuum |  | 2 | Rad/Vac wet-dry high eff. vacuum |  | 1 | Rad/Vac wet-dry high eff. vacuum |  | 0
Rad/Vac wet-dry high eff. vacuum filters |  | 5 | 412 | Rad/Vac wet-dry high eff. vacuum filters |  | 5 | Rad/Vac wet-dry high eff. vacuum filters |  | 5 | Rad/Vac wet-dry high eff. vacuum filters |  | 0
Reciprocating Saws |  | 5 | 1252.26 | Reciprocating Saws |  | 5 | Reciprocating Saws |  | 5 | Reciprocating Saws |  | 0
Pneumatic chipping hammers |  | 2 | 1606.71 | Pneumatic chipping hammers |  | 2 | Pneumatic chipping hammers |  | 2 | Pneumatic chipping hammers |  | 2
Chipping hammer blades |  | 20 | 27.42 | Chipping hammer blades |  | 20 | Chipping hammer blades |  | 20 | Chipping hammer blades |  | 20
Purchase an air compressor: |  | 2 | 1723.44 | Purchase an air compressor: |  | 2 | Purchase an air compressor: |  | 2 | Purchase an air compressor: |  | 2
Jackhammer |  | 4 | 1417.11 | Jackhammer |  | 4 | Jackhammer |  | 4 | Jackhammer |  | 4
Jackhammer Chisels |  | 10 | 24.35 | Jackhammer Chisels |  | 10 | Jackhammer Chisels |  | 10 | Jackhammer Chisels |  | 10
Safety glasses |  | 15 | 8.6 | Safety glasses |  | 15 | Safety glasses |  | 15 | Safety glasses |  | 15
Fall protection - harness |  | 6 | 208 | Fall protection - harness |  | 6 | Fall protection - harness |  | 6 | Fall protection - harness |  | 0
Fall protection - lanyard |  | 6 | 367 | Fall protection - lanyard |  | 6 | Fall protection - lanyard |  | 6 | Fall protection - lanyard |  | 0
Hardhats |  | 15 | 35.5 | Hardhats |  | 15 | Hardhats |  | 15 | Hardhats |  | 15
Hard hat hearing protection |  | 15 | 37.6 | Hard hat hearing protection |  | 15 | Hard hat hearing protection |  | 15 | Hard hat hearing protection |  | 15
Trailer rental |  | 1 | 416 | Trailer rental |  | 1 | Trailer rental |  | 1 | Trailer rental |  | 1
Phone and computer hook-up |  | 1 | 250 | Phone and computer hook-up |  | 1 | Phone and computer hook-up |  | 1 | Phone and computer hook-up |  | 1
Instrumentation |  | 0 |  | Instrumentation |  | 0 | Instrumentation |  | 0 | Instrumentation |  | 0
Tractor loader, wheeled |  | 1 | 7160.5905 | Tractor loader, wheeled |  | 1 | Tractor loader, wheeled |  | 1 | Tractor loader, wheeled |  | 1
Wheeled Skid steer with conc. Hammer |  | 1 | 4421.3693 | Wheeled Skid steer with conc. Hammer |  | 1 | Wheeled Skid steer with conc. Hammer |  | 1 | Wheeled Skid steer with conc. Hammer |  | 1
Excavator |  | 1 | 28738.389 | Excavator |  | 1 | Excavator |  | 1 | Excavator |  | 1
Floor Shaver |  | 1 | 8000 | Floor Shaver |  | 1 | Floor Shaver |  | 1 | Floor Shaver |  | 0
Wall Shaver |  | 1 | 15000 | Wall Shaver |  | 1 | Wall Shaver |  | 1 | Wall Shaver |  | 0
Man lift |  | 2 | 4727.44 | Man lift |  | 2 | Man lift |  | 2 | Man lift |  | 0
Crane rental for building removal |  | 1 | 15600 | Crane rental for building removal |  | 1 | Crane rental for building removal |  | 1 | Crane rental for building removal |  | 0
|  | B1 | C1 | D1 | D2 |  | US | dollars
Consumables |  | Quantity | Quantity | Quantity | Quantity |  | Unit Cost
Coveralls |  | 2 | 2 | 2 | 0 | /man/day | 11
Hoods |  | 0.1 | 0.1 | 0.1 | 0 | /man/day | 0
Shoe covers |  | 4 | 4 | 4 | 0 | /man/day | 0.94
Latex gloves |  | 4 | 4 | 4 | 0 | /man/day | 0.94
Rubber overshoes |  | 0.01 | 0.01 | 0.01 | 0 | /man/day | 3
Gloves |  | 0.01 | 0.01 | 0.01 | 0 | /man/day | 2
Dosimeters |  | 1 | 1 | 1 | 0 | /man/year | 200
TLDs |  | 1 | 1 | 1 | 0 | /man/mo | 3
Bioassays |  | 2 | 2 | 2 | 0 | /man/year | 250
(Bioassays for aver. crew & management)
Small Tools - 2% of total labor costs = |  |  |  |  | 2%
HP Equipment Replacement - 5% of total labor |  |  |  |  | 5%
DGC OH &P on equipment and materials |  |  |  |  | 8%
1 cubic foot = | 0.02832 | cubic meter | 1 square foot = | 0.0929 | square meter | 1 foot = | 0.3048 | meters
1cubic foot/square foot = |  | 0.30484 | cubic meter/square meter | [6 empty] | B17
1cubic foot/foot = | 0.092913 | cubic meter/meter
Building Information for B17, B18, 54, 56 & 70
Building B17 | 17A | D1 | Non-Indust/Rad | 17B = | C1 | Industrial/Rad
Number of floors | 2 |  |  |  | 17A | 17B
Floor Area | 100 | sqft |  |  | 704 | 158
Project Duration | 180 | days |  |  |  | 158
Decontamination Duration | 90 | days |  |  | 704 |  | 704 | 7577.7962 | sqft
Contaminated removal adjustment |  | -50% | Judgement due to complexity of the facility
Length of asbestos insulated pipe |  | 0 | ft. (estimated) | 0
One crew is based 12 laborers, if reasonable, leave at 1 |  | 1 | for all removal |  | 12 | LABORERS
Building B18 | D2 | Non-Indust/Non-Rad
Total Area = | 6900 | m^2 | 74271.0139 | sqft
Building 18 = | 1900 | m^2 | 20451.4386 | sqft
Building 48 = | 403 | m^2 | 4337.8578 | sqft
Areas were derived from Google Earth
B18
Assumptions: |  |  | 35.3147 | ft^3 per m^3
Removal depth = | 1 | m
Percent Clean | 50%
Project Duration | 90 | days
Clean Volume = | 3450 | m^3 | 121835.715 | ft^3
Contaminated Volume = | 3450 | m^3 | 121835.715 | ft^3
Contaminated removal adjustment |  | -50% | Judgement due to complexity of the facility
Length of asbestos insulated pipe |  | 0 | ft. (estimated)
One crew is based 12 laborers, if sufficient leave at 1. |  | 1 | for all removal |  | 12 | LABORERS
Building B54 | B1 | Lab/Rad
Total area = | 1204 | m^2 | 12959.7537 | sqft
Project Duration | 180 | work days (per PT&C report) |  | 36 | weeks | 252 | total days
Contaminated removal adjustment |  | 50% | Due to complexity of the facility
Length of asbestos insulated pipe |  | 2000 | ft. (estimated) | 609.6 | meters
Assume two crews; therefor apply a multiplier of |  | 2 | for all removal | Based on 30.7 FTEs per PT&C report |  |  | 24 | LABORERS
Building B56 | B1 | Non-Indust/Rad
Total area = | 1557 | m^2 | 16759.4157 | sqft
Project Duration | 75 | work days (per PT&C report) |  | 15 | weeks | 105 | total days
Contaminated removal adjustment |  | 50% | Simpler building to remove
Length of asbestos insulated pipe |  | 0 | ft. (estimated) | 0
Assume a crew of 9; therefor apply a multiplier of |  | 2 | for all removal | Based on 8.6 FTEs per PT&C report |  |  | 24 | LABORERS
Building B70 | D2 | Non-Indust/Non-Rad
Total area = | 152.2139 | m^2 | 1638.4175 | sqft | 24670 | mm = | 24.67 | m | X | 6170 | mm = | 6.17
Project Duration | 60 | Estimated |  | 12 | weeks | 84 | total days
Contaminated removal adjustment |  | -50% | Simpler building to remove
Length of asbestos insulated pipe |  | 1000 | ft. (estimated) | 304.8
Assume a crew of 9; therefor apply a multiplier of |  | 0.75 | for all removal | Estimated |  | 9 | LABORERS
Building Blank | B1 | Non-Indust/Rad
Total area = | 1557 | m^2 | 16759.4157 | sqft
Project Duration | 75 | work days (per PT&C report) |  | 15 | weeks | 105 | total days
Contaminated removal adjustment |  | 50% | Simpler building to remove
Length of asbestos insulated pipe |  | 0 | ft. (estimated) | 0
Assume a crew of 9; therefor apply a multiplier of |  | 2 | for all removal | Based on 8.6 FTEs per PT&C report |  |  | 24 | LABORERS

## Comparison
COMPARISON OF ESTIMATES BETWEEN 2018 PT&C ESITMATE AND CAA ESTIMATE
Facility Name/Description | Gross Area (SM) | Facility Class Adj | Total Cost (FY18 AU$) | Unit Cost (AU$/SM) | Total Cost (FY26 AU$) | Unit Cost (AU$/SM) | CAA Estimate, 2026AU$ | Delta
B17A - Nuclear Services (Material Storage) | 158 | D1 | [5 empty] | Variance from PT&C and CAA
B17B - Nuclear Operations (Workshop) | 704 | C1 | [5 empty] | Delta | % | Item
B17 | 862 |  | 1931756.69 | 2241.017 | 2515594.051 | 2918.3226 | 2665719.484 | 150125.433 | 5.968% | B17
B18 |  | D2 | 3579999.25 |  | 4661987.123 |  | 5140902.648 | 478915.5243 | 10.27% | B18
B54 |  | B1 | 12388722 |  | 16132981.72 |  | 14159309.17 | -1973672.547 | -12.23% | B54
B56 |  | B1 | 13866487.4522 |  | 18057374.16 |  | 14150956.13 | -3906418.028 | -21.63% | B56
B70 |  | D2 | 487422.3 |  | 634736.5817 |  | 765186.9129 | 130450.3312 | 20.55% | B70

## WBS Summary
ESTIMATED COSTS BY WORK BREAKDOWN STRUCTURE - B17, 18, 54 ,56 & 70
WBS | Description | LSA Waste (M3) | Hazardous Waste Vol (M3) | Mixed Waste Vol (M3) | Clean Waste Vol. (M3) | Mat's, Consumables & Equip. | Labor Cost | LSA Waste Cost (TBD) | Hazardous Waste Cost | Mixed Waste Cost | Clean Waste Cost | Total Cost
1.0 | Building B17
1.1 | Project Management
1.1.1 | Staff | [5 empty] | 268756.2 |  |  |  |  | 268756.2
1.1.2 | Equipment, Materials & Consumables |  |  |  |  | 649056.6154 | [5 empty] | 649056.6154
1.2 | Project Planning
1.2.1 | Procedure Development | [5 empty] | 22935.2 |  |  |  |  | 22935.2
1.2.2 | QA and Safety Documents | [5 empty] | 22935.2 |  |  |  |  | 22935.2
1.2.3 | Mobilization | [5 empty] | 123378.7 |  |  |  |  | 123378.7
1.3 | Preliminary Site Investigation | [10 empty] | 0
1.3.1 | Decontamination Readiness Review | [5 empty] | See Note |  |  |  |  | 0
1.3.2 | Site Prep | [5 empty] | 45402.544 |  |  |  |  | 45402.544
1.4 | Detailed Characterization | [5 empty] | 74430.4 |  |  |  |  | 74430.4
1.5 | Decontamination
1.5.1 | Asbestos Removal | [5 empty] | 0 |  |  |  |  | 0
1.5.2 | Remove systems and Components | [5 empty] | 365585.2834 |  |  |  |  | 365585.2834
1.5.3 | Decontaminate Structure | 15.9602 | 0.24497 | 2.0287 | 155.4977 |  | 156964.7554 |  |  |  |  | 156964.7554
1.5.4 | Final Survey | [5 empty] | 170610.1206 |  |  |  |  | 170610.1206
1.6 | Site Remediation |  |  |  | 542.6954
1.6.1 | Remove Building | [5 empty] | 320487.6499 |  |  |  |  | 320487.6499
1.6.2 | Grade and Seed | [5 empty] | 22280.8551 |  |  |  |  | 22280.8551
1.6.3 | Backfill | [5 empty] | 51041.1686 |  |  |  |  | 51041.1686
1.7 | Waste Disposal | [7 empty] | 2007.338 |  | 369847.4532 | 371854.7912
| TOTAL | 15.9602 | 0.24497 | 2.0287 | 698.1931 | 649056.6154 | 1644808.077 | 0 | 2007.338 | 0 | 369847.4532 | 2665719.484
NOTE: Cost included in overall staff costs
WBS | Description | LSA Waste (M3) | Hazardous Waste Vol (M3) | Mixed Waste Vol (M3) | Clean Waste Vol. (M3) | Mat's, Consumables & Equip. | Labor Cost | LSA Waste Cost (TBD) | Hazardous Waste Cost | Mixed Waste Cost | Clean Waste Cost | Total Cost
1.0 | Building B18
1.1 | Project Management
1.1.1 | Staff | [5 empty] | 134378.1 |  |  |  |  | 134378.1
1.1.2 | Equipment, Material & Consumables |  |  |  |  | 461768.1684 | [5 empty] | 461768.1684
1.2 | Project Planning
1.2.1 | Procedure Development | [5 empty] | 22935.2 |  |  |  |  | 22935.2
1.2.2 | QA and Safety Documents | [5 empty] | 22935.2 |  |  |  |  | 22935.2
1.2.3 | Mobilization | [5 empty] | 123378.7 |  |  |  |  | 123378.7
1.3 | Preliminary Site Investigation | [10 empty] | 0
1.3.1 | Decontamination Readiness Review | [5 empty] | See Note 1 |  |  |  |  | 0
1.3.2 | Site Prep | [5 empty] | 44658.24 |  |  |  |  | 44658.24
1.4 | Detailed Characterization | [5 empty] | 297721.6 |  |  |  |  | 297721.6
1.5 | Decontamination
1.5.1 | Remove Soil and Asphalt | 3450 |  |  | 3450 |  | 260100.7498 |  |  |  |  | 260100.7498
1.5.2 | Final Survey | [5 empty] | 1672173.057 |  |  |  |  | 1672173.057
1.6 | Site Remediation
1.6.1 | Remove Building | [5 empty] | See Note 2 |  |  |  |  | 0
1.6.2 | Grade and Seed | [5 empty] | 109188.8494 |  |  |  |  | 109188.8494
1.6.3 | Backfill | [5 empty] | 164127.7735 |  |  |  |  | 164127.7735
1.7 | Waste Disposal | [9 empty] | 1827537.01 | 1827537.01
| TOTAL | 3450 | 0 | 0 | 3450 | 461768.1684 | 2851597.47 | 0 | 0 | 0 | 1827537.01 | 5140902.648
NOTE: Cost included in overall staff costs
WBS | Description | LSA Waste (M3) | Hazardous Waste Vol (M3) | Mixed Waste Vol (M3) | Clean Waste Vol. (M3) | Mat's, Consumables & Equip. | Labor Cost | LSA Waste Cost (TBD) | Hazardous Waste Cost | Mixed Waste Cost | Clean Waste Cost | Total Cost
1.0 | Building B54
1.1 | Project Management
1.1.1 | Staff | [5 empty] | 614958.12 |  |  |  |  | 614958.12
1.1.2 | Equipment, Material & Consumables |  |  |  |  | 1975720.329 | [5 empty] | 1975720.329
1.2 | Project Planning
1.2.1 | Procedure Development | [5 empty] | 22935.2 |  |  |  |  | 22935.2
1.2.2 | QA and Safety Documents | [5 empty] | 22935.2 |  |  |  |  | 22935.2
1.2.3 | Mobilization | [5 empty] | 225123.7 |  |  |  |  | 225123.7
1.3 | Preliminary Site Investigation | [10 empty] | 0
1.3.1 | Decontamination Readiness Review | [5 empty] | See Note |  |  |  |  | 0
1.3.2 | Site Prep | [5 empty] | 44658.24 |  |  |  |  | 44658.24
1.4 | Detailed Characterization | [5 empty] | 446582.4 |  |  |  |  | 446582.4
1.5 | Decontamination | 30.3567 | 328.6629 | 3.4695 | 265.9365
1.5.1 | Asbestos Removal | [5 empty] | 880073.3645 |  |  |  |  | 880073.3645
1.5.2 | Remove systems and Components | [5 empty] | 3751403.533 |  |  |  |  | 3751403.533
1.5.3 | Decontaminate Structure | [5 empty] | 2123535.756 |  |  |  |  | 2123535.756
1.5.4 | Final Survey | [5 empty] | 583564.1624 |  |  |  |  | 583564.1624
1.6 | Site Remediation |  |  |  | 1075.2731
1.6.1 | Remove Building | [5 empty] | 1644320.158 |  |  |  |  | 1644320.158
1.6.2 | Remove Hot Cell | [5 empty] | 544168.8938 |  |  |  |  | 544168.8938
1.6.3 | Grade and Seed | [5 empty] | 76210.652 |  |  |  |  | 76210.652
1.6.4 | Backfill | [5 empty] | 174583.9972 |  |  |  |  | 174583.9972
1.7 | Waste Disposal | [7 empty] | 290166.0198 | 27902.7608 | 710466.6813 | 1028535.462
| TOTAL | 30.3567 | 328.6629 | 3.4695 | 1341.2095 | 1975720.329 | 11155053.38 | 0 | 290166.0198 | 27902.7608 | 710466.6813 | 14159309.17
NOTE: Cost included in overall staff costs
WBS | Description | LSA Waste (M3) | Hazardous Waste Vol (M3) | Mixed Waste Vol (M3) | Clean Waste Vol. (M3) | Mat's, Consumables & Equip. | Labor Cost | LSA Waste Cost (TBD) | Hazardous Waste Cost | Mixed Waste Cost | Clean Waste Cost | Total Cost
1.0 | Building B56
1.1 | Project Management
1.1.1 | Staff | [5 empty] | 256232.55 |  |  |  |  | 256232.55
1.1.2 | Equipment, Material & Consumables |  |  |  |  | 1843799.953 | [5 empty] | 1843799.953
1.2 | Project Planning
1.2.1 | Procedure Development | [5 empty] | 22935.2 |  |  |  |  | 22935.2
1.2.2 | QA and Safety Documents | [5 empty] | 22935.2 |  |  |  |  | 22935.2
1.2.3 | Mobilization | [5 empty] | 225123.7 |  |  |  |  | 225123.7
1.3 | Preliminary Site Investigation | [10 empty] | 0
1.3.1 | Decontamination Readiness Review | [5 empty] | See Note |  |  |  |  | 0
1.3.2 | Site Prep | [5 empty] | 44658.24 |  |  |  |  | 44658.24
1.4 | Detailed Characterization | [5 empty] | 297721.6 |  |  |  |  | 297721.6
1.5 | Decontamination | 39.257 | 425.0234 | 4.4867 | 343.9062
1.5.1 | Asbestos Removal | [5 empty] | 0 |  |  |  |  | 0
1.5.2 | Remove systems and Components | [5 empty] | 4851275.167 |  |  |  |  | 4851275.167
1.5.3 | Decontaminate Structure | [5 empty] | 2082904.467 |  |  |  |  | 2082904.467
1.5.4 | Final Survey | [5 empty] | 754658.9708 |  |  |  |  | 754658.9708
1.6 | Site Remediation |  |  |  | 1390.5317
1.6.1 | Remove Building | [5 empty] | 2126417.348 |  |  |  |  | 2126417.348
1.6.2 | Grade and Seed | [5 empty] | 98554.805 |  |  |  |  | 98554.805
1.6.3 | Backfill | [5 empty] | 225770.1691 |  |  |  |  | 225770.1691
1.7 | Waste Disposal | [7 empty] | 375239.612 | 3961.1919 | 918767.9592 | 1297968.763
| TOTAL | 39.257 | 425.0234 | 4.4867 | 1734.4379 | 1843799.953 | 11009187.42 | 0 | 375239.612 | 3961.1919 | 918767.9592 | 14150956.13
NOTE: Cost included in overall staff costs
WBS | Description | LSA Waste (M3) | Hazardous Waste Vol (M3) | Mixed Waste Vol (M3) | Clean Waste Vol. (M3) | Mat's, Consumables & Equip. | Labor Cost | LSA Waste Cost (TBD) | Hazardous Waste Cost | Mixed Waste Cost | Clean Waste Cost | Total Cost
1.0 | Building B70
1.1 | Project Management
1.1.1 | Staff | [5 empty] | 71961.96 |  |  |  |  | 71961.96
1.1.2 | Equipment, Material & Consumables |  |  |  |  | 188017.7686 | [5 empty] | 188017.7686
1.2 | Project Planning
1.2.1 | Procedure Development | [5 empty] | 11467.6 |  |  |  |  | 11467.6
1.2.2 | QA and Safety Documents | [5 empty] | 11467.6 |  |  |  |  | 11467.6
1.2.3 | Mobilization | [5 empty] | 32130 |  |  |  |  | 32130
1.3 | Preliminary Site Investigation | [10 empty] | 0
1.3.1 | Decontamination Readiness Review | [5 empty] | See Note |  |  |  |  | 0
1.3.2 | Site Prep | [5 empty] | 44658.24 |  |  |  |  | 44658.24
1.4 | Detailed Characterization | [10 empty] | 0
1.5 | Decontamination
1.5.1 | Asbestos Removal | [5 empty] | 165013.7558 |  |  |  |  | 165013.7558
1.5.2 | Remove systems and Components | [5 empty] | 35618.372 |  |  |  |  | 35618.372
1.5.3 | Decontaminate Structure |  | 41.5507 |  | 33.6206 | [6 empty] | 0
1.5.4 | Final Survey | [5 empty] | 27666.0851 |  |  |  |  | 27666.0851
1.6 | Site Remediation
1.6.1 | Remove Building | [5 empty] | 25985.0897 |  |  |  |  | 25985.0897
1.6.2 | Remove Hot Cell | [5 empty] | 0
6.2 | Grade and Seed | [5 empty] | 3613.0567 |  |  |  |  | 3613.0567
1.6.3 | Backfill | [5 empty] | 8276.8203 |  |  |  |  | 8276.8203
1.7 | Waste Disposal | [7 empty] | 36683.8052 | 12807.0714 | 89819.688 | 139310.5647
| TOTAL | 0 | 41.5507 | 0 | 33.6206 | 188017.7686 | 437858.5796 | 0 | 36683.8052 | 12807.0714 | 89819.688 | 765186.9129
NOTE: Cost included in overall staff costs
WBS | Description | LSA Waste (M3) | Hazardous Waste Vol (M3) | Mixed Waste Vol (M3) | Clean Waste Vol. (M3) | Mat's, Consumables & Equip. | Labor Cost | LSA Waste Cost (TBD) | Hazardous Waste Cost | Mixed Waste Cost | Clean Waste Cost | Total Cost
1.0 | Building Blank (XX)
1.1 | Project Management
1.1.1 | Staff | [5 empty] | 256232.55 |  |  |  |  | 256232.55
1.1.2 | Equipment, Material & Consumables |  |  |  |  | 1843799.953 | [5 empty] | 1843799.953
1.2 | Project Planning
1.2.1 | Procedure Development | [5 empty] | 22935.2 |  |  |  |  | 22935.2
1.2.2 | QA and Safety Documents | [5 empty] | 22935.2 |  |  |  |  | 22935.2
1.2.3 | Mobilization | [5 empty] | 225123.7 |  |  |  |  | 225123.7
1.3 | Preliminary Site Investigation | [10 empty] | 0
1.3.1 | Decontamination Readiness Review | [5 empty] | See Note |  |  |  |  | 0
1.3.2 | Site Prep | [5 empty] | 44658.24 |  |  |  |  | 44658.24
1.4 | Detailed Characterization | [5 empty] | 297721.6 |  |  |  |  | 297721.6
1.5 | Decontamination
1.5.1 | Asbestos Removal | [5 empty] | 0 |  |  |  |  | 0
1.5.2 | Remove systems and Components | [5 empty] | 4851275.167 |  |  |  |  | 4851275.167
1.5.3 | Decontaminate Structure | [5 empty] | 2082904.467 |  |  |  |  | 2082904.467
1.5.4 | Final Survey | [5 empty] | 754658.9708 |  |  |  |  | 754658.9708
1.6 | Site Remediation
1.6.1 | Remove Building | [5 empty] | 2126417.348 |  |  |  |  | 2126417.348
1.6.2 | Grade and Seed | [5 empty] | 98554.805 |  |  |  |  | 98554.805
1.6.3 | Backfill | [5 empty] | 225770.1691 |  |  |  |  | 225770.1691
1.7 | Waste Disposal | [7 empty] | 375239.612 | 3961.1919 | 918767.9592 | 1297968.763
| TOTAL | 0 | 0 | 0 | 0 | 1843799.953 | 11009187.42 | 0 | 375239.612 | 3961.1919 | 918767.9592 | 14150956.13
NOTE: Cost included in overall staff costs

## Building B17
B 17 DATA - Data highlighted in GREEN can be adjusted as needed
Uncorrected Duration
[8 empty] | Crew | (No. of Hours) | Prod. Factor | Adjusted Duration (hrs) | Man-hours | LSA Waste Disp. Vol (cm) | Hazardous Waste Vol (cm) |  | Mixed Waste Volume (cm) | Clean Waste Volume (cm) | Materials, Consumables & Equipment | Labor Cost | LSA Waste Costs | Hazardous Waste Costs | LSA Waste Costs | Mixed Waste Costs | Clean Waste Costs | Total Cost
1.0 | Building B17 | [9 empty] | 631 | 3073 | 15.9602 | 0.24497 |  | 2.0287 | 698.1931 | 649056.6154 | 1644808.077 |  | 2007.338 |  |  | 369847.4532 | 2665719.484
1.1 | Project Management | [16 empty] | 649056.6154 | 268756.2 | [5 empty] | 917812.8154
1.1.1 | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
| Portfolio Manager |  |  | 1 | 157.87 | 180 | 0.25 | 56833.2 | 450
| Senior Project Manager / Characterization SME |  |  | 1 | 127.28 | 180 | 0.5 | 114552 | 900
| Project Manager / Waste Management |  |  | 1 | 108.19 | 180 | 0.5 | 97371 | 900
| Decom Technician / Safety SME |  |  | 0 | 89.25 | 180 | 1 | 0 | 1800
|  |  |  | 3 |  |  |  | 268756.2 | 4050
1.1.2 | Equipment & Materials
US
|  | Equipment |  |  | Quantity | Rate | Escalated Cost
|  | HEPA filter systems |  |  | 2 | 3598.14 | 11371.1239
|  | Replacement filters |  |  | 24 | 581.07 | 22036.1152
|  | Respirator |  |  | 12 | 259 | 4911.0725
|  | Rad/Vac wet-dry high eff. vacuum |  |  | 2 | 3879 | 12258.7197
|  | Rad/Vac wet-dry high eff. vacuum filters |  |  | 5 | 412 | 3255.0867
|  | Reciprocating Saws |  |  | 5 | 1252.26 | 9893.7254
|  | Pneumatic chipping hammers |  |  | 2 | 1606.71 | 5077.6508
|  | Chipping hammer blades |  |  | 20 | 27.42 | 866.5483
|  | Purchase an air compressor: |  |  | 2 | 1723.44 | 5446.5501
|  | Jackhammer |  |  | 4 | 1417.11 | 8956.9241
|  | Jackhammer Chisels |  |  | 10 | 24.35 | 384.7639
|  | Safety glasses |  |  | 15 | 8.6 | 203.838
|  | Fall protection - harness |  |  | 6 | 208 | 1972.0137
|  | Fall protection - lanyard |  |  | 6 | 367 | 3479.4665
|  | Hardhats |  |  | 15 | 35.5 | 841.4241
|  | Hard hat hearing protection |  |  | 15 | 37.6 | 891.1985
|  | Trailer rental |  |  | 1 | 416 | 657.3379
|  | Phone and computer hook-up |  |  | 1 | 250 | 395.0348
|  | Industrial hygiene instrumentation, calibration and hygienists - 1% of total activity $. |  |  | 0 |  | 0
|  | Tractor loader, wheeled |  |  | 1 | 7160.5905 | 11314.7295
|  | Wheeled Skid steer with conc. Hammer |  |  | 1 | 4421.3693 | 6986.3788
|  | Excavator |  |  | 1 | 28738.389 | 45410.6542
|  | Floor Shaver |  |  | 1 | 8000 | 12641.1134
|  | Wall Shaver |  |  | 1 | 15000 | 23702.0876
|  | Man lift |  |  | 2 | 4727.44 | 14940.0263
|  | Crane rental for building removal |  |  | 1 | 15600 | 24650.1711
232543.7549
US
|  | Consumables |  | Quantity |  | Duration |  | # workers | quantity | Unit Qty | Unit Cost | Escalated Cost
|  | Coveralls |  | 2 | /man/day | 90 | days | 12 | 2160 | 1 | 11 | 37544.1067
|  | Hoods |  | 0.1 | /man/day | 90 | days | 12 | 108 | 1 | 0 | 0
|  | Shoe covers |  | 4 | /man/day | 90 | days | 12 | 4320 | 1 | 0.94 | 6416.6291
|  | Latex gloves |  | 4 | /man/day | 90 | days | 12 | 4320 | 1 | 0.94 | 6416.6291
|  | Rubber overshoes |  | 0.01 | /man/day | 90 | days | 12 | 10.8 | 1 | 3 | 51.1965
|  | Gloves |  | 0.01 | /man/day | 90 | days | 12 | 10.8 | 1 | 2 | 34.131
|  | Dosimeters |  | 1 | /man/year | 0.33333 | year | 12 | 4 | 1 | 200 | 1264.1113
|  | TLDs |  | 1 | /man/mo | 3 | month | 12 | 36 | 1 | 3 | 170.655
|  | Bioassays |  | 2 | /man/year | 1 | year | 12 | 24 | 1 | 250 | 9480.835
|  | (Bioassays for aver. crew & management) | [9 empty] | 61378.2939
|  | Small Tools - 2% of total labor costs = |  |  |  | 1376051.877 | labor costs x | 2% | = | 27521.0375
|  | HP Equipment Replacement - 5% of total labor |  |  |  | 1376051.877 | labor costs x | 5% | = | 68802.5939
|  | DGC OH &P on equipment and materials |  |  |  | 390245.6802 |  | 8% | = | 31219.6544
1.2 | Project Planning | [7 empty] | 415 |  | 415 | 1785 | [6 empty] | 169249.1 | [5 empty] | 169249.1
1.2.1 | Procedure Development and Review | [7 empty] | 160 | 1 | 160 | 240 | [6 empty] | 22935.2
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 89.25 | 80 | 1 | 14280 | 160
|  |  | Project Manager |  |  | 1 | 108.19 | 80 | 1 | 8655.2 | 80
[6 empty] | 3 |  | 160 |  | 22935.2 | 240
1.2.2 | Preparation of QA and Safety Documents | [7 empty] | 160 | 1 | 160 | 240 | [6 empty] | 22935.2
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 89.25 | 80 | 1 | 14280 | 160
|  |  | Project Manager |  |  | 1 | 108.19 | 80 | 1 | 8655.2 | 80
[6 empty] | 3 |  | 160 |  | 22935.2 | 240
1.2.3 | Site Mobilization and General Employee Training (GET) | [7 empty] | 95 | 1 | 95 | 1305 | [6 empty] | 123378.7
|  | 1.2.3.1 | Site Mobilization | [5 empty] | 40 | 1 | 40 | 480 | [6 empty] | 42840
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 12 | Decom Technician / Safety SME |  | 89.25 | 1071
|  |  | Receipt of material and equipment |  |  | 16 | hr
|  |  | Staging of equipment |  |  | 8 | hr
|  |  | Set up office and amenities |  |  | 12 | hr
|  |  | Familiarize staff with facility |  |  | 4 | hr
[6 empty] | 40 | hr
|  |  | Total Cost = |  | 40 | x | 1071 | 42840
|  | 1.2.3.2 | General Employee Training (All proj. management and 3 crews of 4) | [5 empty] | 55 | 1 | 55 | 825 | [5 empty] | 30030 | 80538.7
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Portfolio Manager |  | 157.87 | 157.87
|  |  | 1 | Senior Project Manager / Characterization SME |  | 127.28 | 127.28
|  |  | 1 | Project Manager / Waste Management |  | 108.19 | 108.19
|  |  | 12 | Decom Technician / Safety SME |  | 89.25 | 1071
|  |  | 15 |  |  |  | 1464.34
[8 empty] | Number | Test | Labor | Total
[7 empty] | Unit Cost | Required | Cost | Costs | Cost
|  |  | In-Vivo |  |  |  | 600 | 15 | 9000 | 0 | 9000
|  |  | In-Vitro |  |  |  | 350 | 15 | 5250 | 0 | 5250
|  |  | Physical @ |  | 4 | hour and | 150 | 15 | 2250 | 5857.36 | 8107.36
|  |  | Resp. Tests |  | 1 | hour and | 50 | 15 | 750 | 1464.34 | 2214.34
|  |  | Resp Fit Tests |  | 1 | hour and | 25 | 15 | 375 | 1464.34 | 1839.34
|  |  | Blood Tests |  | 1 | hour and | 125 | 15 | 1875 | 1464.34 | 3339.34
|  |  | OSHA recertification |  | 8 | hour |  |  |  | 11714.72 | 11714.72
|  |  | Site specific 1 week of training |  | 40 | hour |  |  |  | 58573.6 | 58573.6
[5 empty] | 55 |  |  |  | 19500 | 80538.7 | 100038.7
1.3 | Preliminary Site Investigation | [7 empty] | 176 |  | 176 | 488 | [6 empty] | 45402.544 | using this for 1.3.1 |  |  |  |  | 45402.544
1.3.1 | Decontamination Readiness Review - (Contractor staff cost included in Undistributed Costs) | [7 empty] | 80 | 1 | 80
1.3.2 | Site Preparation | [5 empty] | A |  | 96 | 1 | 96 | 488 | [5 empty] | 1.3.2 | 45402.544
| 1.3.2.1 | Initial Site Survey |  |  |  |  | A |  | 16 | 1 | 16 | 88 | [6 empty] | 8187.344
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1.1 | 6283.2 | 70.4
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1.1 | 1904.144 | 17.6
[6 empty] | 5 |  | 32 |  | 8187.344 | 88
| 1.3.2.2 | Setup work areas | [6 empty] | 32 |  | 32 | 160 | [6 empty] | 14886.08
| 1.3.2.2.1 | Setup boundaries, install HEPA filters & seal off openings |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.2.2 | Establish staging area |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.3 | Setup Rad. and Non-Rad. segregation and packaging stations |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.4 | Isolate Bldg B17 | [6 empty] | 32 |  | 32 | 160 | [6 empty] | 14886.08
| 1.3.2.4.1 | Electrical |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.4.2 | Piping |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
1.4 | Detailed Charaterisation | [7 empty] | 40 | 1 | 40 | 800 | [6 empty] | 74430.4 | Charterization |  |  |  |  | 74430.4
|  |  |  | Estimated Duration | 40 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 160 | 1 | 57120 | 640
|  |  | Project Manager |  |  | 1 | 108.19 | 160 | 1 | 17310.4 | 160
[6 empty] | 5 |  | 320 |  | 74430.4 | 800
1.5 | Decontamination | [11 empty] | 15.9602 | 0.24497 |  | 2.0287 | 155.4977 |  | 693160.1593 | [5 empty] | 693160.1593
[6 empty] | Removal Rate, Australian dollars | Units | Cost | Adjustment | Clean Disposal volume rate | Units | Clean Disposal Volume, cubic meters | LLW Disposal volume rate | Units | LLW Disposal Volume, cubic meters | Hazardous Disposal volume rate | Units | Hazardous Disposal Volume, cubic meters | Mixed Disposal volume rate | Units | Mixed Disposal Volume, cubic meters
1.5.1 | Asbestos Removal
| 1.5.1.1 | Remove asbestos pipe insulation |  |  |  | 721.845 | /meter |  |  | 0.046153 | meter^3/meter
| 1.5.1.2 | Remove asbestos tile |  |  |  | 58.2518 | /m^2 |  |  | 0.030615 | meter^3/meter^2
1.5.2 | Remove systems and Components
| 1.5.2.1 | Sys. Clean |  |  |  | 603.9881 | /m^2 | 212603.8282 | -50% | 0.21097 | meter^3/meter^2 | 148.5242
| 1.5.2.2 | Sys. LLW |  |  |  | 414.589 | /m^2 | 145935.3138 | -50% |  |  |  | 0.021826 | meter^3/meter^2 | 15.3656
| 1.5.2.3 | Sys. Hazardous |  |  |  | 11.1968 | /m^2 | 3941.2713 | -50% | [6 empty] | 0.00034797 | meter^3/meter^2 | 0.24497
| 1.5.2.4 | Sys. Mixed |  |  |  | 8.8207 | /m^2 | 3104.8701 | -50% | [9 empty] | 0.0028817 | meter^3/meter^2 | 2.0287 | meter^3/meter^2
365585.2834
1.5.3 | Decontaminate Structure
| 1.5.3.1 | Decon Clean |  |  |  | 18.15 | /m^2 | 6388.8175 | -50% | 0.0099056 | meter^3/meter^2 | 6.9736
| 1.5.3.2 | Decon Contaminated |  |  |  | 427.7726 | /m^2 | 150575.9378 | -50% |  |  |  | 0.0008445 | meter^3/meter^2 | 0.59453
156964.7554
1.5.4 | Final Survey |  |  |  |  | 242.3439 | /m^2 | 170610.1206
1.6 | Site Remediation | [15 empty] | 542.6954 |  | 393809.6736 | [5 empty] | 393809.6736
1.6.1 | Remove Building |  |  |  |  | 455.2381 | /m^2 | 320487.6499 |  | 0.77087 | cuft/sq ft | 542.6954
1.6.2 | Grade and seed (assume an area 2X building footprint) |  |  |  |  | 15.8245 | /m^2 | 22280.8551
1.6.3 | Backfill (assume building footprint x 10' deep) |  |  |  |  | 23.7866 | /cuft | 51041.1686
393809.6736
1.7 | Waste Disposal |  |  |  |  | 0.028317 | 100 | lbs/cuft | [12 empty] | 2007.338 |  |  | 369847.4532 | 371854.7912
[5 empty] | Volume, cuft | Volume, m^3 | Tonnes | Rate | Cost
|  | Sys. Clean |  |  | 24656.4969 | 698.1931 | 1232.8248 | 300 | 369847.4532
|  | Sys. LLW |  |  | 563.6287 | 15.9602 | 28.1814
|  | Sys. Hazardous |  |  | 71.6424 | 2.0287 | 3.5821 | 500 | 1791.0592
|  | Sys. Mixed |  |  | 8.6512 | 0.24497 | 0.43256 | 500 | 216.2788

## Building B54
B 54 DATA - Data highlighted in GREEN can be adjusted as needed
Uncorrected Duration
[8 empty] | Crew | (No. of Hours) | Prod. Factor | Adjusted Duration (hrs) | Man-hours | LSA Waste Disp. Vol (cm) | Hazardous Waste Vol (cm) |  | Mixed Waste Volume (cm) | Clean Waste Volume (cm) | Materials, Consumables & Equipment | Labor Cost | LSA Waste Costs | Hazardous Waste Costs | LSA Waste Costs | Mixed Waste Costs | Clean Waste Costs | Total Cost
1.0 | Building B54 | [9 empty] | 631 | 8205 | 30.3567 | 328.6629 |  | 3.4695 | 1341.2095 | 1975720.329 | 11155053.38 |  | 290166.0198 |  | 27902.7608 | 710466.6813 | 14159309.17
1.1 | Project Management | [16 empty] | 1975720.329 | 614958.12 | [5 empty] | 2590678.449
1.1.1 | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
| Portfolio Manager |  |  | 1 | 157.87 | 252 | 1 | 318265.92 | 2520
| Senior Project Manager / Characterization SME |  |  | 1 | 127.28 | 252 | 0.5 | 160372.8 | 1260
| Project Manager / Waste Management |  |  | 1 | 108.19 | 252 | 0.5 | 136319.4 | 1260
| Decom Technician / Safety SME |  |  | 0 | 89.25 | 252 | 1 | 0 | 2520
|  |  |  | 3 |  |  |  | 614958.12 | 7560
1.1.2 | Equipment & Materials
US
|  | Equipment |  |  | Quantity | Rate | Escalated Cost
|  | HEPA filter systems |  |  | 2 | 3598.14 | 11371.1239
|  | Replacement filters |  |  | 24 | 581.07 | 22036.1152
|  | Respirator |  |  | 12 | 259 | 4911.0725
|  | Rad/Vac wet-dry high eff. vacuum |  |  | 1 | 3879 | 6129.3598
|  | Rad/Vac wet-dry high eff. vacuum filters |  |  | 5 | 412 | 3255.0867
|  | Reciprocating Saws |  |  | 5 | 1252.26 | 9893.7254
|  | Pneumatic chipping hammers |  |  | 2 | 1606.71 | 5077.6508
|  | Chipping hammer blades |  |  | 20 | 27.42 | 866.5483
|  | Purchase an air compressor: |  |  | 2 | 1723.44 | 5446.5501
|  | Jackhammer |  |  | 4 | 1417.11 | 8956.9241
|  | Jackhammer Chisels |  |  | 10 | 24.35 | 384.7639
|  | Safety glasses |  |  | 15 | 8.6 | 203.838
|  | Fall protection - harness |  |  | 6 | 208 | 1972.0137
|  | Fall protection - lanyard |  |  | 6 | 367 | 3479.4665
|  | Hardhats |  |  | 15 | 35.5 | 841.4241
|  | Hard hat hearing protection |  |  | 15 | 37.6 | 891.1985
|  | Trailer rental |  |  | 1 | 416 | 657.3379
|  | Phone and computer hook-up |  |  | 1 | 250 | 395.0348
|  | Industrial hygiene instrumentation, calibration and hygienists - 1% of total activity $. |  |  | 0 |  | 0
|  | Tractor loader, wheeled |  |  | 1 | 7160.5905 | 11314.7295
|  | Wheeled Skid steer with conc. Hammer |  |  | 1 | 4421.3693 | 6986.3788
|  | Excavator |  |  | 1 | 28738.389 | 45410.6542
|  | Floor Shaver |  |  | 1 | 8000 | 12641.1134
|  | Wall Shaver |  |  | 1 | 15000 | 23702.0876
|  | Man lift |  |  | 2 | 4727.44 | 14940.0263
|  | Crane rental for building removal |  |  | 1 | 15600 | 24650.1711
226414.3951
|  | Consumables |  | Quantity |  | Duration |  | # workers | quantity | Unit Qty | Unit Cost | Escalated Cost
|  | Coveralls |  | 2 | /man/day | 180 | days | 24 | 8640 | 1 | 11 | 150176.4269
|  | Hoods |  | 0.1 | /man/day | 180 | days | 24 | 432 | 1 | 0 | 0
|  | Shoe covers |  | 4 | /man/day | 180 | days | 24 | 17280 | 1 | 0.94 | 25666.5166
|  | Latex gloves |  | 4 | /man/day | 180 | days | 24 | 17280 | 1 | 0.94 | 25666.5166
|  | Rubber overshoes |  | 0.01 | /man/day | 180 | days | 24 | 43.2 | 1 | 3 | 204.786
|  | Gloves |  | 0.01 | /man/day | 180 | days | 24 | 43.2 | 1 | 2 | 136.524
|  | Dosimeters |  | 1 | /man/year | 0.33333 | year | 24 | 8 | 1 | 200 | 2528.2227
|  | TLDs |  | 1 | /man/mo | 3 | month | 24 | 72 | 1 | 3 | 341.3101
|  | Bioassays |  | 2 | /man/year | 1 | year | 24 | 48 | 1 | 250 | 18961.6701
|  | (Bioassays for aver. crew & management) | [9 empty] | 223681.9729
|  | Small Tools - 2% of total labor costs = |  |  |  | 10540095.26 | labor costs x | 2% | = | 210801.9051
|  | HP Equipment Replacement - 5% of total labor |  |  |  | 10540095.26 | labor costs x | 5% | = | 527004.7629
|  | DGC OH &P on equipment and materials |  |  |  | 1187903.036 |  | 8% | = | 95032.2429
1.2 | Project Planning | [7 empty] | 415 |  | 415 | 2925 | [6 empty] | 270994.1 | [5 empty] | 270994.1
1.2.1 | Procedure Development and Review | [7 empty] | 160 | 1 | 160 | 240 | [6 empty] | 22935.2
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 89.25 | 80 | 1 | 14280 | 160
|  |  | Project Manager |  |  | 1 | 108.19 | 80 | 1 | 8655.2 | 80
[6 empty] | 3 |  | 160 |  | 22935.2 | 240
1.2.2 | Preparation of QA and Safety Documents | [7 empty] | 160 | 1 | 160 | 240 | [6 empty] | 22935.2
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 89.25 | 80 | 1 | 14280 | 160
|  |  | Project Manager |  |  | 1 | 108.19 | 80 | 1 | 8655.2 | 80
[6 empty] | 3 |  | 160 |  | 22935.2 | 240
1.2.3 | Site Mobilization and General Employee Training (GET) | [7 empty] | 95 | 1 | 95 | 2445 | [6 empty] | 225123.7
|  | 1.2.3.1 | Site Mobilization | [5 empty] | 40 | 1 | 40 | 960 | [6 empty] | 85680
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 24 | Decom Technician / Safety SME |  | 89.25 | 2142
|  |  | Receipt of material and equipment |  |  | 16 | hr
|  |  | Staging of equipment |  |  | 8 | hr
|  |  | Set up office and amenities |  |  | 12 | hr
|  |  | Familiarize staff with facility |  |  | 4 | hr
[6 empty] | 40 | hr
|  |  | Total Cost = |  | 40 | x | 2142 | 85680
|  | 1.2.3.2 | General Employee Training (All proj. management and 3 crews of 4) | [5 empty] | 55 | 1 | 55 | 1485 | [5 empty] | 54054 | 139443.7
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Portfolio Manager |  | 157.87 | 157.87
|  |  | 1 | Senior Project Manager / Characterization SME |  | 127.28 | 127.28
|  |  | 1 | Project Manager / Waste Management |  | 108.19 | 108.19
|  |  | 24 | Decom Technician / Safety SME |  | 89.25 | 2142
|  |  | 27 |  |  |  | 2535.34
[8 empty] | Number | Test | Labor | Total
[7 empty] | Unit Cost | Required | Cost | Costs | Cost
|  |  | In-Vivo |  |  |  | 600 | 27 | 16200 | 0 | 16200
|  |  | In-Vitro |  |  |  | 350 | 27 | 9450 | 0 | 9450
|  |  | Physical @ |  | 4 | hour and | 150 | 27 | 4050 | 10141.36 | 14191.36
|  |  | Resp. Tests |  | 1 | hour and | 50 | 27 | 1350 | 2535.34 | 3885.34
|  |  | Resp Fit Tests |  | 1 | hour and | 25 | 27 | 675 | 2535.34 | 3210.34
|  |  | Blood Tests |  | 1 | hour and | 125 | 27 | 3375 | 2535.34 | 5910.34
|  |  | OSHA recertification |  | 8 | hour |  |  |  | 20282.72 | 20282.72
|  |  | Site specific 1 week of training |  | 40 | hour |  |  |  | 101413.6 | 101413.6
[5 empty] | 55 |  |  |  | 35100 | 139443.7 | 174543.7
1.3 | Preliminary Site Investigation | [7 empty] | 176 |  | 176 | 480 | [6 empty] | 44658.24 | [5 empty] | 44658.24
1.3.1 | Decontamination Readiness Review - (Contractor staff cost included in Undistributed Costs) | [7 empty] | 80 | 1 | 80
1.3.2 | Site Preparation | [5 empty] | A |  | 96 | 1 | 96 | 480 | [6 empty] | 44658.24
| 1.3.2.1 | Initial Site Survey |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.2 | Setup work areas | [6 empty] | 32 |  | 32 | 160 | [6 empty] | 14886.08
| 1.3.2.2.1 | Setup boundaries, install HEPA filters & seal off openings |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.2.2 | Establish staging area |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.3 | Setup Rad. and Non-Rad. segregation and packaging stations |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.4 | Isolate Bldg B54 | [6 empty] | 32 |  | 32 | 160 | [6 empty] | 14886.08
| 1.3.2.4.1 | Electrical |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.4.2 | Piping |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
1.4 | Detailed Charaterisation | [7 empty] | 40 | 1 | 40 | 4800 | [6 empty] | 446582.4 | [5 empty] | 446582.4
|  |  |  | Estimated Duration | 40 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 12 | 89.25 | 320 | 1 | 342720 | 3840
|  |  | Project Manager |  |  | 3 | 108.19 | 320 | 1 | 103862.4 | 960
[6 empty] | 15 |  | 640 |  | 446582.4 | 4800
1.5 | Decontamination | [11 empty] | 30.3567 | 328.6629 |  | 3.4695 | 265.9365 |  | 7338576.816 | [5 empty] | 7338576.816
[6 empty] | Removal Rate, Australian dollars | Units | Cost | Adjustment | Clean Disposal volume rate | Units | Clean Disposal Volume, cubic meters | LLW Disposal volume rate | Units | LLW Disposal Volume, cubic meters | Hazardous Disposal volume rate | Units | Hazardous Disposal Volume, cubic meters | Mixed Disposal volume rate | Units | Mixed Disposal Volume, cubic meters
1.5.1 | Asbestos Removal
| 1.5.1.1 | Remove contaminated asbestos pipe insulation |  |  |  | 1443.6899 | /meter | 880073.3645 |  | 0.046153 | meter^3/meter | [7 empty] | 0.046153 | meter^3/meter | 28.1352
| 1.5.1.2 | Remove asbestos tile |  |  |  | 116.5036 | /m^2 |  |  | 0.030615 | meter^3/meter^2
1.5.2 | Remove systems and Components
| 1.5.2.1 | Sys. Clean |  |  |  | 1207.9763 | /m^2 | 2181605.192 | 50% | 0.21097 | meter^3/meter^2 | 254.0101
| 1.5.2.2 | Sys. LLW |  |  |  | 829.1779 | /m^2 | 1497495.323 | 50% |  |  |  | 0.021826 | meter^3/meter^2 | 26.2787
| 1.5.2.3 | Sys. Hazardous |  |  |  | 22.3936 | /m^2 | 40442.8176 | 50% | [6 empty] | 0.00034797 | meter^3/meter^2 | 0.41896
| 1.5.2.4 | Sys. Mixed |  |  |  | 17.6413 | /m^2 | 31860.2008 | 50% | [9 empty] | 0.0028817 | meter^3/meter^2 | 3.4695
3751403.533
1.5.3 | Decontaminate Structure
| 1.5.3.1 | Decon Clean |  |  |  | 36.3001 | /m^2 | 65557.9801 | 50% | 0.0099056 | meter^3/meter^2 | 11.9264
| 1.5.3.2 | Decontaminate Hot Cells |  |  |  | 241.6738 | /m^2 | 436462.8544 | 50% |  |  |  | 0.0025425 | meter^3/meter^2 | 3.0612
| 1.5.3.3 | Remove hazardous material |  |  |  | 42.3037 | /m^2 | 76400.4686 | 50% | [6 empty] | 0.27263 | meter^3/meter^2 | 328.244
| 1.5.3.4 | Decon Contaminated |  |  |  | 855.5451 | /m^2 | 1545114.453 | 50% |  |  |  | 0.0008445 | meter^3/meter^2 | 1.0168
2123535.756
1.5.4 | Final Survey |  |  |  |  | 484.6878 | /m^2 | 583564.1624
1.6 | Site Remediation | [15 empty] | 1075.2731 |  | 2439283.701 | [5 empty] | 2439283.701
1.6.1 | Remove Building |  |  |  |  | 910.4763 | /m^2 | 1644320.158 | 50% | 0.77087 | cuft/sq ft | 928.1324
1.6.2 | Remove hot cell |  |  |  |  | 27.9928 | /m^2 | 544168.8938 | 50% | 0.12221 | cuft/sq ft | 147.1407
1.6.3 | Grade and seed (assume an area 2X building footprint) |  |  |  |  | 31.6489 | /m^2 | 76210.652
1.6.4 | Backfill (assume building footprint x 10' deep) |  |  |  |  | 47.5733 | /cuft | 174583.9972
2439283.701
1.7 | Waste Disposal |  |  |  |  | 0.028317 | 100 | lbs/cuft | [12 empty] | 290166.0198 |  | 27902.7608 | 710466.6813 | 1028535.462
[5 empty] | Volume, cuft | Volume, m^3 | Tonnes | Rate | Cost
|  | Sys. Clean |  |  | 47364.4454 | 1341.2095 | 2368.2223 | 300 | 710466.6813
|  | Sys. LLW |  |  | 1072.0383 | 30.3567 | 53.6019
|  | Sys. Hazardous |  |  | 11606.6408 | 328.6629 | 580.332 | 500 | 290166.0198
|  | Sys. Mixed |  |  | 1116.1104 | 31.6047 | 55.8055 | 500 | 27902.7608

## Building B18
B 18 DATA - Data highlighted in GREEN can be adjusted as needed
Uncorrected Duration
[8 empty] | Crew | (No. of Hours) | Prod. Factor | Adjusted Duration (hrs) | Man-hours | LSA Waste Disp. Vol (cm) | Hazardous Waste Vol (cm) |  | Mixed Waste Volume (cm) | Clean Waste Volume (cm) | Materials, Consumables & Equipment | Labor Cost | LSA Waste Costs | Hazardous Waste Costs | LSA Waste Costs | Mixed Waste Costs | Clean Waste Costs | Total Cost
1.0 | Building B18 | [9 empty] | 663 | 5465 | 3450 | 0 |  | 0 | 3450 | 461768.1684 | 2851597.47 |  | 0 |  |  | 1827537.01 | 5140902.648
1.1 | Project Management | [16 empty] | 461768.1684 | 134378.1 | [5 empty] | 596146.2684
1.1.1 | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
| Portfolio Manager |  |  | 1 | 157.87 | 90 | 0.25 | 28416.6 | 225
| Senior Project Manager / Characterization SME |  |  | 1 | 127.28 | 90 | 0.5 | 57276 | 450
| Project Manager / Waste Management |  |  | 1 | 108.19 | 90 | 0.5 | 48685.5 | 450
| Decom Technician / Safety SME |  |  | 0 | 89.25 | 90 | 1 | 0 | 900
|  |  |  | 3 |  |  |  | 134378.1 | 2025
1.1.2 | Equipment & Materials
US
|  | Equipment |  |  | Quantity | Rate | Escalated Cost
|  | HEPA filter systems |  |  | 0 | 3598.14 | 0
|  | Replacement filters |  |  | 0 | 581.07 | 0
|  | Respirator |  |  | 0 | 259 | 0
|  | Rad/Vac wet-dry high eff. vacuum |  |  | 0 | 3879 | 0
|  | Rad/Vac wet-dry high eff. vacuum filters |  |  | 0 | 412 | 0
|  | Reciprocating Saws |  |  | 0 | 1252.26 | 0
|  | Pneumatic chipping hammers |  |  | 2 | 1606.71 | 5077.6508
|  | Chipping hammer blades |  |  | 20 | 27.42 | 866.5483
|  | Purchase an air compressor: |  |  | 2 | 1723.44 | 5446.5501
|  | Jackhammer |  |  | 4 | 1417.11 | 8956.9241
|  | Jackhammer Chisels |  |  | 10 | 24.35 | 384.7639
|  | Safety glasses |  |  | 15 | 8.6 | 203.838
|  | Fall protection - harness |  |  | 0 | 208 | 0
|  | Fall protection - lanyard |  |  | 0 | 367 | 0
|  | Hardhats |  |  | 15 | 35.5 | 841.4241
|  | Hard hat hearing protection |  |  | 15 | 37.6 | 891.1985
|  | Trailer rental |  |  | 1 | 416 | 657.3379
|  | Phone and computer hook-up |  |  | 1 | 250 | 395.0348
|  | Industrial hygiene instrumentation, calibration and hygienists - 1% of total activity $. |  |  | 0 |  | 0
|  | Tractor loader, wheeled |  |  | 1 | 7160.5905 | 11314.7295
|  | Wheeled Skid steer with conc. Hammer |  |  | 1 | 4421.3693 | 6986.3788
|  | Excavator |  |  | 1 | 28738.389 | 45410.6542
|  | Floor Shaver |  |  | 0 | 8000 | 0
|  | Wall Shaver |  |  | 0 | 15000 | 0
|  | Man lift |  |  | 0 | 4727.44 | 0
|  | Crane rental for building removal |  |  | 0 | 15600 | 0
87433.033
|  | Consumables |  | Quantity |  | Duration |  | # workers | quantity | Unit Qty | Unit Cost | Escalated Cost
|  | Coveralls |  | 0 | /man/day | 90 | days | 12 | 0 | 1 | 11 | 0
|  | Hoods |  | 0 | /man/day | 90 | days | 12 | 0 | 1 | 0 | 0
|  | Shoe covers |  | 0 | /man/day | 90 | days | 12 | 0 | 1 | 0.94 | 0
|  | Latex gloves |  | 0 | /man/day | 90 | days | 12 | 0 | 1 | 0.94 | 0
|  | Rubber overshoes |  | 0 | /man/day | 90 | days | 12 | 0 | 1 | 3 | 0
|  | Gloves |  | 0 | /man/day | 90 | days | 12 | 0 | 1 | 2 | 0
|  | Dosimeters |  | 0 | /man/year | 0.25 | year | 12 | 0 | 1 | 200 | 0
|  | TLDs |  | 0 | /man/mo | 3 | month | 12 | 0 | 1 | 3 | 0
|  | Bioassays |  | 0 | /man/year | 0.25 | year | 12 | 0 | 1 | 250 | 0
|  | (Bioassays for aver. crew & management) | [9 empty] | 0
|  | Small Tools - 2% of total labor costs = |  |  |  | 2717219.37 | labor costs x | 2% | = | 54344.3874
|  | HP Equipment Replacement - 5% of total labor |  |  |  | 2717219.37 | labor costs x | 5% | = | 135860.9685
|  | DGC OH &P on equipment and materials |  |  |  | 277638.3889 |  | 8% | = | 22211.0711
1.2 | Project Planning | [7 empty] | 415 |  | 447 | 1785 | [6 empty] | 169249.1 | [5 empty] | 169249.1
1.2.1 | Procedure Development and Review | [7 empty] | 160 | 1.1 | 176 | 240 | [6 empty] | 22935.2
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 89.25 | 80 | 1 | 14280 | 160
|  |  | Project Manager |  |  | 1 | 108.19 | 80 | 1 | 8655.2 | 80
[6 empty] | 3 |  | 160 |  | 22935.2 | 240
1.2.2 | Preparation of QA and Safety Documents | [7 empty] | 160 | 1.1 | 176 | 240 |  |  |  |  | 169249.1 |  | 22935.2
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 89.25 | 80 | 1 | 14280 | 160
|  |  | Project Manager |  |  | 1 | 108.19 | 80 | 1 | 8655.2 | 80
[6 empty] | 3 |  | 160 |  | 22935.2 | 240
1.2.3 | Site Mobilization and General Employee Training (GET) | [7 empty] | 95 | 1 | 95 | 1305 | [6 empty] | 123378.7
|  | 1.2.3.1 | Site Mobilization | [5 empty] | 40 | 1 | 40 | 480 | [6 empty] | 42840
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 12 | Decom Technician / Safety SME |  | 89.25 | 1071
|  |  | Receipt of material and equipment |  |  | 16 | hr
|  |  | Staging of equipment |  |  | 8 | hr
|  |  | Set up office and amenities |  |  | 12 | hr
|  |  | Familiarize staff with facility |  |  | 4 | hr
[6 empty] | 40 | hr
|  |  | Total Cost = |  | 40 | x | 1071 | 42840
|  | 1.2.3.2 | General Employee Training (All proj. management and 3 crews of 4) | [5 empty] | 55 | 1 | 55 | 825 | [5 empty] | 30030 | 80538.7
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Portfolio Manager |  | 157.87 | 157.87
|  |  | 1 | Senior Project Manager / Characterization SME |  | 127.28 | 127.28
|  |  | 1 | Project Manager / Waste Management |  | 108.19 | 108.19
|  |  | 12 | Decom Technician / Safety SME |  | 89.25 | 1071
|  |  | 15 |  |  |  | 1464.34
[8 empty] | Number | Test | Labor | Total
[7 empty] | Unit Cost | Required | Cost | Costs | Cost
|  |  | In-Vivo |  |  |  | 600 | 15 | 9000 | 0 | 9000
|  |  | In-Vitro |  |  |  | 350 | 15 | 5250 | 0 | 5250
|  |  | Physical @ |  | 4 | hour and | 150 | 15 | 2250 | 5857.36 | 8107.36
|  |  | Resp. Tests |  | 1 | hour and | 50 | 15 | 750 | 1464.34 | 2214.34
|  |  | Resp Fit Tests |  | 1 | hour and | 25 | 15 | 375 | 1464.34 | 1839.34
|  |  | Blood Tests |  | 1 | hour and | 125 | 15 | 1875 | 1464.34 | 3339.34
|  |  | OSHA recertification |  | 8 | hour |  |  |  | 11714.72 | 11714.72
|  |  | Site specific 1 week of training |  | 40 | hour |  |  |  | 58573.6 | 58573.6
[5 empty] | 55 |  |  |  | 19500 | 80538.7 | 100038.7
1.3 | Preliminary Site Investigation | [7 empty] | 176 |  | 176 | 480 | [6 empty] | 44658.24 | [5 empty] | 44658.24
1.3.1 | Decontamination Readiness Review - (Contractor staff cost included in Undistributed Costs) | [7 empty] | 80 | 1 | 80
1.3.2 | Site Preparation | [5 empty] | A |  | 96 | 1 | 96 | 480 | [6 empty] | 44658.24
| 1.3.2.1 | Initial Site Survey |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.2 | Setup work areas | [6 empty] | 32 |  | 32 | 160 | [6 empty] | 14886.08
| 1.3.2.2.1 | Setup boundaries, install HEPA filters & seal off openings |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.2.2 | Establish staging area |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.3 | Setup Rad. and Non-Rad. segregation and packaging stations |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.4 | Isolate B18 | [6 empty] | 32 |  | 32 | 160 | [6 empty] | 14886.08
| 1.3.2.4.1 | Electrical |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.4.2 | Piping |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
1.4 | Detailed Charaterisation | [7 empty] | 40 | 1 | 40 | 3200 | [6 empty] | 297721.6 | [5 empty] | 297721.6
|  |  |  | Estimated Duration | 40 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 8 | 89.25 | 320 | 1 | 228480 | 2560
|  |  | Project Manager |  |  | 2 | 108.19 | 320 | 1 | 69241.6 | 640
[6 empty] | 10 |  | 640 |  | 297721.6 | 3200
1.5 | Decontamination | [11 empty] | 3450 | 0 |  | 0 | 3450 |  | 1932273.807 | [5 empty] | 1932273.807
[6 empty] | Removal Rate, Australian dollars | Units | Cost | Adjustment | Clean Disposal volume rate | Units | Clean Disposal Volume, cubic meters | LLW Disposal volume rate | Units | LLW Disposal Volume, cubic meters | Hazardous Disposal volume rate | Units | Hazardous Disposal Volume, cubic meters | Mixed Disposal volume rate | Units | Mixed Disposal Volume, cubic meters
1.5.1 | Asbestos Removal
| 1.5.1.1 | Remove asbestos pipe insulation |  |  |  | 721.845 | /meter |  |  | 0.046153 | cuft/foot
| 1.5.1.2 | Remove asbestos tile |  |  |  | 58.2518 | /m^2 |  |  | 0.030615 | cuft/sq ft
1.5.1 | Remove Soil and Asphalt
| 1.5.2.1 | Clean |  |  |  | 31.4239 | /cuft | 54206.3083 | -50% |  |  | 3450
| 1.5.2.2 | Contaminated |  |  |  | 31.4239 | /cuft | 54206.3083 | -50% | [5 empty] | 3450
| 1.5.2.3 | Sys. Hazardous |  |  |  | 11.1968 | /m^2 | 84847.018 | [9 empty] | 0
| 1.5.2.4 | Sys. Mixed |  |  |  | 8.8207 | /m^2 | 66841.1153 | [12 empty] | 0
260100.7498
1.5.3 | Decontaminate Structure
| 1.5.3.1 | Decon Clean |  |  |  | 18.15 | /m^2 |  |  |  |  | 0
| 1.5.3.2 | Decon Contaminated |  |  |  | 427.7726 | /m^2 | [7 empty] | 0
0
1.5.4 | Final Survey |  |  |  |  | 242.3439 | /m^2 | 1672173.057
1.6 | Site Remediation | [15 empty] | 0 |  | 273316.623 | [5 empty] | 273316.623
1.6.1 | Remove Building |  |  |  |  | 455.2381 | /m^2 |  |  |  |  | 0
1.6.2 | Grade and seed |  |  |  |  | 15.8245 | /m^2 | 109188.8494
1.6.3 | Backfill (assume total area x 1 meter deep) |  |  |  |  | 23.7866 | /cuft | 164127.7735
273316.623
1.7 | Waste Disposal |  |  |  |  | 0.028317 | 100 | lbs/cuft | [12 empty] | 0 |  |  | 1827537.01 | 1827537.01
[5 empty] | Volume, cuft | Volume, m^3 | Tonnes | Rate | Cost
|  | Sys. Clean |  |  | 121835.8007 | 3450 | 6091.79 | 300 | 1827537.01
|  | Sys. LLW |  |  | 121835.8007 | 3450 | 6091.79
|  | Sys. Hazardous |  |  | 0 | 0 | 0 | 500 | 0
|  | Sys. Mixed |  |  | 0 | 0 | 0 | 500 | 0

## Building B56
B 56 DATA - Data highlighted in GREEN can be adjusted as needed
Uncorrected Duration
[8 empty] | Crew | (No. of Hours) | Prod. Factor | Adjusted Duration (hrs) | Man-hours | LSA Waste Disp. Vol (cm) | Hazardous Waste Vol (cm) |  | Mixed Waste Volume (cm) | Clean Waste Volume (cm) | Materials, Consumables & Equipment | Labor Cost | LSA Waste Costs | Hazardous Waste Costs | LSA Waste Costs | Mixed Waste Costs | Clean Waste Costs | Total Cost
1.0 | Building B56 | [9 empty] | 647 | 6605 | 39.257 | 425.0234 |  | 4.4867 | 1734.4379 | 1843799.953 | 11009187.42 |  | 375239.612 |  | 3961.1919 | 918767.9592 | 14150956.13
1.1 | Project Management | [16 empty] | 1843799.953 | 256232.55 | [5 empty] | 2100032.503
1.1.1 | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
| Portfolio Manager |  |  | 1 | 157.87 | 105 | 1 | 132610.8 | 1050
| Senior Project Manager / Characterization SME |  |  | 1 | 127.28 | 105 | 0.5 | 66822 | 525
| Project Manager / Waste Management |  |  | 1 | 108.19 | 105 | 0.5 | 56799.75 | 525
| Decom Technician / Safety SME |  |  | 0 | 89.25 | 105 | 1 | 0 | 1050
|  |  |  | 3 |  |  |  | 256232.55 | 3150
1.1.2 | Equipment & Materials
US
|  | Equipment |  |  | Quantity | Rate | Escalated Cost
|  | HEPA filter systems |  |  | 2 | 3598.14 | 11371.1239
|  | Replacement filters |  |  | 24 | 581.07 | 22036.1152
|  | Respirator |  |  | 12 | 259 | 4911.0725
|  | Rad/Vac wet-dry high eff. vacuum |  |  | 1 | 3879 | 6129.3598
|  | Rad/Vac wet-dry high eff. vacuum filters |  |  | 5 | 412 | 3255.0867
|  | Reciprocating Saws |  |  | 5 | 1252.26 | 9893.7254
|  | Pneumatic chipping hammers |  |  | 2 | 1606.71 | 5077.6508
|  | Chipping hammer blades |  |  | 20 | 27.42 | 866.5483
|  | Purchase an air compressor: |  |  | 2 | 1723.44 | 5446.5501
|  | Jackhammer |  |  | 4 | 1417.11 | 8956.9241
|  | Jackhammer Chisels |  |  | 10 | 24.35 | 384.7639
|  | Safety glasses |  |  | 15 | 8.6 | 203.838
|  | Fall protection - harness |  |  | 6 | 208 | 1972.0137
|  | Fall protection - lanyard |  |  | 6 | 367 | 3479.4665
|  | Hardhats |  |  | 15 | 35.5 | 841.4241
|  | Hard hat hearing protection |  |  | 15 | 37.6 | 891.1985
|  | Trailer rental |  |  | 1 | 416 | 657.3379
|  | Phone and computer hook-up |  |  | 1 | 250 | 395.0348
|  | Industrial hygiene instrumentation, calibration and hygienists - 1% of total activity $. |  |  | 0 |  | 0
|  | Tractor loader, wheeled |  |  | 1 | 7160.5905 | 11314.7295
|  | Wheeled Skid steer with conc. Hammer |  |  | 1 | 4421.3693 | 6986.3788
|  | Excavator |  |  | 1 | 28738.389 | 45410.6542
|  | Floor Shaver |  |  | 1 | 8000 | 12641.1134
|  | Wall Shaver |  |  | 1 | 15000 | 23702.0876
|  | Man lift |  |  | 2 | 4727.44 | 14940.0263
|  | Crane rental for building removal |  |  | 1 | 15600 | 24650.1711
226414.3951
|  | Consumables |  | Quantity |  | Duration |  | # workers | quantity | Unit Qty | Unit Cost | Escalated Cost
|  | Coveralls |  | 2 | /man/day | 105 | days | 24 | 5040 | 1 | 11 | 87602.9157
|  | Hoods |  | 0.1 | /man/day | 105 | days | 24 | 252 | 1 | 0 | 0
|  | Shoe covers |  | 4 | /man/day | 105 | days | 24 | 10080 | 1 | 0.94 | 14972.1347
|  | Latex gloves |  | 4 | /man/day | 105 | days | 24 | 10080 | 1 | 0.94 | 14972.1347
|  | Rubber overshoes |  | 0.01 | /man/day | 105 | days | 24 | 25.2 | 1 | 3 | 119.4585
|  | Gloves |  | 0.01 | /man/day | 105 | days | 24 | 25.2 | 1 | 2 | 79.639
|  | Dosimeters |  | 1 | /man/year | 0.25 | year | 24 | 6 | 1 | 200 | 1896.167
|  | TLDs |  | 1 | /man/mo | 3 | month | 24 | 72 | 1 | 3 | 341.3101
|  | Bioassays |  | 2 | /man/year | 0.5 | year | 24 | 24 | 1 | 250 | 9480.835
|  | (Bioassays for aver. crew & management) | [9 empty] | 129464.5947
|  | Small Tools - 2% of total labor costs = |  |  |  | 10752954.87 | labor costs x | 2% | = | 215059.0973
|  | HP Equipment Replacement - 5% of total labor |  |  |  | 10752954.87 | labor costs x | 5% | = | 537647.7433
|  | DGC OH &P on equipment and materials |  |  |  | 1108585.83 |  | 8% | = | 88686.8664
1.2 | Project Planning | [7 empty] | 415 |  | 431 | 2925 | [6 empty] | 270994.1 | [5 empty] | 270994.1
1.2.1 | Procedure Development and Review | [7 empty] | 160 | 1 | 160 | 240 | [6 empty] | 22935.2
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 89.25 | 80 | 1 | 14280 | 160
|  |  | Project Manager |  |  | 1 | 108.19 | 80 | 1 | 8655.2 | 80
[6 empty] | 3 |  | 160 |  | 22935.2 | 240
1.2.2 | Preparation of QA and Safety Documents | [7 empty] | 160 | 1.1 | 176 | 240 | [6 empty] | 22935.2
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 89.25 | 80 | 1 | 14280 | 160
|  |  | Project Manager |  |  | 1 | 108.19 | 80 | 1 | 8655.2 | 80
[6 empty] | 3 |  | 160 |  | 22935.2 | 240
1.2.3 | Site Mobilization and General Employee Training (GET) | [7 empty] | 95 | 1 | 95 | 2445 | [6 empty] | 225123.7
|  | 1.2.3.1 | Site Mobilization | [5 empty] | 40 | 1 | 40 | 960 | [6 empty] | 85680
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 24 | Decom Technician / Safety SME |  | 89.25 | 2142
|  |  | Receipt of material and equipment |  |  | 16 | hr
|  |  | Staging of equipment |  |  | 8 | hr
|  |  | Set up office and amenities |  |  | 12 | hr
|  |  | Familiarize staff with facility |  |  | 4 | hr
[6 empty] | 40 | hr
|  |  | Total Cost = |  | 40 | x | 2142 | 85680
|  | 1.2.3.2 | General Employee Training (All proj. management and 3 crews of 4) | [5 empty] | 55 | 1 | 55 | 1485 | [5 empty] | 54054 | 139443.7
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Portfolio Manager |  | 157.87 | 157.87
|  |  | 1 | Senior Project Manager / Characterization SME |  | 127.28 | 127.28
|  |  | 1 | Project Manager / Waste Management |  | 108.19 | 108.19
|  |  | 24 | Decom Technician / Safety SME |  | 89.25 | 2142
|  |  | 27 |  |  |  | 2535.34
[8 empty] | Number | Test | Labor | Total
[7 empty] | Unit Cost | Required | Cost | Costs | Cost
|  |  | In-Vivo |  |  |  | 600 | 27 | 16200 | 0 | 16200
|  |  | In-Vitro |  |  |  | 350 | 27 | 9450 | 0 | 9450
|  |  | Physical @ |  | 4 | hour and | 150 | 27 | 4050 | 10141.36 | 14191.36
|  |  | Resp. Tests |  | 1 | hour and | 50 | 27 | 1350 | 2535.34 | 3885.34
|  |  | Resp Fit Tests |  | 1 | hour and | 25 | 27 | 675 | 2535.34 | 3210.34
|  |  | Blood Tests |  | 1 | hour and | 125 | 27 | 3375 | 2535.34 | 5910.34
|  |  | OSHA recertification |  | 8 | hour |  |  |  | 20282.72 | 20282.72
|  |  | Site specific 1 week of training |  | 40 | hour |  |  |  | 101413.6 | 101413.6
[5 empty] | 55 |  |  |  | 35100 | 139443.7 | 174543.7
1.3 | Preliminary Site Investigation | [7 empty] | 176 |  | 176 | 480 | [6 empty] | 44658.24 | [5 empty] | 44658.24
1.3.1 | Decontamination Readiness Review - (Contractor staff cost included in Undistributed Costs) | [7 empty] | 80 | 1 | 80
1.3.2 | Site Preparation | [5 empty] | A |  | 96 | 1 | 96 | 480 | [6 empty] | 44658.24
| 1.3.2.1 | Initial Site Survey |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.2 | Setup work areas | [6 empty] | 32 |  | 32 | 160 | [6 empty] | 14886.08
| 1.3.2.2.1 | Setup boundaries, install HEPA filters & seal off openings |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.2.2 | Establish staging area |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.3 | Setup Rad. and Non-Rad. segregation and packaging stations |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.4 | Isolate Bldg B56 | [6 empty] | 32 |  | 32 | 160 | [6 empty] | 14886.08
| 1.3.2.4.1 | Electrical |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.4.2 | Piping |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
1.4 | Detailed Charaterisation | [7 empty] | 40 | 1 | 40 | 3200 | [6 empty] | 297721.6 | [5 empty] | 297721.6
|  |  |  | Estimated Duration | 40 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 8 | 89.25 | 320 | 1 | 228480 | 2560
|  |  | Project Manager |  |  | 2 | 108.19 | 320 | 1 | 69241.6 | 640
[6 empty] | 10 |  | 640 |  | 297721.6 | 3200
1.5 | Decontamination | [11 empty] | 39.257 | 425.0234 |  | 4.4867 | 343.9062 |  | 7688838.604 | [5 empty] | 7688838.604
[6 empty] | Removal Rate, Australian dollars | Units | Cost | Adjustment | Clean Disposal volume rate | Units | Clean Disposal Volume, cubic meters | LLW Disposal volume rate | Units | LLW Disposal Volume, cubic meters | Hazardous Disposal volume rate | Units | Hazardous Disposal Volume, cubic meters | Mixed Disposal volume rate | Units | Mixed Disposal Volume, cubic meters
1.5.1 | Asbestos Removal
| 1.5.1.1 | Remove contaminated asbestos pipe insulation |  |  |  | 1443.6899 | /meter | 0 |  | 0.046153 | meter^3/meter | [7 empty] | 0.046153 | meter^3/meter | 0
| 1.5.1.2 | Remove asbestos tile |  |  |  | 116.5036 | /m^2 |  |  | 0.030615 | meter^3/meter^2
1.5.2 | Remove systems and Components
| 1.5.2.1 | Sys. Clean |  |  |  | 1207.9763 | /m^2 | 2821228.641 | 50% | 0.21097 | meter^3/meter^2 | 328.4832
| 1.5.2.2 | Sys. LLW |  |  |  | 829.1779 | /m^2 | 1936545.031 | 50% |  |  |  | 0.021826 | meter^3/meter^2 | 33.9834
| 1.5.2.3 | Sys. Hazardous |  |  |  | 22.3936 | /m^2 | 52300.2217 | 50% | [6 empty] | 0.00034797 | meter^3/meter^2 | 0.54179
| 1.5.2.4 | Sys. Mixed |  |  |  | 17.6413 | /m^2 | 41201.273 | 50% | [9 empty] | 0.0028817 | meter^3/meter^2 | 4.4867
4851275.167
1.5.3 | Decontaminate Structure
| 1.5.3.1 | Decon Clean |  |  |  | 36.3001 | /m^2 | 84778.8829 | 50% | 0.0099056 | meter^3/meter^2 | 15.4231
| 1.5.3.2 | Decontaminate Hot Cells |  |  |  | 0 | /m^2 | 0 | 50% |  |  |  | 0.0025425 | meter^3/meter^2 | 3.9587
| 1.5.3.3 | Remove hazardous material |  |  |  | 0 | /m^2 | 0 | 50% | [6 empty] | 0.27263 | meter^3/meter^2 | 424.4816
| 1.5.3.4 | Decon Contaminated |  |  |  | 855.5451 | /m^2 | 1998125.584 | 50% |  |  |  | 0.0008445 | meter^3/meter^2 | 1.3149
2082904.467
1.5.4 | Final Survey |  |  |  |  | 484.6878 | /m^2 | 754658.9708
1.6 | Site Remediation | [15 empty] | 1390.5317 |  | 2450742.322 | [5 empty] | 2450742.322
1.6.1 | Remove Building |  |  |  |  | 910.4763 | /m^2 | 2126417.348 | 50% | 0.77087 | meter^3/meter^2 | 1200.2509
1.6.2 | Remove hot cell |  |  |  |  | 0 | /m^2 | 0 |  | 0.12221 | meter^3/meter^2 | 190.2807
1.6.3 | Grade and seed (assume an area 2X building footprint) |  |  |  |  | 31.6489 | /m^2 | 98554.805
1.6.4 | Backfill (assume building footprint x 10' deep) |  |  |  |  | 47.5733 | /cuft | 225770.1691
2450742.322
1.7 | Waste Disposal |  |  |  |  | 0.028317 | 100 | lbs/cuft | [12 empty] | 375239.612 |  | 3961.1919 | 918767.9592 | 1297968.763
[5 empty] | Volume, cuft | Volume, m^3 | Tonnes | Rate | Cost
|  | Sys. Clean |  |  | 61251.1973 | 1734.4379 | 3062.5599 | 300 | 918767.9592
|  | Sys. LLW |  |  | 1386.3485 | 39.257 | 69.3174
|  | Sys. Hazardous |  |  | 15009.5845 | 425.0234 | 750.4792 | 500 | 375239.612
|  | Sys. Mixed |  |  | 158.4477 | 4.4867 | 7.9224 | 500 | 3961.1919

## Building B70
B 56 DATA - Data highlighted in GREEN can be adjusted as needed
[9 empty] | Uncorrected Duration | [6 empty] | Mixed | Clean | Materials, |  |  | Hazardous |  | Mixed | Clean
[8 empty] | Crew | (No. of Hours) | Prod. Factor | Adjusted Duration (hrs) | Man-hours | LSA Waste Disp. Vol (cm) | Hazardous Waste Vol (cm) |  | Mixed Waste Volume (cm) | Clean Waste Volume (cm) | Materials, Consumables & Equipment | Labor Cost | LSA Waste Costs | Hazardous Waste Costs | LSA Waste Costs | Mixed Waste Costs | Clean Waste Costs | Total Cost
1.0 | Building B70 | [9 empty] | 416 | 1080 | 0 | 41.5507 |  | 0.43863 | 169.5604 | 188017.7686 | 437858.5796 |  | 36683.8052 |  | 12807.0714 | 89819.688 | 765186.9129
1.1 | Project Management | [16 empty] | 188017.7686 | 71961.96 | [5 empty] | 259979.7286
1.1.1 | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
| Portfolio Manager |  |  | 1 | 157.87 | 84 | 0.25 | 26522.16 | 210
| Senior Project Manager / Characterization SME |  |  | 1 | 127.28 | 84 | 0 | 0 | 0
| Project Manager / Waste Management |  |  | 1 | 108.19 | 84 | 0.5 | 45439.8 | 420
| Decom Technician / Safety SME |  |  | 0 | 89.25 | 84 | 1 | 0 | 840
|  |  |  | 3 |  |  |  | 71961.96 | 1470
1.1.2 | Equipment & Materials
US
|  | Equipment |  |  | Quantity | Rate | Escalated Cost
|  | HEPA filter systems |  |  | 0 | 3598.14 | 0
|  | Replacement filters |  |  | 0 | 581.07 | 0
|  | Respirator |  |  | 0 | 259 | 0
|  | Rad/Vac wet-dry high eff. vacuum |  |  | 0 | 3879 | 0
|  | Rad/Vac wet-dry high eff. vacuum filters |  |  | 0 | 412 | 0
|  | Reciprocating Saws |  |  | 0 | 1252.26 | 0
|  | Pneumatic chipping hammers |  |  | 2 | 1606.71 | 5077.6508
|  | Chipping hammer blades |  |  | 20 | 27.42 | 866.5483
|  | Purchase an air compressor: |  |  | 2 | 1723.44 | 5446.5501
|  | Jackhammer |  |  | 4 | 1417.11 | 8956.9241
|  | Jackhammer Chisels |  |  | 10 | 24.35 | 384.7639
|  | Safety glasses |  |  | 15 | 8.6 | 203.838
|  | Fall protection - harness |  |  | 0 | 208 | 0
|  | Fall protection - lanyard |  |  | 0 | 367 | 0
|  | Hardhats |  |  | 15 | 35.5 | 841.4241
|  | Hard hat hearing protection |  |  | 15 | 37.6 | 891.1985
|  | Trailer rental |  |  | 1 | 416 | 657.3379
|  | Phone and computer hook-up |  |  | 1 | 250 | 395.0348
|  | Industrial hygiene instrumentation, calibration and hygienists - 1% of total activity $. |  |  | 0 |  | 0
|  | Tractor loader, wheeled |  |  | 1 | 7160.5905 | 11314.7295
|  | Wheeled Skid steer with conc. Hammer |  |  | 1 | 4421.3693 | 6986.3788
|  | Excavator |  |  | 1 | 28738.389 | 45410.6542
|  | Floor Shaver |  |  | 0 | 8000 | 0
|  | Wall Shaver |  |  | 0 | 15000 | 0
|  | Man lift |  |  | 0 | 4727.44 | 0
|  | Crane rental for building removal |  |  | 0 | 15600 | 0
87433.033
|  | Consumables |  | Quantity |  | Duration |  | # workers | quantity | Unit Qty | Unit Cost | Escalated Cost
|  | Coveralls |  | 0 | /man/day | 0 | days | 9 | 0 | 1 | 11 | 0
|  | Hoods |  | 0 | /man/day | 0 | days | 9 | 0 | 1 | 0 | 0
|  | Shoe covers |  | 0 | /man/day | 0 | days | 9 | 0 | 1 | 0.94 | 0
|  | Latex gloves |  | 0 | /man/day | 0 | days | 9 | 0 | 1 | 0.94 | 0
|  | Rubber overshoes |  | 0 | /man/day | 0 | days | 9 | 0 | 1 | 3 | 0
|  | Gloves |  | 0 | /man/day | 0 | days | 9 | 0 | 1 | 2 | 0
|  | Dosimeters |  | 0 | /man/year | 0 | year | 9 | 0 | 1 | 200 | 0
|  | TLDs |  | 0 | /man/mo | 0 | month | 9 | 0 | 1 | 3 | 0
|  | Bioassays |  | 0 | /man/year | 0 | year | 9 | 0 | 1 | 250 | 0
|  | (Bioassays for aver. crew & management) | [9 empty] | 0
|  | Small Tools - 2% of total labor costs = |  |  |  | 365896.6196 | labor costs x | 2% | = | 7317.9324
|  | HP Equipment Replacement - 5% of total labor |  |  |  | 365896.6196 | labor costs x | 5% | = | 18294.831
|  | DGC OH &P on equipment and materials |  |  |  | 113045.7964 |  | 8% | = | 9043.6637
1.2 | Project Planning | [7 empty] | 200 |  | 200 | 600 | [6 empty] | 55065.2 | [5 empty] | 55065.2
1.2.1 | Procedure Development and Review | [7 empty] | 80 | 1 | 80 | 120 | [6 empty] | 11467.6
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 89.25 | 40 | 1 | 7140 | 80
|  |  | Project Manager |  |  | 1 | 108.19 | 40 | 1 | 4327.6 | 40
[6 empty] | 3 |  | 80 |  | 11467.6 | 120
1.2.2 | Preparation of QA and Safety Documents | [7 empty] | 80 | 1 | 80 | 120 | [6 empty] | 11467.6
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 89.25 | 40 | 1 | 7140 | 80
|  |  | Project Manager |  |  | 1 | 108.19 | 40 | 1 | 4327.6 | 40
[6 empty] | 3 |  | 80 |  | 11467.6 | 120
1.2.3 | Site Mobilization and General Employee Training (GET) | [7 empty] | 40 | 1 | 40 | 360 | [6 empty] | 32130
|  | 1.2.3.1 | Site Mobilization | [5 empty] | 40 | 1 | 40 | 360 | [6 empty] | 32130
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 9 | Decom Technician / Safety SME |  | 89.25 | 803.25
|  |  | Receipt of material and equipment |  |  | 16 | hr
|  |  | Staging of equipment |  |  | 8 | hr
|  |  | Set up office and amenities |  |  | 12 | hr
|  |  | Familiarize staff with facility |  |  | 4 | hr
[6 empty] | 40 | hr
|  |  | Total Cost = |  | 40 | x | 803.25 | 32130
|  | 1.2.3.2 | General Employee Training (All proj. management and 3 crews of 4) | [5 empty] | 0 | 1 | 0 | 0 | [5 empty] | 0 | 0
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Portfolio Manager |  | 157.87 | 157.87
|  |  | 1 | Senior Project Manager / Characterization SME |  | 127.28 | 127.28
|  |  | 1 | Project Manager / Waste Management |  | 108.19 | 108.19
|  |  | 9 | Decom Technician / Safety SME |  | 89.25 | 803.25
|  |  | 12 |  |  |  | 1196.59
[8 empty] | Number | Test | Labor | Total
[7 empty] | Unit Cost | Required | Cost | Costs | Cost
|  |  | In-Vivo |  |  |  | 600 | 0 | 0 | 0 | 0
|  |  | In-Vitro |  |  |  | 350 | 0 | 0 | 0 | 0
|  |  | Physical @ |  | 0 | hour and | 150 | 0 | 0 | 0 | 0
|  |  | Resp. Tests |  | 0 | hour and | 50 | 0 | 0 | 0 | 0
|  |  | Resp Fit Tests |  | 0 | hour and | 25 | 0 | 0 | 0 | 0
|  |  | Blood Tests |  | 0 | hour and | 125 | 0 | 0 | 0 | 0
|  |  | OSHA recertification |  | 0 | hour |  |  |  | 0 | 0
|  |  | Site specific 1 week of training |  | 0 | hour |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0 | 0
1.3 | Preliminary Site Investigation | [7 empty] | 176 |  | 176 | 480 | [6 empty] | 44658.24 | [5 empty] | 44658.24
1.3.1 | Decontamination Readiness Review - (Contractor staff cost included in Undistributed Costs) | [7 empty] | 80 | 1 | 80
1.3.2 | Site Preparation | [5 empty] | A |  | 96 | 1 | 96 | 480 | [6 empty] | 44658.24
| 1.3.2.1 | Initial Site Survey |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.2 | Setup work areas | [6 empty] | 32 |  | 32 | 160 | [6 empty] | 14886.08
| 1.3.2.2.1 | Setup boundaries, install HEPA filters & seal off openings |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.2.2 | Establish staging area |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.3 | Setup Rad. and Non-Rad. segregation and packaging stations |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.4 | Isolate Bldg B70 | [6 empty] | 32 |  | 32 | 160 | [6 empty] | 14886.08
| 1.3.2.4.1 | Electrical |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.4.2 | Piping |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
1.4 | Detailed Charaterisation | [7 empty] | 40 | 1 | 40 | 0 | [6 empty] | 0 | [5 empty] | 0
|  |  |  | Estimated Duration | 40 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 0 | 89.25 | 40 | 1 | 0 | 0
|  |  | Project Manager |  |  | 0 | 108.19 | 40 | 1 | 0 | 0
[6 empty] | 0 |  | 80 |  | 0 | 0
1.5 | Decontamination | [11 empty] | 0 | 41.5507 |  | 0.43863 | 33.6206 |  | 228298.2129 | [5 empty] | 228298.2129
[6 empty] | Removal Rate, Australian dollars | Units | Cost | Adjustment | Clean Disposal volume rate | Units | Clean Disposal Volume, cubic meters | LLW Disposal volume rate | Units | LLW Disposal Volume, cubic meters | Hazardous Disposal volume rate | Units | Hazardous Disposal Volume, cubic meters | Mixed Disposal volume rate | Units | Mixed Disposal Volume, cubic meters
1.5.1 | Asbestos Removal
| 1.5.1.1 | Remove contaminated asbestos pipe insulation |  |  |  | 541.3837 | /meter | 165013.7558 |  | 0.046153 | meter^3/meter | [7 empty] | 0.046153 | meter^3/meter | 14.0676
| 1.5.1.2 | Remove asbestos tile |  |  |  | 116.5036 | /m^2 |  |  | 0.030615 | meter^3/meter^2
1.5.2 | Remove systems and Components
| 1.5.2.1 | Sys. Clean |  |  |  | 452.9911 | /m^2 | 34475.7719 | -50% | 0.21097 | meter^3/meter^2 | 32.1128
| 1.5.2.2 | Sys. LLW |  |  |  | 310.9417 | /m^2 | 0 | -50% |  |  |  | 0.021826 | meter^3/meter^2 | 0
| 1.5.2.3 | Sys. Hazardous |  |  |  | 8.3976 | /m^2 | 639.1153 | -50% | [6 empty] | 0.00034797 | meter^3/meter^2 | 0.052966
| 1.5.2.4 | Sys. Mixed |  |  |  | 6.6155 | /m^2 | 503.4848 | -50% | [9 empty] | 0.0028817 | meter^3/meter^2 | 0.43863
35618.372
1.5.3 | Decontaminate Structure
| 1.5.3.1 | Decon Clean |  |  |  | 13.6125 | /m^2 | 0 | -50% | 0.0099056 | meter^3/meter^2 | 1.5078
| 1.5.3.2 | Decontaminate Hot Cells |  |  |  | 0 | /m^2 | 0 | -50% |  |  |  | 0.0025425 | meter^3/meter^2 | 0
| 1.5.3.3 | Remove hazardous material |  |  |  | 0 | /m^2 | 0 | -50% | [6 empty] | 0.27263 | meter^3/meter^2 | 41.4978
| 1.5.3.4 | Decon Contaminated |  |  |  | 320.8294 | /m^2 | 0 | -50% |  |  |  | 0.0008445 | meter^3/meter^2 | 0
0
1.5.4 | Final Survey |  |  |  |  | 181.7579 | /m^2 | 27666.0851
1.6 | Site Remediation | [15 empty] | 135.9398 |  | 37874.9667 | [5 empty] | 37874.9667
1.6.1 | Remove Building |  |  |  |  | 341.4286 | /m^2 | 25985.0897 | -50% | 0.77087 | meter^3/meter^2 | 117.3377
1.6.2 | Remove hot cell |  |  |  |  | 0 | /m^2 | 0 |  | 0.12221 | meter^3/meter^2 | 18.602
1.6.3 | Grade and seed (assume an area 2X building footprint) |  |  |  |  | 11.8684 | /m^2 | 3613.0567
1.6.4 | Backfill (assume building footprint x 10' deep) |  |  |  |  | 17.84 | /cuft | 8276.8203
37874.9667
1.7 | Waste Disposal |  |  |  |  | 0.028317 | 100 | lbs/cuft | [12 empty] | 36683.8052 |  | 12807.0714 | 89819.688 | 139310.5647
[5 empty] | Volume, cuft | Volume, m^3 | Tonnes | Rate | Cost
|  | Sys. Clean |  |  | 5987.9792 | 169.5604 | 299.399 | 300 | 89819.688
|  | Sys. LLW |  |  | 0 | 0 | 0
|  | Sys. Hazardous |  |  | 1467.3522 | 41.5507 | 73.3676 | 500 | 36683.8052
|  | Sys. Mixed |  |  | 512.2829 | 14.5062 | 25.6141 | 500 | 12807.0714

## Building XX
B XX DATA - Data highlighted in GREEN should be adjusted as needed
[9 empty] | Uncorrected Duration | [6 empty] | Mixed | Clean | Materials, |  |  | Hazardous |  | Mixed | Clean
| GENERIC TEMPLATE | [6 empty] | Crew | (No. of Hours) | Prod. Factor | Adjusted Duration (hrs) | Man-hours | LSA Waste Disp. Vol (cm) | Hazardous Waste Vol (cm) |  | Mixed Waste Volume (cm) | Clean Waste Volume (cm) | Materials, Consumables & Equipment | Labor Cost | LSA Waste Costs | Hazardous Waste Costs | LSA Waste Costs | Mixed Waste Costs | Clean Waste Costs | Total Cost
1.0 | Building XX | [9 empty] | 647 | 6605 | 39.257 | 425.0234 |  | 4.4867 | 1734.4379 | 1843799.953 | 11009187.42 |  | 375239.612 |  | 3961.1919 | 918767.9592 | 14150956.13
1.1 | Project Management | [16 empty] | 1843799.953 | 256232.55 | [5 empty] | 2100032.503
1.1.1 | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
| Portfolio Manager |  |  | 1 | 157.87 | 105 | 1 | 132610.8 | 1050
| Senior Project Manager / Characterization SME |  |  | 1 | 127.28 | 105 | 0.5 | 66822 | 525
| Project Manager / Waste Management |  |  | 1 | 108.19 | 105 | 0.5 | 56799.75 | 525
| Decom Technician / Safety SME |  |  | 0 | 89.25 | 105 | 1 | 0 | 1050
|  |  |  | 3 |  |  |  | 256232.55 | 3150
1.1.2 | Equipment & Materials
US
|  | Equipment |  |  | Quantity | Rate | Escalated Cost
|  | HEPA filter systems |  |  | 2 | 3598.14 | 11371.1239
|  | Replacement filters |  |  | 24 | 581.07 | 22036.1152
|  | Respirator |  |  | 12 | 259 | 4911.0725
|  | Rad/Vac wet-dry high eff. vacuum |  |  | 1 | 3879 | 6129.3598
|  | Rad/Vac wet-dry high eff. vacuum filters |  |  | 5 | 412 | 3255.0867
|  | Reciprocating Saws |  |  | 5 | 1252.26 | 9893.7254
|  | Pneumatic chipping hammers |  |  | 2 | 1606.71 | 5077.6508
|  | Chipping hammer blades |  |  | 20 | 27.42 | 866.5483
|  | Purchase an air compressor: |  |  | 2 | 1723.44 | 5446.5501
|  | Jackhammer |  |  | 4 | 1417.11 | 8956.9241
|  | Jackhammer Chisels |  |  | 10 | 24.35 | 384.7639
|  | Safety glasses |  |  | 15 | 8.6 | 203.838
|  | Fall protection - harness |  |  | 6 | 208 | 1972.0137
|  | Fall protection - lanyard |  |  | 6 | 367 | 3479.4665
|  | Hardhats |  |  | 15 | 35.5 | 841.4241
|  | Hard hat hearing protection |  |  | 15 | 37.6 | 891.1985
|  | Trailer rental |  |  | 1 | 416 | 657.3379
|  | Phone and computer hook-up |  |  | 1 | 250 | 395.0348
|  | Industrial hygiene instrumentation, calibration and hygienists - 1% of total activity $. |  |  | 0 |  | 0
|  | Tractor loader, wheeled |  |  | 1 | 7160.5905 | 11314.7295
|  | Wheeled Skid steer with conc. Hammer |  |  | 1 | 4421.3693 | 6986.3788
|  | Excavator |  |  | 1 | 28738.389 | 45410.6542
|  | Floor Shaver |  |  | 1 | 8000 | 12641.1134
|  | Wall Shaver |  |  | 1 | 15000 | 23702.0876
|  | Man lift |  |  | 2 | 4727.44 | 14940.0263
|  | Crane rental for building removal |  |  | 1 | 15600 | 24650.1711
226414.3951
|  | Consumables |  | Quantity |  | Duration |  | # workers | quantity | Unit Qty | Unit Cost | Escalated Cost
|  | Coveralls |  | 2 | /man/day | 105 | days | 24 | 5040 | 1 | 11 | 87602.9157
|  | Hoods |  | 0.1 | /man/day | 105 | days | 24 | 252 | 1 | 0 | 0
|  | Shoe covers |  | 4 | /man/day | 105 | days | 24 | 10080 | 1 | 0.94 | 14972.1347
|  | Latex gloves |  | 4 | /man/day | 105 | days | 24 | 10080 | 1 | 0.94 | 14972.1347
|  | Rubber overshoes |  | 0.01 | /man/day | 105 | days | 24 | 25.2 | 1 | 3 | 119.4585
|  | Gloves |  | 0.01 | /man/day | 105 | days | 24 | 25.2 | 1 | 2 | 79.639
|  | Dosimeters |  | 1 | /man/year | 0.25 | year | 24 | 6 | 1 | 200 | 1896.167
|  | TLDs |  | 1 | /man/mo | 3 | month | 24 | 72 | 1 | 3 | 341.3101
|  | Bioassays |  | 2 | /man/year | 0.5 | year | 24 | 24 | 1 | 250 | 9480.835
|  | (Bioassays for aver. crew & management) | [9 empty] | 129464.5947
|  | Small Tools - 2% of total labor costs = |  |  |  | 10752954.87 | labor costs x | 2% | = | 215059.0973
|  | HP Equipment Replacement - 5% of total labor |  |  |  | 10752954.87 | labor costs x | 5% | = | 537647.7433
|  | DGC OH &P on equipment and materials |  |  |  | 1108585.83 |  | 8% | = | 88686.8664
1.2 | Project Planning | [7 empty] | 415 |  | 431 | 2925 | [6 empty] | 270994.1 | [5 empty] | 270994.1
1.2.1 | Procedure Development and Review | [7 empty] | 160 | 1 | 160 | 240 | [6 empty] | 22935.2
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 89.25 | 80 | 1 | 14280 | 160
|  |  | Project Manager |  |  | 1 | 108.19 | 80 | 1 | 8655.2 | 80
[6 empty] | 3 |  | 160 |  | 22935.2 | 240
1.2.2 | Preparation of QA and Safety Documents | [7 empty] | 160 | 1.1 | 176 | 240 | [6 empty] | 22935.2
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 89.25 | 80 | 1 | 14280 | 160
|  |  | Project Manager |  |  | 1 | 108.19 | 80 | 1 | 8655.2 | 80
[6 empty] | 3 |  | 160 |  | 22935.2 | 240
1.2.3 | Site Mobilization and General Employee Training (GET) | [7 empty] | 95 | 1 | 95 | 2445 | [6 empty] | 225123.7
|  | 1.2.3.1 | Site Mobilization | [5 empty] | 40 | 1 | 40 | 960 | [6 empty] | 85680
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 24 | Decom Technician / Safety SME |  | 89.25 | 2142
|  |  | Receipt of material and equipment |  |  | 16 | hr
|  |  | Staging of equipment |  |  | 8 | hr
|  |  | Set up office and amenities |  |  | 12 | hr
|  |  | Familiarize staff with facility |  |  | 4 | hr
[6 empty] | 40 | hr
|  |  | Total Cost = |  | 40 | x | 2142 | 85680
|  | 1.2.3.2 | General Employee Training (All proj. management and 3 crews of 4) | [5 empty] | 55 | 1 | 55 | 1485 | [5 empty] | 54054 | 139443.7
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Portfolio Manager |  | 157.87 | 157.87
|  |  | 1 | Senior Project Manager / Characterization SME |  | 127.28 | 127.28
|  |  | 1 | Project Manager / Waste Management |  | 108.19 | 108.19
|  |  | 24 | Decom Technician / Safety SME |  | 89.25 | 2142
|  |  | 27 |  |  |  | 2535.34
[8 empty] | Number | Test | Labor | Total
[7 empty] | Unit Cost | Required | Cost | Costs | Cost
|  |  | In-Vivo |  |  |  | 600 | 27 | 16200 | 0 | 16200
|  |  | In-Vitro |  |  |  | 350 | 27 | 9450 | 0 | 9450
|  |  | Physical @ |  | 4 | hour and | 150 | 27 | 4050 | 10141.36 | 14191.36
|  |  | Resp. Tests |  | 1 | hour and | 50 | 27 | 1350 | 2535.34 | 3885.34
|  |  | Resp Fit Tests |  | 1 | hour and | 25 | 27 | 675 | 2535.34 | 3210.34
|  |  | Blood Tests |  | 1 | hour and | 125 | 27 | 3375 | 2535.34 | 5910.34
|  |  | OSHA recertification |  | 8 | hour |  |  |  | 20282.72 | 20282.72
|  |  | Site specific 1 week of training |  | 40 | hour |  |  |  | 101413.6 | 101413.6
[5 empty] | 55 |  |  |  | 35100 | 139443.7 | 174543.7
1.3 | Preliminary Site Investigation | [7 empty] | 176 |  | 176 | 480 | [6 empty] | 44658.24 | [5 empty] | 44658.24
1.3.1 | Decontamination Readiness Review - (Contractor staff cost included in Undistributed Costs) | [7 empty] | 80 | 1 | 80
1.3.2 | Site Preparation | [5 empty] | A |  | 96 | 1 | 96 | 480 | [6 empty] | 44658.24
| 1.3.2.1 | Initial Site Survey |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.2 | Setup work areas | [6 empty] | 32 |  | 32 | 160 | [6 empty] | 14886.08
| 1.3.2.2.1 | Setup boundaries, install HEPA filters & seal off openings |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.2.2 | Establish staging area |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.3 | Setup Rad. and Non-Rad. segregation and packaging stations |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.4 | Isolate Bldg B56 | [6 empty] | 32 |  | 32 | 160 | [6 empty] | 14886.08
| 1.3.2.4.1 | Electrical |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
| 1.3.2.4.2 | Piping |  |  |  |  | A |  | 16 | 1 | 16 | 80 | [6 empty] | 7443.04
|  |  |  | Estimated Duration | 16 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 4 | 89.25 | 16 | 1 | 5712 | 64
|  |  | Project Manager |  |  | 1 | 108.19 | 16 | 1 | 1731.04 | 16
[6 empty] | 5 |  | 32 |  | 7443.04 | 80
1.4 | Detailed Charaterisation | [7 empty] | 40 | 1 | 40 | 3200 | [6 empty] | 297721.6 | [5 empty] | 297721.6
|  |  |  | Estimated Duration | 40 | hrs
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 8 | 89.25 | 320 | 1 | 228480 | 2560
|  |  | Project Manager |  |  | 2 | 108.19 | 320 | 1 | 69241.6 | 640
[6 empty] | 10 |  | 640 |  | 297721.6 | 3200
1.5 | Decontamination | [11 empty] | 39.257 | 425.0234 |  | 4.4867 | 343.9062 |  | 7688838.604 | [5 empty] | 7688838.604
[6 empty] | Removal Rate, Australian dollars | Units | Cost | Adjustment | Clean Disposal volume rate | Units | Clean Disposal Volume, cubic meters | LLW Disposal volume rate | Units | LLW Disposal Volume, cubic meters | Hazardous Disposal volume rate | Units | Hazardous Disposal Volume, cubic meters | Mixed Disposal volume rate | Units | Mixed Disposal Volume, cubic meters
1.5.1 | Asbestos Removal
| 1.5.1.1 | Remove contaminated asbestos pipe insulation |  |  |  | 1443.6899 | /meter | 0 |  | 0.046153 | meter^3/meter | [7 empty] | 0.046153 | meter^3/meter | 0
| 1.5.1.2 | Remove asbestos tile |  |  |  | 116.5036 | /m^2 |  |  | 0.030615 | meter^3/meter^2
1.5.2 | Remove systems and Components
| 1.5.2.1 | Sys. Clean |  |  |  | 1207.9763 | /m^2 | 2821228.641 | 50% | 0.21097 | meter^3/meter^2 | 328.4832
| 1.5.2.2 | Sys. LLW |  |  |  | 829.1779 | /m^2 | 1936545.031 | 50% |  |  |  | 0.021826 | meter^3/meter^2 | 33.9834
| 1.5.2.3 | Sys. Hazardous |  |  |  | 22.3936 | /m^2 | 52300.2217 | 50% | [6 empty] | 0.00034797 | meter^3/meter^2 | 0.54179
| 1.5.2.4 | Sys. Mixed |  |  |  | 17.6413 | /m^2 | 41201.273 | 50% | [9 empty] | 0.0028817 | meter^3/meter^2 | 4.4867
4851275.167
1.5.3 | Decontaminate Structure
| 1.5.3.1 | Decon Clean |  |  |  | 36.3001 | /m^2 | 84778.8829 | 50% | 0.0099056 | meter^3/meter^2 | 15.4231
| 1.5.3.2 | Decontaminate Hot Cells |  |  |  | 0 | /m^2 | 0 | 50% |  |  |  | 0.0025425 | meter^3/meter^2 | 3.9587
| 1.5.3.3 | Remove hazardous material |  |  |  | 0 | /m^2 | 0 | 50% | [6 empty] | 0.27263 | meter^3/meter^2 | 424.4816
| 1.5.3.4 | Decon Contaminated |  |  |  | 855.5451 | /m^2 | 1998125.584 | 50% |  |  |  | 0.0008445 | meter^3/meter^2 | 1.3149
2082904.467
1.5.4 | Final Survey |  |  |  |  | 484.6878 | /m^2 | 754658.9708
1.6 | Site Remediation | [15 empty] | 1390.5317 |  | 2450742.322 | [5 empty] | 2450742.322
1.6.1 | Remove Building |  |  |  |  | 910.4763 | /m^2 | 2126417.348 | 50% | 0.77087 | meter^3/meter^2 | 1200.2509
1.6.2 | Remove hot cell |  |  |  |  | 0 | /m^2 | 0 |  | 0.12221 | meter^3/meter^2 | 190.2807
1.6.3 | Grade and seed (assume an area 2X building footprint) |  |  |  |  | 31.6489 | /m^2 | 98554.805
1.6.4 | Backfill (assume building footprint x 10' deep) |  |  |  |  | 47.5733 | /cuft | 225770.1691
2450742.322
1.7 | Waste Disposal |  |  |  |  | 0.028317 | 100 | lbs/cuft | [12 empty] | 375239.612 |  | 3961.1919 | 918767.9592 | 1297968.763
[5 empty] | Volume, cuft | Volume, m^3 | Tonnes | Rate | Cost
|  | Sys. Clean |  |  | 61251.1973 | 1734.4379 | 3062.5599 | 300 | 918767.9592
|  | Sys. LLW |  |  | 1386.3485 | 39.257 | 69.3174
|  | Sys. Hazardous |  |  | 15009.5845 | 425.0234 | 750.4792 | 500 | 375239.612
|  | Sys. Mixed |  |  | 158.4477 | 4.4867 | 7.9224 | 500 | 3961.1919

## Summary 2026
SUMMARY OF U.S. DCE DATA - INFORMATION ONLY. Do not change data on this workbook OR hidden files
Bldg 1
|  | 2009 | 2026
|  | Removal | Escalated |  | Waste Volume
| Floor area | 28033.8 |  | sq ft |  |  |  | Exchange rate | 2025-10-16 12:11 | 1.54 |  |  | Converted from US to Metric | [5 empty] | Waste Unit Rate, metric
[8 empty] | Summary |  |  | Average Removal Rate* |  | Asbestos | Asbestos tile | Sys. Clean | Sys. LLW | Sys. Hazardous | Sys. Mixed | Asbestos | Asbestos tile | Sys. Clean | Sys. LLW | Sys. Hazardous | Sys. Mixed
Asbestos removal | [7 empty] | Remove asbestos pipe insulation | 571.4762 | 4 | 721.845 | /meter | 0.18461 | [5 empty] | 0.046153
Remove asbestos pipe insulation |  | 76.9204 | 121.5449 | $/foot | 0.5 | cuft/ft | Asbestos | Remove asbestos tile | 14.0561 | 4 | 58.2518 | /m^2 |  | 0.12246 | [5 empty] | 0.030615
Remove asbestos tile |  | 2.0978 | 3.3149 | $/sq ft | 0.16152 | cuft/sqft | Asbestos tile | Remove systems and Components
[8 empty] | Sys. Clean | 182.1769 | 5 | 603.9881 | /m^2 |  |  | 1.0549 | [5 empty] | 0.21097
Remove systems and Components | [7 empty] | Sys. LLW | 125.0497 | 5 | 414.589 | /m^2 |  |  |  | 0.10913 | [5 empty] | 0.021826
Sys. Clean |  | 17.5405 | 27.7164 | /sqft | 0.17206 | cuft/sqft | Clean | Sys. Hazardous | 2.7018 | 4 | 11.1968 | /m^2 |  |  |  |  | 0.0013919 | [5 empty] | 0.00034797
Sys. LLW |  | 9.2782 | 14.6609 | /sqft | 0.11739 | cuft/sqft | LLW | Sys. Mixed | 2.1284 | 4 | 8.8207 | /m^2 | [5 empty] | 0.011527 | [5 empty] | 0.0028817
Sys. Hazardous |  | 1.4592 | 2.3058 | /sqft | 0.0045659 | cuft/sqft | Hazardous | Decontaminate Structure
Sys. Mixed |  | 1.347 | 2.1284 | /sqft | 0.037811 | cuft/sqft | Mixed | Decon Clean | 4.3796 | 4 | 18.15 | /m^2 |  |  | 0.039622 | [5 empty] | 0.0099056
[8 empty] | Decon Contaminated | 129.0262 | 5 | 427.7726 | /m^2 |  |  |  | 0.0042225 | [5 empty] | 0.0008445
Decontaminate Structure | [7 empty] | Final Survey | 73.0966 | 5 | 242.3439 | /m^2
Decon Clean | [5 empty] | cuft/sqft | Clean | Remove Building | 137.3105 | 5 | 455.2381 | /m^2 |  |  | 3.8544 | [5 empty] | 0.77087
Decon Contaminated |  | 3.5098 | 5.546 | /sqft | 0.00045741 | cuft/sqft | LLW | Grade and seed | 4.773 | 5 | 15.8245 | /m^2
[5 empty] | 0.036173 | cuft/sqft | Hazardous | Backfill | 1.7497 | 4 | 23.7866 | /m^3
[6 empty] | cuft/sqft | Mixed | Soil | 1.1557 | 2 | 31.4239 | /m^3
Final Survey |  | 0.79571 | 1.2573 | /sqft |  |  |  | Pipe - clean | 104.5204 | 1 | 528.0887 | /meter |  |  | 0.099324 | [5 empty] | 0.099324
[8 empty] | Pipe - contaminated | 138.8108 | 1 | 701.3406 | /meter |  |  |  | 0.099324 | [5 empty] | 0.099324
Remove Building |  | 7.1982 | 11.3742 | /sqft | 6.0597 | cuft/sqft | Clean | Hot Cell
[6 empty] | cuft/sqft | LLW | Hot Cell Clean | 13.9964 | 1 | 232.0175 | /m^2 |  |  | 0.037255 | [5 empty] | 0.037255
[6 empty] | cuft/sqft | Hazardous | Hot Cell LLW | 7.2894 | 1 | 120.8369 | /m^2 |  |  |  | 0.00077507 | [5 empty] | 0.00077507
[6 empty] | cuft/sqft | Mixed | Hot Cell Hazardous | 1.276 | 1 | 21.1518 | /m^2 |  |  |  |  | 0.083109 | [5 empty] | 0.083109
Grade and seed |  | 0.38063 | 0.60145 | /sqft |  |  |  | * Adjusted to Australian dollars
Backfill |  | 0.20719 | 0.32739 | /cuft
Remove Contaminated Soil and Pipe
Soil |  | 0.25899 | 0.40924 | /cuft
Pipe - clean |  | 66.1463 | 104.5204 | /ft | 1.069 | cuft/ft | Clean
Pipe - contaminated |  | 87.8472 | 138.8108 | /ft | 1.069 | cuft/ft | LLW
Bldg 2
|  | 2010 | 2026
|  | Removal | Escalated |  | Waste Volume
Asbestos removal
Remove asbestos pipe insulation |  | 74.6526 | 114.6147 | $/foot | 0.13974 | cuft/ft | asbestos
Remove asbestos tile |  | 2.036 | 3.1259 | $/sq ft | 0.064222 | cuft/sqft | asbestos tile
Remove systems and Components
Sys. Clean |  | 37.8194 | 58.0644 | $/sq ft | 3.107 | cuft/sqft | Clean
Sys. LLW |  | 15.9882 | 24.5468 | $/sq ft | 0.17582 | cuft/sqft | LLW
Sys. Hazardous |  | 0 | 0 | $/sq ft | 0 | cuft/sqft | Hazardous
Sys. Mixed |  | 0 | 0 | $/sq ft | 0 | cuft/sqft | Mixed
Decontaminate Structure
Decon Clean | [5 empty] | cuft/sqft | Clean
Decon Contaminated |  | 13.6252 | 20.9188 | /sqft | 0 | cuft/sqft | LLW
[5 empty] | 0.17582 | cuft/sqft | Hazardous
Hot Cell | [5 empty] | cuft/sqft | Mixed
Hot Cell Clean |  | 9.1163 | 13.9964 | /sqft | 0.12221 | cuft/sqft | Clean
Hot Cell LLW |  | 4.7479 | 7.2894 | /sqft | 0.0025425 | cuft/sqft | LLW
Hot Cell Hazardous |  | 0.83109 | 1.276 | /sqft | 0.27263 | cuft/sqft | Hazardous
Final Survey |  | 16.9579 | 26.0356 | /sqft
Remove Building |  | 15.2289 | 23.3811 | /sqft | 3.7552 | cuft/sqft | Clean
[6 empty] | cuft/sqft | LLW
[6 empty] | cuft/sqft | Hazardous
[6 empty] | cuft/sqft | Mixed
Grade and seed |  | 0.36941 | 0.58372 | /sqft
Backfill |  | 0.1828 | 0.28886 | /cuft
Bldg 3
|  | 2010 | 2026
|  | Removal | Escalated |  | Waste Volume
Asbestos removal
Remove asbestos pipe insulation |  | 82.1251 | 126.0874 | $/foot | 0.035452 | cuft/ft | asbestos
Remove asbestos tile |  | 2.2398 | 3.4387 | $/sq ft | 0.12965 | cuft/sqft | asbestos tile
Remove systems and Components
Sys. Clean |  | 8.3504 | 12.8205 | /sqft | 0.067919 | cuft/sqft | Clean
Sys. LLW |  | 12.1976 | 18.7271 | /sqft | 0.062637 | cuft/sqft | LLW
Sys. Hazardous |  | 0.25792 | 0.39599 | /sqft |  | cuft/sqft | Hazardous
Sys. Mixed |  |  | 0 | /sqft |  |  | Mixed
Decontaminate Structure
Decon Clean |  |  |  |  | 0.0049801 | cuft/sqft | LLW
Decon Contaminated |  | 2.6207 | 4.0236 | /sqft |  | cuft/sqft | Hazardous
[6 empty] | cuft/sqft | Mixed
Final Survey |  | 5.2658 | 8.0846 | /sqft
Remove Building |  | 5.0315 | 7.725 | /sqft | 1.6171 | cuft/sqft | Clean
[6 empty] | cuft/sqft | LLW
[6 empty] | cuft/sqft | Hazardous
[6 empty] | cuft/sqft | Mixed
Grade and seed |  | 0.36944 | 0.58377 | /sqft
Backfill |  | 0.18282 | 0.28888 | /cuft
Bldg 4
|  | 2012 | 2026
|  | Removal | Escalated |  | Waste Volume
Asbestos removal
Remove asbestos pipe insulation |  | 143.2532 | 209.2292 | $/foot | 1.3118 | cuft/ft | asbestos
Remove asbestos tile |  | 2.8596 | 4.1766 | $/sq ft | 0.046324 | cuft/sqft | asbestos tile
Remove systems and Components
Sys. Clean |  | 8.8489 | 12.9243 | $/sq ft | 0.11333 | cuft/sqft | Clean
Sys. LLW |  | 0.1877 | 0.27415 | $/sq ft | 0.0021378 | cuft/sqft | LLW
Sys. Hazardous |  | 0 | 0 | $/sq ft |  | cuft/sqft | Hazardous
Sys. Mixed |  |  | 0 | $/sq ft |  |  | Mixed
Decontaminate Structure
Decon Clean |  | 2.9986 | 4.3796 | /sqft | 0.125 | cuft/sqft | Clean
Decon Contaminated |  | 2.2543 | 3.2925 | /sqft | 0.013394 | cuft/sqft | LLW
[6 empty] | cuft/sqft | Hazardous
[6 empty] | cuft/sqft | Mixed
Final Survey |  | 18.8456 | 27.5251 | /sqft
Remove Building |  | 16.9924 | 24.8183 | /sqft | 1.2117 | cuft/sqft | Clean
Grade and seed |  | 0.75116 | 1.1869 | /sqft
Backfill |  | 0.5345 | 0.84458 | /cuft
Remove buried pipe
| Clean | 170.7546 | 249.3966 | /foot of pipe | 1.3405 | cuft/foot of pipe
| LLW | 271.0982 | 395.954 | /foot of pipe | 0.37855 | cuft/foot of pipe
Soil |  | 0.51111 | 0.74651 | /cuft
Remove foundations and shell below grade |  | 27.9615 | 40.8394 | /cuft
PWR - 2015
|  | 2015 | 2026
|  | Removal | Escalated |  | Waste Volume
Asbestos removal
Remove asbestos pipe insulation |  | 0 | 0 | $/foot | 0 | cuft/ft | asbestos
Remove asbestos tile |  | 0 | 0 | $/sq ft | 0 | cuft/sqft | asbestos tile
Remove systems and Components
Sys. Clean |  | 48.3728 | 70.6512 | $/sq ft | 0 | cuft/sqft | Clean
Sys. LLW |  | 45.764 | 66.8409 | $/sq ft | 0 | cuft/sqft | LLW
Sys. Hazardous |  | 0 | 0 | $/sq ft | 0 | cuft/sqft | Hazardous
Sys. Mixed |  | 0 | 0 | $/sq ft |  |  | Mixed
Decontaminate Structure
Decon Clean |  | 0 | 0 | /sqft | 0 | cuft/sqft | Clean
Decon Contaminated |  | 65.2117 | 95.2453 | /sqft | 0 | cuft/sqft | LLW
[6 empty] | cuft/sqft | Hazardous
[6 empty] | cuft/sqft | Mixed
Final Survey |  | 6.9796 | 10.1941 | /sqft
Remove Building |  | 47.9351 | 70.0119 | /sqft | 0 | cuft/sqft | Clean
Grade and seed |  | 1.15 | 1.8172 | /sqft
Backfill |  | 0 | 0 | /cuft

## REPORT INFO TABLES (hidden)
Facility | Description | Cost 2026 AUD
B17 | Material Storage | 3021527.8529
B18 | Workshop | 5178909.7886
B54 | Warehouse | 14159309.1686
B56 | Mo99 Process Facility | 14150956.1323
B70 | Laboratories | 765186.9129
| Total | 37275889.86

## BLDG 1 2009 (hidden)
[15 empty] | Mixed | Clean | Materials, |  |  | Hazardous |  | Mixed | Clean |  |  |  | Clean | Hazardous | LLW | Mixed
[8 empty] | Uncorrected Duration |  | Adjusted |  | LSA Waste | Hazardous | Ballast | Waste | Waste | Consumables, |  | LSA Waste | Waste | >LSA Waste | Waste | Waste |  | Removal |  | Waste | Waste | Waste | Waste
|  | Total floor area |  | 28033.8 | sqft |  | Crew | (No. of Hours) | Prod. Factor | Duration | Man-hours | Disp. Vol (cf) | Waste Vol (cf) | Volume (cf) | Volume (cf) | Volume (cf) | & Equipment | Labor Cost | Cost | Cost | Cost | Cost | Cost | Total Cost | Unit Rate |  | Volume | Volume | Volume | Volume
| Grand Total Building 310 | [22 empty] | 19285611.8169
| Contingency = |  | 25% | [20 empty] | 3857122.3634
2 | Total Building 310 | [22 empty] | 15428489.4535
| ANL Oversight @ 24% | [21 empty] | 24% | 2986159.2491
ANL Tax | General and Administration | [21 empty] | 2.9% | 74666.0198
ANL Tax | IGPP/IGPE | [21 empty] | 2.7% | 67689.0352
ANL Tax | Service Center | [21 empty] | 18.5% | 1811700.1613 | On total
ANL Tax | Material and Subcontracts Tax | [21 empty] | 7.1% | 695301.143 | On total
2 | Building 310 | [9 empty] | 41086.2007 | 62074.6589 | 140.8229 | 142 | 1060 | 252160.8726 | 1261378.3836 | 3091857.7892 | 4704633.3514 | 3758.9635 | 0 | 167932.2667 | 563413.0906 | 9792973.845
UNDISTRIBUTED COSTS | [10 empty] | 24428.5714 | [5 empty] | 873670.7058 | 2100477.1429 | 0 | 0 | 0 | 0 | 0 | 2974147.8487
|  | Project duration = |  |  | 380 | days/7days/wk = | 54.2857 | See Project Schedule
[5 empty] | 271.4286 | working days
|  | Average crew size = |  | 14842.6293 | man-hrs/ | 4894.2098 | sched-hrs = | 3
|  | Labor cost = |  | 991380.6464 | (Used to determine small tool costs and HP Supplies)
| 2.1 | Project Management | [8 empty] | 24428.5714 | [6 empty] | 1827257.1429 | [5 empty] | 1827257.1429
|  | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
|  | Project Manager |  |  | 1 | 100.85 | 271.4286 | 100% | 273735.7143 | 2714.2857
|  | Project Safety Manager |  |  | 1 | 78.56 | 271.4286 | 100% | 213234.2857 | 2714.2857
|  | Project Specialist |  |  | 1 | 67.91 | 271.4286 | 100% | 184327.1429 | 2714.2857
|  | Health Physicist |  |  | 1 | 89.16 | 271.4286 | 100% | 242005.7143 | 2714.2857
|  | Chief HP Tech |  |  | 1 | 57.77 | 271.4286 | 100% | 156804.2857 | 2714.2857
|  | Building Maintenance |  |  | 1 | 51.38 | 271.4286 | 100% | 139460 | 2714.2857
|  | Secretary |  |  | 1 | 31.79 | 271.4286 | 100% | 86287.1429 | 2714.2857
|  | Project Control Specialist |  |  | 1 | 97.64 | 271.4286 | 100% | 265022.8571 | 2714.2857
|  | HP Tech |  |  | 2 | 49.07 | 271.4286 | 100% | 266380 | 2714.2857
[5 empty] | 10 |  |  |  | 1827257.1429 | 24428.5714
| 2.2 | Project Management Per Diem | [15 empty] | 273220 | [5 empty] | 273220
[6 empty] | Per Diem | Number of
|  | Staff |  |  | Number | Rate, $/day | Days | Total
|  | Project Manager |  |  | 1 | 161 | 380 | 61180
|  | Project Safety Manager |  |  | 1 | 161 | 380 | 61180
|  | Project Specialist |  |  | 1 | 161 | 380 | 61180
|  | Health Physicist |  |  | 1 | 161 | 380 | 61180
|  | Chief HP Tech |  |  | 1 | 75 | 380 | 28500
[5 empty] | 5 |  |  | 273220
| 2.3 | Equipment & Materials | [14 empty] | 873670.7058 | [6 empty] | 873670.7058
|  | Equipment |  |  | Quantity | Rate | Cost
|  | HEPA filter systems |  |  | 2 | 3598.14 | 7196.28
|  | Replacement filters |  |  | 24 | 581.07 | 13945.68
|  | Respirator |  |  | 30 | 259 | 7770
|  | Rad/Vac wet-dry high eff. vacuum |  |  | 4 | 3879 | 15516
|  | Rad/Vac wet-dry high eff. vacuum filters |  |  | 10 | 412 | 4120
|  | Reciprocating Saws |  |  | 10 | 1252.26 | 12522.6
|  | Pneumatic chipping hammers |  |  | 4 | 1606.71 | 6426.84
|  | Chipping hammer blades |  |  | 20 | 27.42 | 548.4
|  | Purchase an air compressor: |  |  | 4 | 1723.44 | 6893.76
|  | Jackhammer |  |  | 4 | 1417.11 | 5668.44
|  | Jackhammer Chisels |  |  | 20 | 24.35 | 487
|  | Safety glasses |  |  | 150 | 8.6 | 1290
|  | Fall protection - harness |  |  | 22 | 208 | 4576
|  | Fall protection - lanyard |  |  | 22 | 367 | 8074
|  | Hardhats |  |  | 40 | 35.5 | 1420
|  | Hard hat hearing protection |  |  | 40 | 37.6 | 1504
|  | Trailer rental |  |  | 2 | 416 | 10387.4713
|  | Phone and computer hook-up |  |  | 1 | 250 | 3121.2354
|  | Industrial hygiene instrumentation, calibration and hygienists - 1% of total activity $. |  |  |  |  | 68188.26
|  | Tractor loader, wheeled |  |  | 1 | 7160.5905 | 66343.8787
|  | Wheeled Skid steer with conc. Hammer |  |  | 2 | 4421.3693 | 32248.7346
|  | Excavator |  |  | 2 | 28738.389 | 226608.6965
|  | Floor Shaver |  |  | 2 | 8000 | 13667.7253
|  | Wall Shaver |  |  | 2 | 15000 | 25626.985
|  | Man lift |  |  | 4 | 4727.44 | 91949.7694
|  | Crane rental for building removal |  |  | 1 | 15600 | 25626.985
661728.741
|  | Consumables |  | Quantity |  | Duration |  | # workers | quantity | Unit Qty | Unit Cost | Cost
|  | Coveralls |  | 2 | /man/day | 271.4286 | days | 6 | 3257.1429 | 1 | 8.7 | 28337.1429
|  | Hoods |  | 0.1 | /man/day | 271.4286 | days | 6 | 162.8571 | 1 | 0.93333 | 152
|  | Shoe covers |  | 4 | /man/day | 271.4286 | days | 6 | 6514.2857 | 1 | 0.37 | 2410.2857
|  | Latex gloves |  | 4 | /man/day | 271.4286 | days | 6 | 6514.2857 | 1 | 2 | 13028.5714
|  | Rubber overshoes |  | 0.01 | /man/day | 271.4286 | days | 6 | 16.2857 | 1 | 3 | 48.8571
|  | Gloves |  | 0.01 | /man/day | 271.4286 | days | 6 | 16.2857 | 1 | 1.63 | 26.5457
|  | Dosimeters |  | 1 | /man/year | 1.044 | year | 17 | 17.7473 | 1 | 201.7059 | 3579.7253
|  | TLDs |  | 1 | /man/mo | 12.5371 | month | 17 | 213.131 | 1 | 3 | 639.3929
|  | Bioassays |  | 2 | /man/year | 1.044 | year | 17 | 35.4945 | 1 | 25 | 887.3626
|  | (Bioassays for aver. crew & management) | [9 empty] | 49109.8837
|  | Small Tools - 2% of total labor costs = |  |  |  | 991380.6464 | labor costs x | 2% | = | 19827.6129
|  | HP Equipment Replacement - 5% of total labor |  |  |  | 991380.6464 | labor costs x | 5% | = | 49569.0323
|  | DGC OH &P on equipment and materials |  |  |  | 1167942.9478 |  | 8% | = | 93435.4358
ACTIVITIES | [7 empty] | 5307.2807 |  | 5502.2098 | 16657.6293 | 62074.6589 | 140.8229 | 142 | 1060 | 252160.8726 | 387707.6778 | 991380.6464 | 4704633.3514 | 3758.9635 | 0 | 167932.2667 | 563413.0906 | 6818825.9964
| 2.4 | Procedure Development and Review | [5 empty] | 240 | 1.1 | 264 | 440 | [6 empty] | 32779.12 | [5 empty] | 32779.12
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 67.91 | 160 | 1.1 | 23904.32 | 352
|  |  | Project Manager |  |  | 1 | 100.85 | 80 | 1.1 | 8874.8 | 88
[6 empty] | 3 |  | 240 |  | 32779.12 | 440
| 2.5 | Preparation of QA and Safety Documents | [5 empty] | 240 | 1.1 | 264 | 440 | [6 empty] | 32779.12 | [5 empty] | 32779.12
|  |  | Staff |  |  | Number | Rate | Duration | PLF |  | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 67.91 | 160 | 1.1 |  | 23904.32 | 352
|  |  | Project Manager |  |  | 1 | 100.85 | 80 | 1.1 |  | 8874.8 | 88
[6 empty] | 3 |  | 240 |  |  | 32779.12 | 440
| 2.6 | Site Mobilization and General Employee Training (GET) | [5 empty] | 80 | 1 | 80 | 1095 | [5 empty] | 22100 | 70221.55 | [5 empty] | 92321.55
|  | 2.6.1 | Site Mobilization |  |  |  |  | 40 |  |  | 160 | [6 empty] | 9571.84 | [5 empty] | 9571.84
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | HP Tech |  | 64.477 | 64.477
|  |  | 3 | Decon Techs |  | 58.273 | 174.819
|  |  | 4 |  |  |  | 239.296
|  |  | Receipt of material and equipment |  |  | 16 | hr
|  |  | Staging of equipment |  |  | 8 | hr
|  |  | Set up office and amenities |  |  | 12 | hr
|  |  | Familiarize staff with facility |  |  | 4 | hr
[6 empty] | 40 | hr
|  |  | Total Cost = |  | 40 | x | 239.296 | 9571.84
|  | 2.6.2 | General Employee Training (All proj. management and 2 crews of 4) |  |  |  |  | 40 | 1 |  | 935 | [5 empty] | 22100 | 60649.71 | [5 empty] | 82749.71
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Project Manager |  | 100.85 | 100.85
|  |  | 1 | Project Safety Manager |  | 78.56 | 78.56
|  |  | 1 | Project Specialist |  | 67.91 | 67.91
|  |  | 1 | Health Physicist |  | 89.16 | 89.16
|  |  | 1 | Chief HP Tech |  | 57.77 | 57.77
|  |  | 1 | Building Maintenance |  | 51.38 | 51.38
|  |  | 1 | Secretary |  | 31.79 | 31.79
|  |  | 1 | Project Control Specialist |  | 97.64 | 97.64
|  |  | 1 | HP Tech |  | 49.07 | 49.07
|  |  | 2 | HP Tech |  | 64.477 | 128.954
|  |  | 6 | Decon Techs |  | 58.273 | 349.638
|  |  | 17 |  |  |  | 1102.722
[8 empty] | Number | Test | Labor | Total
[7 empty] | Unit Cost | Required | Cost | Costs | Cost
|  |  | In-Vivo |  |  |  | 600 | 17 | 10200 |  | 10200
|  |  | In-Vitro |  |  |  | 350 | 17 | 5950 |  | 5950
|  |  | Physical @ |  | 4 | hour and | 150 | 17 | 2550 | 4410.888 | 6960.888
|  |  | Resp. Tests |  | 1 | hour and | 50 | 17 | 850 | 1102.722 | 1952.722
|  |  | Resp Fit Tests |  | 1 | hour and | 25 | 17 | 425 | 1102.722 | 1527.722
|  |  | Blood Tests |  | 1 | hour and | 125 | 17 | 2125 | 1102.722 | 3227.722
|  |  | OSHA recertification |  | 8 | hour |  |  |  | 8821.776 | 8821.776
|  |  | Site specific 1 week of training |  | 40 | hour |  |  |  | 44108.88 | 44108.88
[5 empty] | 55 |  |  |  | 22100 | 60649.71 | 82749.71
| 2.7 | Decontamination Readiness Review - (Contractor staff cost included in Undistributed Costs) | [5 empty] | 80 | 1 | 80
| 2.8 | Site Preparation |  |  |  |  | A | 152 | 1.21 | 178.64 | 535.92 | 0 | 0 | 0 | 0 | 0 | 12000 | 31229.6662 | 0 | 0 | 0 | 0 | 0 | 43229.6662
|  | 2.8.1 | Initial Site Survey |  |  |  | A | 16 | 1.21 | 19.36 | 58.08 | [6 empty] | 3384.4958 | [5 empty] | 3384.4958
|  |  |  | Estimated Duration | 16 | hrs
|  | 2.8.2 | Setup work areas |  |  |  |  | 32 |  | 37.84 | 113.52 | 0 | 0 | 0 | 0 | 0 | 1000 | 6615.151 | [5 empty] | 7615.151
|  | 2.8.2.1 | Setup boundaries, install HEPA filters & seal off openings |  |  |  | A | 24 | 1.21 | 29.04 | 87.12 | 0 | 0 |  |  |  | 1000 | 5076.7438 | [5 empty] | 6076.7438
(estimated)
|  | 2.8.2.2 | Establish staging area |  |  |  | A | 8 | 1.1 | 8.8 | 26.4 | 0 | 0 |  |  |  |  | 1538.4072 | [5 empty] | 1538.4072
|  | 2.8.3 | Setup Rad. and Non-Rad. segregation and packaging stations |  |  |  | A | 40 | 1.1 | 44 | 132 |  |  |  | 0 |  | 1000 | 7692.036 | [5 empty] | 8692.036
|  | 2.8.4 | Isolate Bldg 310 |  |  |  |  | 64 |  | 77.44 | 232.32 | 0 | 0 | 0 | 0 | 0 | 10000 | 13537.9834 | 0 |  | 0 | 0 | 0 | 23537.9834
|  | 2.8.4.1 | Electrical |  |  |  | A | 24 | 1.21 | 29.04 | 87.12 |  |  |  | 0 |  | 5000 | 5076.7438 | [5 empty] | 10076.7438
(new material allowance)
|  | 2.8.4.2 | Piping |  |  |  | A | 40 | 1.21 | 48.4 | 145.2 |  |  |  | 0 |  | 5000 | 8461.2396 | [5 empty] | 13461.2396
(new material allowance)
| 2.9 | Remove Miscellaneous Material |  |  |  |  | A | 40 | 1 | 40 | 120 | [6 empty] | 6992.76 | [5 empty] | 6992.76
All material appears to have been removed from building.
| 2.10 | Remove Asbestos |  |  |  |  | A | 726.891 | 1.1 | 799.5801 | 2398.7403 | 0 | 0 |  | 0 | 5321.1 |  | 139781.7935 | 0 | 0 |  | 0 | 16587.3796 | 156369.1731
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove asbestos pipe insulation |  |  | 5673 |  | 2836.5 | 0% | 2836.5 | 3.5019 | 0.11 | crew hrs/ft | 624.03 | 2009 mean, p33, 02 82 13.43 1200 with glove bags | [8 empty] | 76.9204 | /foot | 0.5 | cu. ft./ft
|  |  | Clean | Remove asbestos tile |  |  |  | 9589.5 | 1747.6 | 0% | 1747.6 | 2.1575 | 0.003 | crew hrs/sq. ft. | 28.7685 | 2009 mean, p33, 02 82 13.43 5000 | [8 empty] | 2.0978 | /sq ft | 0.16152 | cu. ft./sq.ft
|  |  | Clean | Remove carpet |  |  |  | 2849 | 287 | 0% | 287 | 0.35432 | 0.0015 | crew hrs/sq. ft. | 4.2735 | Productivity estimated at 2x that of VAT removal.
|  |  | Clean | Remove asbestos tile from Main floor |  |  |  | 3273 | 330 | 0% | 330 | 0.40741 | 0.003 | crew hrs/sq. ft. | 9.819 | 2009 mean, p33, 02 82 13.43 5000
|  |  | Clean | Remove asbestos fire door |  | 15 |  |  | 120 | 0% | 120 | 0.14815 | 4 | crew hrs/comp | 60 | estimated
[11 empty] | 5321.1 | 6.5693 |  |  | 726.891
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 5321.1 | 6.5693 | 0 | 3284.6296 | 13302.75 | 16587.3796
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Fluorescent light ballasts, lbs |  | 0 | 0 | 0 | 0 | 0 | 0
| 2.11 | Remove systems and components | [5 empty] | 1195.6563 |  | 1195.6563 | 3586.969 | 3290.906 | 128 | 142 | 1060 | 4823.455 | 0 | 209023.4445 | 222568.1373 | 2996 | 0 | 167932.2667 | 14836.5727 | 617356.4212 | 7.4561 | /sqft
|  |  | Assumptions: | [6 empty] | 703.1943 | [13 empty] | Clean | 17.5405 |  | 0.17206
|  |  | 1. Fluorescent lights have PCB containing ballasts, except in the addition | [6 empty] | 371.962 | [13 empty] | Contmainted | 9.2782 |  |  |  | 0.11739
|  |  | 2. Ballasts packaged in 55 gallon drums and disposed of as hazardous waste | [6 empty] | 58.5 | [13 empty] | Hazardous | 1.4592 |  |  | 0.0045659
|  |  | 3. Clean waste packaged in 30 cu. yd. containers | [6 empty] | 54 | [13 empty] | Mixed | 1.347 |  |  |  |  | 0.037811
4. LSA disposal includes 10.2059% tax
5. Asbestos will be double bagged and disposed of at a controlled landfill licensed to accept ACM
6. Productivity factors are included in the rates, unless otherwise specified.
|  | 2.11.1 | Remove systems from Fan Loft |  |  |  | A | 19 | 1 | 19 | 57 | 0 |  | 8 | 0 | 16 |  | 3321.561 | 0 | 94 |  | 0 | 49.8765 | 3465.4375
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Weight, lbs | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | HVAC equipment |  | 2 |  |  | 8 | 0% | 8 | 0.0098765 | 4 | crew hrs/comp | 8 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | Fluorescent lights |  | 12 |  |  | 6 | 0% | 6 | 0.0074074 | 0.25 | crew hrs/comp | 3 | UCF 63 - <300 lbs
|  |  | Hazardous | Fluorescent light ballasts, lbs |  | 12 | 36 |  |  | 0% | 0 | 1 | 0.25 | crew hrs/comp | 3 | UCF 63 - <300 lbs
|  |  | Clean | Miscellaneous equipment |  | 2 |  |  | 2 | 0% | 2 | 0.0024691 | 2.5 | crew hrs/comp | 5 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 16 | 1.0198 |  |  | 19
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 16 | 0.019753 | 0 | 9.8765 | 40 | 49.8765
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Fluorescent light ballasts, lbs |  | 8 | 1 | 65 | 11 | 18 | 94
|  | 2.11.2 | Remove systems from Balcony Lab Fan Area |  |  |  | A | 13 | 1 | 13 | 39 | 0 |  | 8 | 0 | 64 |  | 2272.647 | 0 | 94 |  | 0 |  | 2366.647
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Weight, lbs | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Tanks, 50 - 300 gals |  | 1 |  |  | 16 | 0% | 16 | 0.019753 | 2 | crew hrs/comp | 2 | UCF 50 - Tanks 50 - 300 gals.
|  |  | Clean | Fluorescent lights |  | 12 |  |  | 6 | 0% | 6 | 0.0074074 | 0.25 | crew hrs/comp | 3 | UCF 63 - <300 lbs
|  |  | Hazardous | Fluorescent light ballasts, lbs |  | 12 | 36 |  |  | 0% | 0 | 1 | 0.25 | crew hrs/comp | 3 | UCF 63 - <300 lbs
|  |  | Clean | Miscellaneous equipment |  | 2 |  |  | 42 | 0% | 42 | 0.051852 | 2.5 | crew hrs/comp | 5 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 64 | 1.079 |  |  | 13
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 64 | 0.079012 | 0 | 39.5062 | 160 | 199.5062
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Fluorescent light ballasts, lbs |  | 8 | 1 | 65 | 11 | 18 | 94
|  | 2.11.3 | Remove systems from Main Floor |  |  |  | A | 144.3 | 1 | 144.3 | 432.9 | 100.5 | 128 | 69.6 | 0 | 607 |  | 25226.3817 | 7662.79 | 2131.2 |  | 0 | 1892.1914 | 36912.5631
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | HVAC duct |  |  | 133 |  | 201 | 50% | 100.5 | 1.0469 | 0.1 | crew hrs/ft | 13.3 | UCF 69 - Remove Ductwork
|  |  | Clean | HVAC equipment |  | 5 |  |  | 325 | 0% | 325 | 0.40123 | 4 | crew hrs/comp | 20 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | Fluorescent lights |  | 116 |  |  | 58 | 0% | 58 | 0.071605 | 0.25 | crew hrs/comp | 29 | UCF 63 - <300 lbs
|  |  | Hazardous | Fluorescent light ballasts, lbs |  | 116 | 348 |  |  | 0% | 0 | 8.7 | 0.25 | crew hrs/comp | 29 | UCF 63 - <300 lbs
|  |  | Mercury | Mercury vapor lights, lbs |  | 16 | 160 |  |  | 0% | 0 | 16 | 0.5 | crew hrs/comp | 8 | estimated
|  |  | Clean | Miscellaneous equipment |  | 18 |  |  | 224 | 0% | 224 | 0.27654 | 2.5 | crew hrs/comp | 45 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 707.5 | 26.4963 |  |  | 144.3
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 607 | 0.74938 | 0 | 374.6914 | 1517.5 | 1892.1914
|  |  |  | Contaminated |  | 100.5 | 1.0469 | 1465.625 | 837.5 | 5359.665 | 7662.79
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Fluorescent light ballasts, lbs |  | 69.6 | 8.7 | 565.5 | 95.7 | 174 | 835.2
|  |  | (Use same logic as flour. Ballasts, except 1 /drum) | Mercury vapor lights |  | 128 | 16 | 1040 | 176 | 80 | 1296
|  | 2.11.4 | Remove systems from A114 |  |  |  | A | 6.5133 | 1 | 6.5133 | 19.54 | 15.5 | 0 |  | 0 | 35.681 |  | 1138.6544 | 1181.8233 | 0 |  | 0 | 111.2278 | 2431.7056
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | HVAC duct |  |  | 5 |  | 31 | 50% | 15.5 | 0.16146 | 0.1 | crew hrs/ft | 0.5 | UCF 69 - Remove Ductwork
|  |  | Clean | HVAC equipment |  | 1 |  |  | 31 | 0% | 31 | 0.038272 | 4 | crew hrs/comp | 4 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | <2" pipe |  |  | 151 |  | 4.681 | 0% | 4.681 | 0.005779 | 0.013333 | crew hrs/ft | 2.0133 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
[11 empty] | 51.181 | 0.20551 |  |  | 6.5133
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 35.681 | 0.044051 | 0 | 22.0253 | 89.2025 | 111.2278
|  |  |  | Contaminated |  | 15.5 | 0.16146 | 226.0417 | 129.1667 | 826.615 | 1181.8233
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Fluorescent light ballasts, lbs |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.11.5 | Remove systems from Service Floor |  |  |  | A | 459.2 | 1 | 459.2 | 1377.6 | 2218.775 |  | 7.8 | 1060 | 1547.5 |  | 80276.8848 | 169174.1978 | 93.6 |  | 167932.2667 | 4823.9969 | 422300.9462
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | HVAC duct |  |  | 1987 |  | 4437.55 | 50% | 2218.775 | 23.1122 | 0.1 | crew hrs/ft | 198.7 | UCF 69 - Remove Ductwork
|  |  | Clean | HVAC equipment |  | 39 |  |  | 1346 | 0% | 1346 | 1.6617 | 4 | crew hrs/comp | 156 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | Remove tanks, 0 - 50 gals |  | 8 |  |  | 23 | 0% | 23 | 0.028395 | 1 | crew hrs/comp | 8 | UCF 49 - Tanks <50 gals.
|  |  | Clean | Remove tanks, 50 - 300 gals |  | 8 |  |  | 97 | 0% | 97 | 0.11975 | 2 | crew hrs/comp | 16 | UCF 50 - Tanks 50 - 300 gals.
|  |  | Mixed | Remove tanks, 4k - 15k gals |  | 2 |  |  | 1060 | 0% | 1060 | 11.0417 | 27 | crew hrs/comp | 54 | UCF 52 - Tanks 4k - 15k gals.
|  |  | Clean | Fluorescent lights |  | 13 |  |  | 6.5 | 0% | 6.5 | 0.0080247 | 0.25 | crew hrs/comp | 3.25 | UCF 63 - <300 lbs
|  |  | Hazardous | Fluorescent light ballasts, lbs |  | 13 | 39 |  |  | 0% | 0 | 0.975 | 0.25 | crew hrs/comp | 3.25 | UCF 63 - <300 lbs
|  |  | Clean | Miscellaneous equipment |  | 8 |  |  | 75 | 0% | 75 | 0.092593 | 2.5 | crew hrs/comp | 20 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 4826.275 | 37.0394 |  |  | 459.2
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 1547.5 | 1.9105 | 0 | 955.2469 | 3868.75 | 4823.9969
|  |  |  | Contaminated |  | 2218.775 | 23.1122 | 32357.1354 | 18489.7917 | 118327.2708 | 169174.1978
|  |  |  | Mixed |  | 1060 | 11.0417 | 15458.3333 | 8833.3333 | 143640.6 | 167932.2667
|  |  |  | Fluorescent light ballasts, lbs |  | 7.8 | 0.975 | 63.375 | 10.725 | 19.5 | 93.6
|  | 2.11.6 | Remove systems from Roof and Outside Areas |  |  |  | A | 30.5 | 1 | 30.5 | 91.5 | 0 | 0 |  | 0 | 1190 |  | 5331.9795 | 0 | 0 |  | 0 | 3709.5679 | 9041.5474
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | HVAC equipment |  | 7 |  |  | 1182 | 0% | 1182 | 1.4593 | 4 | crew hrs/comp | 28 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | Miscellaneous equipment |  | 1 |  |  | 8 | 0% | 8 | 0.0098765 | 2.5 | crew hrs/comp | 2.5 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 1190 | 1.4691 |  |  | 30.5
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 1190 | 1.4691 | 0 | 734.5679 | 2975 | 3709.5679
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Fluorescent light ballasts, lbs |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.11.7 | Remove Pipe from Building |  |  |  | A | 406.0863 | 1 | 406.0863 | 1218.259 | 956.131 | 0 |  | 0 | 956.131 |  | 70991.6067 | 44549.3262 | 0 |  | 0 | 2980.5318 | 118521.4647
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | 0 - 2" pipe, clean |  |  | 10534 |  | 326.554 | 0% | 326.554 | 0.40315 | 0.013333 | crew hrs/ft | 140.4533 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 2 - 3.5" pipe, clean |  |  | 1481 |  | 128.847 | 0% | 128.847 | 0.15907 | 0.017667 | crew hrs/ft | 26.1643 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 4 - 6" pipe, clean |  |  | 1151 |  | 276.24 | 0% | 276.24 | 0.34104 | 0.053333 | crew hrs/ft | 61.3867 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, use 2/3 of duration)
|  |  | Clean | 8 - 14" pipe, clean |  |  | 210 |  | 224.49 | 0% | 224.49 | 0.27715 | 0.088667 | crew hrs/ft | 18.62 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, use 2/3 of duration)
|  |  | Contaminated | 0 - 2" pipe, contam. |  |  | 964 |  | 29.884 | 0% | 29.884 | 0.31129 | 0.018 | crew hrs/ft | 17.352 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
|  |  | Contaminated | 2 - 3.5" pipe, contam. |  |  | 1022 |  | 88.914 | 0% | 88.914 | 0.92619 | 0.02385 | crew hrs/ft | 24.3747 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
|  |  | Contaminated | 4 - 6" pipe, contam. |  |  | 1454 |  | 348.96 | 0% | 348.96 | 3.635 | 0.072 | crew hrs/ft | 104.688 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
|  |  | Contaminated | 8 - 14" pipe, contam. |  |  | 109 |  | 116.521 | 0% | 116.521 | 1.2138 | 0.1197 | crew hrs/ft | 13.0473 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
[11 empty] | 1540.41 | 7.2666 |  |  | 406.0863
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 956.131 | 1.1804 | 0 | 590.2043 | 2390.3275 | 2980.5318
|  |  |  | Contaminated |  | 584.279 | 6.0862 | 8520.7354 | 4868.9917 | 31159.5991 | 44549.3262
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Fluorescent light ballasts, lbs |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.11.8 | Remove Systems from Addition |  |  |  | A | 117.0567 | 1 | 117.0567 | 351.17 | 0 |  | 48.6 | 0 | 407.143 |  | 20463.7294 | 0 | 583.2 |  | 0 | 1269.1803 | 22316.1097
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | 0 - 2" pipe, clean |  |  | 703 |  | 21.793 | 0% | 21.793 | 0.026905 | 0.013333 | crew hrs/ft | 9.3733 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 2 - 3.5" pipe, clean |  |  | 50 |  | 4.35 | 0% | 4.35 | 0.0053704 | 0.017667 | crew hrs/ft | 0.88333 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | HVAC duct |  |  | 398 |  | 401 | 50% | 200.5 | 0.24753 | 0.1 | crew hrs/ft | 39.8 | UCF 69 - Remove Ductwork
|  |  | Clean | HVAC equipment |  | 6 |  |  | 140 | 0% | 140 | 0.17284 | 4 | crew hrs/comp | 24 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | Miscellaneous equipment |  | 1 |  |  | 0 | 0% | 0 | 0 | 2.5 | crew hrs/comp | 2.5 | UCF 64 - 300 to 1,000 lbs
|  |  | Clean | Fluorescent light fixtures |  | 81 |  |  | 40.5 | 0% | 40.5 | 0.05 | 0.25 | crew hrs/comp | 20.25 | UCF 63 - <300 lbs
|  |  | Hazardous | Fluorescent light ballasts, lbs |  | 81 | 243 |  |  | 0% | 0 | 6.075 | 0.25 | crew hrs/comp | 20.25 | UCF 63 - <300 lbs
[11 empty] | 407.143 | 6.5776 |  |  | 117.0567
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 407.143 | 0.50265 | 0 | 251.3228 | 1017.8575 | 1269.1803
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Fluorescent light ballasts, lbs |  | 48.6 | 6.075 | 394.875 | 66.825 | 121.5 | 583.2
| 2.12 | Decontaminate Structures | [5 empty] | 562.8271 |  | 562.8271 | 1688.4813 | 1014.0729 | 12.8229 | 0 | 0 | 0 | 0 | 98392.8683 | 77319.6797 | 762.9635 | 0 | 0 | 0 | 176475.5115 | 3.5098 | /sqft |  | 0.00045741 | 0.036173
Assumptions:
1. For contaminated areas, plaster, gypsum, brick and concrete block will be removed and disposed of as contaminated.
2. For contaminated areas, concrete will be scabbled.
3. Productivity factors are included in the rates, unless otherwise specified.
4. Ash pit removal includes productivity factor of 1.86 to account for respirator use, pc's and alara.
|  | 2.12.1 | Decontaminate Fuel Fab Area |  |  |  | A | 176.64 | 1 | 176.64 | 529.92 | 46 | [5 empty] | 30880.0282 | 3507.3467 |  |  |  |  | 34387.3748
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Decon concrete surfaces |  |  |  | 4416 | 46 | 0% | 46 | 0.47917 | 0.04 | crew hr/sq. ft. | 176.64 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 46 | 0.47917 |  |  | 176.64
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Contaminated |  | 46 | 0.47917 | 670.8333 | 383.3333 | 2453.18 | 3507.3467
|  | 2.12.2 | Decontaminate Spent Fuel Pool |  |  |  | A | 27.2 | 1 | 27.2 | 81.6 | 28.3333 | [5 empty] | 4755.0768 | 2160.3222 |  |  |  |  | 6915.399
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Decon concrete surfaces |  |  |  | 680 | 28.3333 | 0% | 28.3333 | 0.29514 | 0.04 | crew hr/sq. ft. | 27.2 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 28.3333 | 0.29514 |  |  | 27.2
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Contaminated |  | 28.3333 | 0.29514 | 413.1944 | 236.1111 | 1511.0167 | 2160.3222
|  | 2.12.3 | Decontaminate High Bay Area |  |  |  | A | 241.3671 | 1 | 241.3671 | 724.1013 | 767.6667 | [5 empty] | 42195.5526 | 58532.0244 |  |  |  |  | 100727.577
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Remove ash pit block |  |  |  |  | 409 | 0% | 409 | 4.2604 | 0.057143 | crew hr/cu. ft. | 23.3714 | Use 2009 Means pg 28, 02 41 19.16 1450, 70 c. f. per day. Will assume 2 x that rate using excavator.
|  |  |  | Remove ash pit concrete |  |  |  |  | 148 | 0% | 148 | 1.5417 | 0.057143 | crew hr/cu. ft. | 15.7557 | Use 2009 Means pg 28, 02 41 19.16 1450, 70 c. f. per day. Will assume 2 x that rate using excavator.
|  |  |  | Decon concrete surfaces |  |  |  | 5056 | 210.6667 | 0% | 210.6667 | 2.1944 | 0.04 | crew hr/sq. ft. | 202.24 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 767.6667 | 7.9965 |  |  | 241.3671
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Contaminated |  | 767.6667 | 7.9965 | 11195.1389 | 6397.2222 | 40939.6633 | 58532.0244
|  | 2.12.4 | Decontaminate Service Level |  |  |  | A | 46.94 | 1 | 46.94 | 140.82 | 164 | 0.45833 |  |  |  |  | 8206.0039 | 12504.4533 | 27.2708 |  |  |  | 20737.728
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Hazardous | Hazardous paint, lbs |  |  | 45.8333 | 44 | 0.45833 | 0% | 0.45833 | 0.057292 | 0.04 | crew hr/sq. ft. | 1.76 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
|  |  | Contaminated | Remove stairs |  |  |  | 243 | 122 | 0% | 122 | 1.2708 | 0.02 | crew hr/sq. ft. | 4.86 | UCF 3 - clean grating
|  |  | Contaminated | Decon concrete surfaces |  |  |  | 1008 | 42 | 0% | 42 | 0.4375 | 0.04 | crew hr/sq. ft. | 40.32 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 164.4583 | 1.7656 |  |  | 46.94
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Contaminated |  | 164 | 1.7083 | 2391.6667 | 1366.6667 | 8746.12 | 12504.4533
|  |  |  | Hazardous |  | 0.45833 | 0.057292 | 3.724 | 0.63021 | 22.9167 | 27.2708
|  | 2.12.5 | Decontaminate A165 - Loading Dock Area |  |  |  | A | 18 | 1 | 18 | 54 | 4.6875 | [5 empty] | 3146.742 | 357.4062 |  |  |  |  | 3504.1483
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Decon concrete surfaces |  |  |  | 450 | 4.6875 | 0% | 4.6875 | 0.048828 | 0.04 | crew hr/sq. ft. | 18 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 4.6875 | 0.048828 |  |  | 18
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Contaminated |  | 4.6875 | 0.048828 | 68.3594 | 39.0625 | 249.9844 | 357.4062
|  | 2.12.6 | Decontaminate Main Level |  |  |  | A | 37.44 | 1 | 37.44 | 112.32 | 0.67708 | 9.0729 |  |  |  |  | 6545.2234 | 51.6253 | 539.8385 |  |  |  | 7136.6872
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Hazardous | Hazardous paint, lbs |  |  | 907.2917 | 871 | 9.0729 | 0% | 9.0729 | 1.1341 | 0.04 | crew hr/sq. ft. | 34.84 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
|  |  | Contaminated | Decon concrete surfaces |  |  |  | 65 | 0.67708 | 0% | 0.67708 | 0.007053 | 0.04 | crew hr/sq. ft. | 2.6 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 9.75 | 1.1412 |  |  | 37.44
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Contaminated |  | 0.67708 | 0.007053 | 9.8741 | 5.6424 | 36.1089 | 51.6253
|  |  |  | Hazardous |  | 9.0729 | 1.1341 | 73.7174 | 12.4753 | 453.6458 | 539.8385
|  | 2.12.7 | Decontaminate 310 Annex |  |  |  | A | 2.6 | 1 | 2.6 | 7.8 | 2.7083 | [5 empty] | 454.5294 | 206.5014 |  |  |  |  | 661.0308
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Decon concrete surfaces |  |  |  | 65 | 2.7083 | 0% | 2.7083 | 0.028212 | 0.04 | crew hr/sq. ft. | 2.6 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 2.7083 | 0.028212 |  |  | 2.6
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Contaminated |  | 2.7083 | 0.028212 | 39.4965 | 22.5694 | 144.4354 | 206.5014
|  | 2.12.8 | Decontaminate Balcony |  |  |  | A | 12.64 | 1 | 12.64 | 37.92 |  | 3.2917 |  |  |  |  | 2209.7122 |  | 195.8542 |  |  |  | 2405.5663
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Hazardous | Hazardous paint, lbs |  |  | 329.1667 | 316 | 3.2917 | 0% | 3.2917 | 0.41146 | 0.04 | crew hr/sq. ft. | 12.64 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 3.2917 | 0.41146 |  |  | 12.64
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Hazardous |  | 3.2917 | 0.41146 | 26.7448 | 4.526 | 164.5833 | 195.8542
| 2.13 | Remove contaminated soil and buried pipe |  |  |  |  | A | 124.048 | 1 | 124.048 | 372.144 | 57769.68 |  |  |  | 141.108 |  | 21685.9473 | 4404745.5344 |  |  |  | 439.8737 | 4426871.3554
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated Soil | Remove contaminated soil |  |  |  |  | 57000 | 0% | 57000 | 593.75 | 0.01 | crew hr/cu. yd. | 21.1111 | UCF 12 - excavate below grade structures | [8 empty] | 0.25899 | /cuft
|  |  | Clean | Excavate buried pipe - assume 4' wide & 4' deep |  |  | 132 |  |  | 0% | 0 | 0 | 0.01 | crew hr/cu. yd. | 0.78222 | UCF 12 - excavate below grade structures
|  |  | Clean | Buried pipe, clean |  |  | 132 |  | 141.108 | 0% | 141.108 | 0.17421 | 0.088667 | crew hrs/ft | 11.704 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, use 2/3 of duration) | [8 empty] | 66.1463 | /ft | 1.069
|  |  | Contaminated | Excavate buried pipe - assume 4' wide & 4' deep |  |  | 720 |  |  | 0% | 0 | 0 | 0.01 | crew hr/cu. yd. | 4.2667 | UCF 12 - excavate below grade structures
|  |  | Contaminated | Buried pipe, contam. |  |  | 720 |  | 769.68 | 0% | 769.68 | 8.0175 | 0.1197 | crew hrs/ft | 86.184 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara) | [8 empty] | 87.8472 | /ft |  |  | 1.069
[11 empty] | 57910.788 | 601.9417 |  |  | 124.048
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 141.108 | 0.17421 | 0 | 87.1037 | 352.77 | 439.8737
|  |  |  | Contaminated Soil |  | 57000 | 593.75 | 831250 | 475000 | 3039810 | 4346060 | Packaged in B-25 boxes
|  |  |  | Contaminated |  | 769.68 | 8.0175 | 11224.5 | 6414 | 41047.0344 | 58685.5344 | Packaged in B-25 boxes
| 2.14 | Final Survey of Structure |  |  |  |  | A | 80 | 1.595 | 127.6 | 382.8 | [6 empty] | 22306.9044 | [5 empty] | 22306.9044 | 0.79571 | /sqft
|  |  |  | Estimated Duration | 80 | hrs
| 2.15 | Demolition Readiness Review - (Contractor staff cost included in Undistributed Costs) | [5 empty] | 80 | 1 | 80
| 2.16 | Remove building | [5 empty] | 1154.3001 |  | 1154.3001 | 3462.9004 | 0 | 0 | 0 | 0 | 169875.2096 | 180.4 | 201793.5928 | 0 | 0 | 0 | 0 | 529549.2646 | 731523.2574 | 7.1982 | /sqft | 6.0597
|  | 2.16.1 | Remove Interior walls |  |  |  |  | 861.0933 |  | 861.0933 | 2583.2798 | 0 | 0 | 0 | 0 | 119400.4256 | 180.4 | 150535.4661 | 0 | 0 | 0 | 0 | 372205.0305 | 522920.8966
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
3. For building removal use 2009 Means pg 28, 02 41 19.16 1450, 70 c. f. per day. This rate assumes a crew of 4 laborers and hand tools. This rate is assumed to be doubled for demolition using an excavator, not hand tools.
|  | 2.16.1.1 | Remove Fan Loft |  |  |  | A | 5.8726 | 1 | 5.8726 | 17.6178 |  |  |  |  | 646 |  | 1026.6408 |  |  |  |  | 2013.7654 | 3040.4062
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Remove stairs |  |  |  | 120 | 120 | 50% | 60 | 0.074074 | 0.02 | crew hr/sq. ft. | 2.4 | UCF 3 - clean grating
|  |  |  | Remove plaster |  |  |  |  | 0 | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove gypsum |  |  |  |  | 0 | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove brick |  |  |  |  | 148 | 0% | 148 | 0.18272 | 50 | cu. yd./day | 0.87704 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete block |  |  |  |  | 218 | 0% | 218 | 0.26914 | 50 | cu. yd./day | 1.2919 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete |  |  |  |  | 220 | 0% | 220 | 0.2716 | 50 | cu. yd./day | 1.3037 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 646 | 0.79753 |  |  | 5.8726
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 646 | 0.79753 | 0 | 398.7654 | 1615 | 2013.7654
|  | 2.16.1.2 | Remove Clerestory |  |  |  | A | 2.9926 | 1 | 2.9926 | 8.9778 |  |  |  |  | 160 |  | 523.162 |  |  |  |  | 498.7654 | 1021.9275
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Remove stairs |  |  |  | 120 | 120 | 50% | 60 | 0.074074 | 0.02 | crew hr/sq. ft. | 2.4 | UCF 3 - clean grating
|  |  |  | Remove plaster | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove gypsum | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove brick | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete block |  |  |  |  | 100 | 0% | 100 | 0.12346 | 50 | cu. yd./day | 0.59259 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete |  |  |  |  | 0 | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 160 | 0.19753 |  |  | 2.9926
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 160 | 0.19753 | 0 | 98.7654 | 400 | 498.7654
|  | 2.16.1.3 | Remove Balcony |  |  |  | A | 38.7274 | 1 | 38.7274 | 116.1822 |  |  |  |  | 2237.5 |  | 6770.2866 |  |  |  |  | 6974.9228 | 13745.2095
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Remove stairs |  |  |  | 1390 | 787 | 50% | 393.5 | 0.4858 | 0.02 | crew hr/sq. ft. | 27.8 | UCF 3 - clean grating
|  |  |  | Remove plaster |  |  |  |  | 0 | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove gypsum |  |  |  |  | 845 | 0% | 845 | 1.0432 | 50 | cu. yd./day | 5.0074 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove brick |  |  |  |  | 0 | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete block |  |  |  |  | 196 | 0% | 196 | 0.24198 | 50 | cu. yd./day | 1.1615 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete |  |  |  |  | 803 | 0% | 803 | 0.99136 | 50 | cu. yd./day | 4.7585 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 2237.5 | 2.7623 |  |  | 38.7274
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 2237.5 | 2.7623 | 0 | 1381.1728 | 5593.75 | 6974.9228
|  | 2.16.1.4 | Remove Main Level |  |  |  | A | 40.1471 | 1 | 40.1471 | 120.4413 |  |  |  |  | 6590.8229 |  | 7018.4757 |  |  |  |  | 20545.4665 | 27563.9422
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Remove stairs |  |  |  | 64 | 64 | 50% | 32 | 0.039506 | 0.02 | crew hr/sq. ft. | 1.28 | UCF 3 - clean grating
|  |  |  | Remove plaster |  |  |  |  | 4819 | 0% | 4819 | 5.9494 | 50 | cu. yd./day | 28.557 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove gypsum | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove brick | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete block | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete |  |  |  |  | 1739.8229 | 0% | 1739.8229 | 2.1479 | 50 | cu. yd./day | 10.3101 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 6590.8229 | 8.1368 |  |  | 40.1471
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 6590.8229 | 8.1368 | 0 | 4068.4092 | 16477.0573 | 20545.4665
|  | 2.16.1.5 | Remove Spent Fuel Pool |  |  |  | A | 110.0949 | 1 | 110.0949 | 330.2846 |  |  |  |  | 8210.3361 |  | 19246.6733 |  |  |  |  | 25593.9488 | 44840.6221
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Tons | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Remove insulation |  |  |  | 4418 | 442 | 0% | 442 | 0.54568 | 0.01 | crew hr/sq. ft. | 44.18 | estimated
|  |  |  | Remove stairs |  |  |  | 345 | 345 | 50% | 172.5 | 0.21296 | 0.02 | crew hr/sq. ft. | 6.9 | UCF 3 - clean grating
|  |  |  | Remove structural steel |  | 20.7195 |  |  | 84.5694 | 0% | 84.5694 | 0.10441 | 0.7 | crew hr/ton | 14.5036 | UCF 8 - structural steel
|  |  |  | Remove gypsum |  |  |  |  | 1428 | 0% | 1428 | 1.763 | 50 | cu. yd./day | 8.4622 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove brick |  |  |  |  | 1069 | 0% | 1069 | 1.3198 | 50 | cu. yd./day | 6.3348 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete block |  |  |  |  | 697 | 0% | 697 | 0.86049 | 50 | cu. yd./day | 4.1304 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete |  |  |  |  | 4317.2667 | 0% | 4317.2667 | 5.33 | 50 | cu. yd./day | 25.5838 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 8210.3361 | 10.1362 |  |  | 110.0949
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 8210.3361 | 10.1362 | 0 | 5068.1087 | 20525.8401 | 25593.9488
|  | 2.16.1.6 | Remove Fuel Fab Area |  |  |  | A | 12.3319 | 1 | 12.3319 | 36.9956 |  |  |  |  | 2081 |  | 2155.842 |  |  |  |  | 6487.0679 | 8642.9099
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Remove plaster | [5 empty] | 0% | 0 | 0 | 0.25 | crew hr/cu. yd. | 0 | UCF 6 - Clean Block Wall
|  |  |  | Remove gypsum | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove brick | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete block |  |  |  |  | 1906 | 0% | 1906 | 2.3531 | 50 | cu. yd./day | 11.2948 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete |  |  |  |  | 175 | 0% | 175 | 0.21605 | 50 | cu. yd./day | 1.037 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 2081 | 2.5691 |  |  | 12.3319
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 2081 | 2.5691 | 0 | 1284.5679 | 5202.5 | 6487.0679
|  | 2.16.1.7 | Remove High Bay Area |  |  |  | A | 53.0657 | 1 | 53.0657 | 159.197 |  |  |  |  | 8926.3333 |  | 9276.8889 |  |  |  |  | 27825.9156 | 37102.8046
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Remove stairs |  |  |  | 12 | 12 | 0% | 12 | 0.014815 | 0.02 | crew hr/sq. ft. | 0.24 | UCF 3 - clean grating
|  |  |  | Remove plaster | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove gypsum |  |  |  |  | 1570 | 0% | 1570 | 1.9383 | 50 | cu. yd./day | 9.3037 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove brick | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete block |  |  |  |  | 1641 | 0% | 1641 | 2.0259 | 50 | cu. yd./day | 9.7244 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete |  |  |  |  | 5703.3333 | 0% | 5703.3333 | 7.0412 | 50 | cu. yd./day | 33.7975 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 8926.3333 | 11.0202 |  |  | 53.0657
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 8926.3333 | 11.0202 | 0 | 5510.0823 | 22315.8333 | 27825.9156
|  | 2.16.1.8 | Remove Service Level - Includes Personnel & Pipe Tunnel |  |  |  | A | 539.3417 | 1 | 539.3417 | 1618.0251 |  |  |  |  | 86307.1417 | 180.4 | 94287.1751 |  |  |  |  | 269043.8675 | 363511.4427
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Remove stairs |  |  |  | 1537.6 | 655.6 | 0% | 655.6 | 0.80938 | 0.02 | crew hr/sq. ft. | 30.752 | UCF 3 - clean grating
|  |  |  | Remove plaster |  |  |  |  | 1218 | 0% | 1218 | 1.5037 | 50 | cu. yd./day | 7.2178 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove gypsum |  |  |  |  | 240 | 0% | 240 | 0.2963 | 50 | cu. yd./day | 1.4222 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove brick |  |  |  |  | 3559 | 0% | 3559 | 4.3938 | 50 | cu. yd./day | 21.0904 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete block |  |  |  |  | 221.5417 | 0% | 221.5417 | 0.27351 | 50 | cu. yd./day | 1.3128 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Seal tunnels at building 306 (Reinforced block 12" thick) |  |  |  | 41 |  | 0% | 0 |  | 320 | sq. ft./day | 1.025 | 2009 Means 04 22 10.34 5650
|  |  |  | Remove concrete |  |  |  |  | 80413 | 0% | 80413 | 99.2753 | 50 | cu. yd./day | 476.5215 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 86307.1417 | 106.552 |  |  | 539.3417
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 86307.1417 | 106.552 | 0 | 53276.0134 | 215767.8542 | 269043.8675
[6 empty] | Area, sq. ft. | Material, $/sq ft. | Material cost, $
|  |  |  | Construct block wall |  | 41 | 4.4 | 180.4
|  | 2.16.1.9 | Remove A165 - Loading Dock Area |  |  |  | A | 3.5081 | 1 | 3.5081 | 10.5244 |  |  |  |  | 592 |  | 613.291 |  |  |  |  | 1845.4321 | 2458.723
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Remove plaster | [5 empty] | 0% | 0 | 0 | 0.25 | crew hr/cu. yd. | 0 | UCF 6 - Clean Block Wall
|  |  |  | Remove gypsum | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove brick | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete block |  |  |  |  | 592 | 0% | 592 | 0.73086 | 50 | cu. yd./day | 3.5081 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 592 | 0.73086 |  |  | 3.5081
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 592 | 0.73086 | 0 | 365.4321 | 1480 | 1845.4321
|  | 2.16.1.10 | Remove 310A |  |  |  | A | 55.0114 | 1 | 55.0114 | 165.0341 |  |  |  |  | 3649.2917 |  | 9617.0306 |  |  |  |  | 11375.8783 | 20992.9089
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Remove plaster |  |  |  |  | 0 | 0% | 0 | 0 | 0.25 | crew hr/cu. yd. | 0 | UCF 6 - Clean Block Wall
|  |  |  | Remove insulation |  |  |  | 3466 | 348 | 0% | 348 | 0.42963 | 0.01 | crew hr/sq. ft. | 34.66 | estimated
|  |  |  | Remove stairs |  |  |  | 56 | 56 | 0% | 56 | 0.069136 | 0.02 | crew hr/sq. ft. | 1.12 | UCF 3 - clean grating
|  |  |  | Remove gypsum |  |  |  |  | 2055 | 0% | 2055 | 2.537 | 50 | cu. yd./day | 12.1778 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove brick |  |  |  |  | 0 | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete block |  |  |  |  | 1051 | 0% | 1051 | 1.2975 | 50 | cu. yd./day | 6.2281 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete |  |  |  |  | 139.2917 | 0% | 139.2917 | 0.17197 | 50 | cu. yd./day | 0.82543 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 3649.2917 | 4.5053 |  |  | 55.0114
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 3649.2917 | 4.5053 | 0 | 2252.6492 | 9123.2292 | 11375.8783
|  | 2.16.2 | Remove buildings 310 and 310A |  |  |  | A | 293.2068 | 1 | 293.2068 | 879.6205 |  |  |  |  | 50474.784 |  | 51258.1267 |  |  |  |  | 157344.2341 | 208602.3608
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Width | Depth | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Built up Roof |  |  |  | 15274 | 5345.9 | 0% | 5345.9 | 6.5999 | 1600 | sq ft/8 hr day | 26.7295 | 2006 RS Means 07060-110-3000
|  |  |  | Remove brick | [5 empty] | 0% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete block on roof |  |  |  |  | 1527.4 | 0% | 1527.4 | 1.8857 | 50 | cu. yd./day | 9.0513 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete roof |  |  |  |  | 16766 | 0% | 16766 | 20.6988 | 50 | cu. yd./day | 99.3541 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove insulation |  |  |  | 6055 | 1211 | 0% | 1211 | 1.4951 | 0.01 | crew hr/sq. ft. | 60.55 | estimated
|  |  |  | Remove structural steel |  | 7.1715 |  |  |  | 0% | 7.1715 | 0.0088537 | 0.7 | crew hr/ton | 5.02 | UCF 8 - structural steel
|  |  |  | Remove brick |  |  |  |  | 16148 | 0% | 16148 | 19.9358 | 0.057143 | crew hr/cu. yd. | 34.1757 | Use 2009 Means pg 28, 02 41 19.16 1450, 70 c. f. per day. Will assume 2 x that rate using excavator.
|  |  |  | Remove transite panels |  |  |  | 80 | 24 | 0% | 24 | 0.02963 | 0.008 | crew hrs/sq. ft. | 0.64 | 2009 mean, p34, 02 82 13.43 8000
|  |  |  | Remove metal deck |  |  |  | 324 | 162 | 0% | 162 | 0.2 |  |  | 2 | estimated
|  |  |  | Remove wood deck |  |  |  | 128 | 55 | 0% | 55 | 0.067901 |  |  | 1 | estimated
|  |  |  | Remove concrete block |  |  |  |  | 5778 | 0% | 5778 | 7.1333 | 50 | cu. yd./day | 34.24 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  |  | Remove concrete |  |  |  |  | 3450.3125 | 0% | 3450.3125 | 4.2596 | 50 | cu. yd./day | 20.4463 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 50474.784 | 62.3145 |  |  | 293.2068
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 50474.784 | 62.3145 | 0 | 31157.2741 | 126186.96 | 157344.2341
| 2.17 | Final Site Survey Structure gone |  |  |  |  | A | 480 | 1 | 480 | 1440 | [6 empty] | 83913.12 | [5 empty] | 83913.12
Schedule
[7 empty] | Work hours |  | duration, days
|  | 2.17.1 | Prepare Final Status Survey Plan |  | 45 | days = | 360 | hrs | 5 | days - 40 days in parallel with 2.16
|  | 2.17.2 | Soil Sampling |  | 2 | days = | 16 | hrs | 0 | days- in parallel with 2.17.1
|  | 2.17.3 | Direct Survey |  | 3 | days = | 24 | hrs | 3 | days
|  | 2.17.4 | Sampling Analysis |  | 20 | days = | 0 | hrs | 20 | days
|  | 2.17.5 | Prepare Final Status Survey Report |  | 10 | days = | 80 | hrs | 7 | days - three days overlap with 2.17.4
[7 empty] | 480 |  | 35
| 2.18 | Orise Site Release Confirmation
|  | Duration equal 45 days; however, this activity will occur in parallel with 2.17. The schedule duration will be 45 - 40 days = | [6 empty] | 5 | days
| 2.19 | Backfill, grade, seed, and pave where applicable |  |  |  |  | A | 151.5581 | 1 | 151.5581 | 454.6744 |  |  |  |  | 72000 | 353427.2778 | 26495.2394 |  |  |  |  | 2000 | 381922.5172
Assumptions:
|  |  | 1. Grade and see area included. | [12 empty] | Grade and seed |  | 27405.3336 | [6 empty] | 0.38063 | /sqft
|  |  | 2. Productivity factors are included in the rates, unless otherwise specified. | [12 empty] | Backfill |  | 70984.2837 | [6 empty] | 0.20719 | /cuft
3. Paving will be performed by subcontractor.
4. Backfill excavated soil and below grade void.
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Width | Depth | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Grade |  |  |  | 72000 |  | 0% | 0 | 0 | 18000 | sq ft/8 hr day | 32 | 2009 RS Means 31 22 16.10 0100
|  |  |  | Seed |  |  |  | 72000 |  | 0% | 0 | 0 | 80100 | sq ft/8 hr day | 7.191 | 2009 RS Means 32 92 19.13 1000
|  |  |  | Backfill |  |  |  |  | 342600 | 0% | 342600 | 422.963 | 1000 | cu. yd./day | 101.5111 | 2009 RS Means 31 23 23.14 2000
|  |  |  | Pavement - binder course |  |  |  | 19550 |  | 0% | 0 | 0 | 25000 | sq ft/8 hr day | 6.256 | 2009 RS Means 32 12 16.14 0400
|  |  |  | Pavement - binder course |  |  |  | 19550 |  | 0% | 0 | 0 | 34000 | sq ft/8 hr day | 4.6 | 2009 RS Means 32 12 16.14 0900
[11 empty] | 342600 | 422.963 |  |  | 151.5581
|  |  |  | Waste |  | Area, sq. ft. | Material, $/SY | Equipment, $/SY | Volume, cu. Ft. | Cost, $/cu. yd. | Total, $
|  |  |  | Seed and equipment |  | 72000 | 0.18 | 0.07 |  |  | 2000 | 2009 RS Means 32 92 19.13 1000
|  |  |  | Pavement |  | 19550 | 1.49 |  |  |  | 29129.5 | 2009 RS Means 32 12 16.14 0400 + 0900
|  |  |  | Structural fill |  |  |  |  | 342600 | 25.4 | 322297.7778 | 2009 RS Means 31 05 16.10 0600 + 0900
353427.2778
| 2.2 | Final Project Report |  |  |  |  | A | 80 | 1 | 80 | 240 | [6 empty] | 13985.52 | [5 empty] | 13985.52
Schedule
[7 empty] | Work hours |  | duration, days
|  |  | Prepare Report |  | 10 | days = | 80 | hrs | 10
|  | Labor Category: |  | Decon Tech.
|  | Allowance/perdiem $/day |  | 75
|  | Days/wk paid |  | 7
|  | Work hours/wk |  | 50
|  | work hourly rate adjustment |  | 10.5
|  | Unadjusted rate |  | 43.43
|  | Adjusted to include 10 hrs OT |  | 47.773
|  | Labor Rate ($/hr): |  | 58.273
|  | Crew | 12 | 699.276 | 12

## BLDG 2 2010 (hidden)
|  | G Wing |  | 15352 | sqft
|  | H Wing |  | 47210 | sqft | [9 empty] | Mixed | Clean | Lead | Materials, |  |  | Hazardous |  | Mixed | Clean | Lead
|  | F Wing |  | 71860 | sqft |  |  | Uncorrected Duration |  | Adjusted |  | LSA Waste | Hazardous | Ballast | Waste | Waste | Waste | Consumables, |  | LSA Waste | Waste | >LSA Waste | Waste | Waste | Waste |  |  |  |  | Clean | Hazardous | LLW | Mixed
|  | Fallout shelter |  | 18264 | sqft |  | Crew | (No. of Hours) | Prod. Factor | Duration | Man-hours | Disp. Vol (cf) | Waste Vol (cf) | Volume (cf) | Volume (cf) | Volume (cf) | Volume (cf) | & Equipment | Labor Cost | Cost | Cost | Cost | Cost | Cost | Cost | Total Cost |  | Removal |  | Waste | Waste | Waste | Waste
[28 empty] | Unit Rate |  | Volume | Volume | Volume | Volume
| Grand Total Building 212 F, G, H wings and Fallout Shelter | [24 empty] | 45165635.3407
| Contingency = |  | 40% | [22 empty] | 12904467.2402
1 | Total Building 212 F, G, H wings and Fallout Shelter | [24 empty] | 32261168.1005
| ANL Oversight @ 24% | [22 empty] | 24% |  | 6244097.0517
ANL Tax | General and Administration | [22 empty] | 2.9% |  | 156127.5992
ANL Tax | IGPP/IGPE | [22 empty] | 2.7% |  | 141538.6354
ANL Tax | Service Center | [22 empty] | 18.5% |  | 3788288.1295 | On total
ANL Tax | Material and Subcontracts Tax | [22 empty] | 7.1% |  | 1453883.5524 | On total
1 | Building 212 F, G, H wings and Fallout Shelter | [9 empty] | 156619.4286 | 34784.4464 | 19591.0394 | 160.2 | 0 | 669956.4449 | 346.82 | 4114974.6218 | 11095979.1143 | 1855054.5274 | 163262.6496 | 0 | 0 | 3122692.8492 | 125269.37 | 20477233.1323
UNDISTRIBUTED COSTS | [10 empty] | 151131.4286 | [6 empty] | 3365691.0996 | 10941979.1143 | 0 | 0 | 0 | 0 | 0 |  | 14307670.2139
|  | Project duration = |  |  | 1133 | days/7days/wk = | 161.8571 | See Project Schedule - Starts with Site Mobilization and ends with Site Demobilization
[5 empty] | 809.2857 | working days
|  | Labor cost = |  | 4307399.2 | (Used to determine small tool costs and HP Supplies)
| 1.1 | Project Management | [8 empty] | 77691.4286 | [7 empty] | 5634052.9143 | [6 empty] | 5634052.9143
|  | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
|  | Project Manager |  |  | 1 | 130 | 809.2857 | 100% | 841657.1429 | 6474.2857
|  | Project Safety Manager |  |  | 1 | 100 | 809.2857 | 100% | 647428.5714 | 6474.2857
|  | Project Specialist |  |  | 1 | 85 | 809.2857 | 100% | 550314.2857 | 6474.2857
|  | Health Physicist |  |  | 1 | 120 | 809.2857 | 100% | 776914.2857 | 6474.2857
|  | Chief HP Tech |  |  | 1 | 57.77 | 809.2857 | 100% | 374019.4857 | 6474.2857
|  | Building Maintenance |  |  | 1 | 51.38 | 809.2857 | 100% | 332648.8 | 6474.2857
|  | Secretary |  |  | 1 | 31.79 | 809.2857 | 100% | 205817.5429 | 6474.2857
|  | Project Control Specialist |  |  | 1 | 98 | 809.2857 | 100% | 634480 | 6474.2857
|  | HP Tech |  |  | 4 | 49.07 | 809.2857 | 100% | 1270772.8 | 25897.1429
[5 empty] | 12 |  |  |  | 5634052.9143 | 77691.4286
| 1.2 | Project Management Per Diem | [16 empty] | 1154527 | [6 empty] | 1154527
[6 empty] | Per Diem | Number of
|  | Staff |  |  | Number | Rate, $/day | Days | Total
|  | Project Manager |  |  | 1 | 161 | 1133 | 182413
|  | Project Safety Manager |  |  | 1 | 161 | 1133 | 182413
|  | Project Specialist |  |  | 1 | 161 | 1133 | 182413
|  | Health Physicist |  |  | 1 | 161 | 1133 | 182413
|  | Chief HP Tech |  |  | 1 | 75 | 1133 | 84975
|  | HP Tech |  |  | 4 | 75 | 1133 | 339900
[5 empty] | 9 |  |  | 1154527
| 1.3 | Crew cost - 4 crews from mobilization through final survey | [8 empty] | 59451.4286 | [7 empty] | 3362275.5429 | [6 empty] | 3362275.5429
|  | Duration | 867 | days/7days/wk = | 123.8571 | 619.2857 | working days | See Project Schedule - Starts with Site Mobilization and ends with Remove Building
|  | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
|  | Decon Techs |  |  | 12 | 56.555 | 619.2857 | 100% | 3362275.5429 | 59451.4286
[5 empty] | 12 |  |  |  | 3362275.5429 | 59451.4286
| 1.4 | Crew cost - 4 crews from final survey through site demobilization | [8 empty] | 13988.5714 | [7 empty] | 791123.6571 | [6 empty] | 791123.6571
|  | Duration | 204 | days/7days/wk = | 29.1429 | 145.7143 | working days | See Project Schedule - Starts with Remove Building and ends with Site Demobilization
|  | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
|  | Decon Techs |  |  | 12 | 56.555 | 145.7143 | 100% | 791123.6571 | 13988.5714
[5 empty] | 12 |  |  |  | 791123.6571 | 13988.5714
| 1.5 | Equipment & Materials | [15 empty] | 3365691.0996 | [7 empty] | 3365691.0996
|  | Equipment |  |  | Quantity | Rate | Cost
|  | HEPA filter systems |  |  | 2 | 3598.14 | 7196.28
|  | Replacement filters |  |  | 24 | 581.07 | 13945.68
|  | Respirator |  |  | 30 | 259 | 7770
|  | Rad/Vac wet-dry high eff. vacuum |  |  | 4 | 3879 | 15516
|  | Rad/Vac wet-dry high eff. vacuum filters |  |  | 10 | 412 | 4120
|  | Reciprocating Saws |  |  | 6 | 1252.26 | 7513.56
|  | Pneumatic chipping hammers |  |  | 2 | 1606.71 | 3213.42
|  | Chipping hammer blades |  |  | 20 | 27.42 | 548.4
|  | Purchase an air compressor: |  |  | 4 | 1723.44 | 6893.76
|  | Jackhammer |  |  | 2 | 1417.11 | 2834.22
|  | Jackhammer Chisels |  |  | 20 | 24.35 | 487
|  | Safety glasses |  |  | 150 | 8.6 | 1290
|  | Fall protection - harness |  |  | 12 | 208 | 2496
|  | Fall protection - lanyard |  |  | 12 | 367 | 4404
|  | Hardhats |  |  | 40 | 35.5 | 1420
|  | Hard hat hearing protection |  |  | 40 | 37.6 | 1504
|  | Trailer rental |  |  | 2 | 416 | 28292.1914
|  | Phone and computer hook-up |  |  | 1 | 250 | 8501.2594
|  | Industrial hygiene instrumentation, calibration and hygienists - 1% of total activity $. |  |  |  |  | 103229.6212
|  | Tractor loader, wheeled |  |  | 1 | 7160.5905 | 235732.5051
|  | Wheeled Skid steer with conc. Hammer |  |  | 2 | 4421.3693 | 48808.8956
|  | Excavator |  |  | 2 | 28738.389 | 317252.1751
|  | Shot Blaster |  |  | 2 | 3522.318 | 25922.6557
|  | Floor Shaver |  |  | 2 | 8000 | 400569.4886
|  | Wall Shaver |  |  | 2 | 15000 | 751067.791
|  | Core Drill & Bits |  |  | 1 | 10000 | 10000
|  | Man lift |  |  | 2 | 4727.44 | 210925.3155
|  | Crane rental for building removal |  |  | 2 | 15600 | 151711.7512
2373165.9699
|  | Consumables |  | Quantity |  | Duration |  | # workers | quantity | Unit Qty | Unit Cost | Cost
|  | Coveralls |  | 2 | /man/day | 809.2857 | days | 16 | 25897.1429 | 1 | 8.7 | 225305.1429 | 4 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Hoods |  | 0.5 | /man/day | 809.2857 | days | 16 | 6474.2857 | 1 | 0.93333 | 6042.6667 | 4 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Shoe covers |  | 4 | /man/day | 809.2857 | days | 16 | 51794.2857 | 1 | 0.37 | 19163.8857 | 4 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Latex gloves |  | 4 | /man/day | 809.2857 | days | 16 | 51794.2857 | 1 | 2 | 103588.5714 | 4 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Rubber overshoes |  | 0.01 | /man/day | 809.2857 | days | 16 | 129.4857 | 1 | 3 | 388.4571 | 4 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Gloves |  | 0.5 | /man/day | 809.2857 | days | 16 | 6474.2857 | 1 | 1.63 | 10553.0857 | 4 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Dosimeters |  | 1 | /man/year | 3.1126 | year | 24 | 74.7033 | 1 | 197.125 | 14725.8874
|  | TLDs |  | 1 | /man/mo | 37.3804 | month | 24 | 897.1297 | 1 | 3 | 2691.389
|  | Bioassays |  | 2 | /man/year | 3.1126 | year | 24 | 149.4066 | 1 | 25 | 3735.1648
|  | (Bioassays for aver. crew & management) | [9 empty] | 386194.2507
|  | Small Tools - 2% of total labor costs = |  |  |  | 4307399.2 | labor costs x | 2% | = | 86147.984
|  | HP Equipment Replacement - 5% of total labor |  |  |  | 4307399.2 | labor costs x | 5% | = | 215369.96
|  | DGC OH &P on equipment and materials |  |  |  | 3810161.6869 |  | 8% | = | 304812.9349
ACTIVITIES | [7 empty] | 19612.076 |  | 21301.1463 | 5488 | 34784.4464 | 19591.0394 | 160.2 | 0 | 669956.4449 | 346.82 | 749283.5222 | 154000 | 1855054.5274 | 163262.6496 | 0 | 0 | 3122692.8492 | 125269.37 | 6169562.9184
| 1.6 | Project Engineering | [5 empty] | 640 |  | 704 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112640 | 0 | 0 | 0 | 0 | 0 | 0 | 112640
|  | 1.6.1 | Procedure Development and Review - Offsite |  |  |  |  | 320 | 1.1 | 352 | 616 | [7 empty] | 56320 | [6 empty] | 56320
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 85 | 240 | 1.1 | 44880 | 528
|  |  | Project Manager |  |  | 1 | 130 | 80 | 1.1 | 11440 | 88
[6 empty] | 3 |  | 320 |  | 56320 | 616
|  | 1.6.2 | Preparation of QA and Safety Documents - Offsite |  |  |  |  | 320 | 1.1 | 352 | 616 | [7 empty] | 56320 | [6 empty] | 56320
|  |  | Staff |  |  | Number | Rate | Duration | PLF |  | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 85 | 240 | 1.1 |  | 44880 | 528
|  |  | Project Manager |  |  | 1 | 130 | 80 | 1.1 |  | 11440 | 88
[6 empty] | 3 |  | 320 |  |  | 56320 | 616
| 1.7 | Site Mobilization and General Employee Training (GET) | [5 empty] | 104 | 1 | 104 | 1896 | [6 empty] | 40800 | 0 | [6 empty] | 40800
|  | 1.7.1 | Site Mobilization |  |  |  |  | 48 |  | 48 | 1152 | [6 empty] | 9600 | 0 | [6 empty] | 9600
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Project Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Safety Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Health Physicist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Chief HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Building Maintenance |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Secretary |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Control Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 4 | HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 12 | Decon Techs |  | 0 | 0 | With Undistributed Costs
|  |  | 24 |  |  |  | 0
|  |  | Travel to site |  |  | 8 | hr
|  |  | Receipt of material and equipment |  |  | 16 | hr
|  |  | Staging of equipment |  |  | 8 | hr
|  |  | Set up office and amenities |  |  | 12 | hr
|  |  | Familiarize staff with facility |  |  | 4 | hr
[6 empty] | 48 | hr
|  |  | Labor Cost = |  | 48 | x | 0 | 0
|  |  | Travel cost = |  | 24 | x | 400 | 9600
|  | 1.7.2 | General Employee Training (All proj. manag. & 4 crews of 4) (1 HP Tech & 3 Decon Techs) |  |  |  |  | 40 | 1 | 40 | 360 | [6 empty] | 31200 | 0 | [6 empty] | 31200
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Project Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Safety Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Health Physicist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Chief HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Building Maintenance |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Secretary |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Control Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 4 | HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 12 | Decon Techs |  | 0 | 0 | With Undistributed Costs
|  |  | 24 |  |  |  | 0
[8 empty] | Number | Test | Labor | Total
[7 empty] | Unit Cost | Required | Cost | Costs | Cost
|  |  | In-Vivo |  |  |  | 600 | 24 | 14400 |  | 14400
|  |  | In-Vitro |  |  |  | 350 | 24 | 8400 |  | 8400
|  |  | Physical @ |  | 4 | hour and | 150 | 24 | 3600 | 0 | 3600
|  |  | Resp. Tests |  | 1 | hour and | 50 | 24 | 1200 | 0 | 1200
|  |  | Resp Fit Tests |  | 1 | hour and | 25 | 24 | 600 | 0 | 600
|  |  | Blood Tests |  | 1 | hour and | 125 | 24 | 3000 | 0 | 3000
|  |  | OSHA recertification |  | 8 | hour |  |  |  | 0 | 0
[5 empty] | 15 |  |  |  | 31200 | 0 | 31200
|  | 1.7.3 | Site Specific Training (All proj. manag. & 4 crews of 4) (1 HP Tech & 3 Decon Techs) |  |  |  |  | 16 | 1 | 16 | 384 | [7 empty] | 0 | [6 empty] | 0
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Project Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Safety Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Health Physicist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Chief HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Building Maintenance |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Secretary |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Control Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 4 | HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 12 | Decon Techs |  | 0 | 0 | With Undistributed Costs
|  |  | 24 |  |  |  | 0
| 1.8 | Decontamination Readiness Review (Labor costs included in Undistributed costs) |  |  |  |  | B | 80 | 1 | 80 | 0 | [7 empty] | 0 | [6 empty] | 0
| 1.9 | Site Preparation (Labor costs included in Undistributed costs) |  |  |  |  | B | 288 | 1.21 | 343.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000
|  | 1.9.1 | Initial Site Survey |  |  |  | B | 16 | 1.21 | 19.36 | 0 | [7 empty] | 0 | [6 empty] | 0
|  |  |  | Estimated Duration | 16 | hrs
|  | 1.9.2 | Setup work areas |  |  |  |  | 72 |  | 81.84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000 | 0 | [6 empty] | 1000
|  | 1.9.2.1 | Setup boundaries, install HEPA filters & seal off ventilation openings |  |  |  | B | 24 | 1.21 | 29.04 | 0 | 0 | 0 |  |  |  |  | 1000 | 0 | [6 empty] | 1000
(estimated)
|  | 1.9.2.2 | Establish staging area |  |  |  | B | 8 | 1.1 | 8.8 | 0 | 0 | 0 | [5 empty] | 0 | [6 empty] | 0
|  | 1.9.2.3 | Setup Rad & Non-Rad Segregation/Packaging Stations |  |  |  | B | 40 | 1.1 | 44 | 0 | 0 | 0 | [5 empty] | 0 | [6 empty] | 0
|  | 1.9.3 | Isolate FGH wings from Bldg 212 |  |  |  |  | 200 |  | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
|  | 1.9.3.1 | Electrical |  |  |  | B | 40 | 1.21 | 48.4 | 0 |  |  |  | 0 |  |  | 5000 | 0 | [6 empty] | 5000
(new material allowance)
|  | 1.9.3.2 | Ventilation |  |  |  | B | 40 | 1.21 | 48.4 | 0 |  |  |  | 0 |  |  | 5000 | 0 | [6 empty] | 5000
|  | 1.9.3.3 | Piping |  |  |  | B | 80 | 1.21 | 96.8 | 0 |  |  |  | 0 |  |  | 5000 | 0 | [6 empty] | 5000
|  | 1.9.3.4 | Seal accesses to M wing |  |  |  | B | 40 | 1.21 | 48.4 | 0 |  |  |  | 0 |  |  | 5000 | 0 | [6 empty] | 5000
| 1.1 | Equipment Removal/Decontamination (Labor costs included in Undistributed costs) | [5 empty] | 14674.9704 |  | 16300.8406 | 0 | 34616.4464 | 0 | 160.2 | 0 | 265244.7849 | 346.82 | 0 | 0 | 1846095.0874 | 1922.4 | 0 | 0 | 1276650.7546 | 125269.37 | 3124668.242
Assumptions:
1. Productivity factors are included in the rates, unless otherwise specified.
2. Scabbled concrete volume will be increased 30% to account for packaging inefficiencies.
|  | 1.10.1 | G Wing |  |  |  |  | 3946.4215 |  | 4632.1536 | 0 | 595.795 | 0 | 60 | 0 | 130695.459 | 344.62 | 0 | 0 | 31773.7473 | 720 | 0 | 0 | 603458.0453 | 125269.37 | 761221.1626
Remove systems and components
|  |  |  | Clean | [5 empty] | 2144.544 | [17 empty] | 94.803 | /sqft | 8.4314
|  |  |  | LLW | [5 empty] | 196.5065 | [17 empty] | 8.6869 | /sqft |  |  | 0.025899
|  |  |  | Hazardous | [5 empty] | 0 | [17 empty] | 0 | /sqft |  | 0
|  |  |  | Mixed | [5 empty] | 0 | [17 empty] | 0 | /sqft |  |  |  | 0
|  | 1.10.1.1 | Remove Miscellaneous Material |  |  |  | A | 360 | 1 | 360 | 0 |  |  |  |  | 3864 |  |  | 0 |  |  |  |  | 17841.1852 |  | 17841.1852
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Miscellaneous equipment |  | 144 |  |  | 3864 | 0% | 3864 | 4.7704 | 2.5 | crew hrs/comp | 360 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 3864 | 4.7704 |  |  | 360
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 3864 | 4.7704 | 0 | 2385.1852 | 15456 | 17841.1852
|  | 1.10.1.2 | Remove Asbestos & other hazardous material |  |  |  | A | 832.491 | 1.595 | 1327.8231 | 0 |  |  | 60 | 0 | 1256.4 | 344.62 |  | 0 |  | 720 |  | 0 | 5801.1556 | 125269.37 | 131790.5256
1. Productivity factors are included in the rates, unless otherwise specified.
2. Asbestos volume will be increased 30% to account for packaging inefficiencies.
3. Asbestos will be double bagged and disposed of at a controlled landfill licensed to accept ACM
4. Fluorescent lights have PCB containing ballasts
5. Ballasts packaged in 55 gallon drums and disposed of as hazardous waste
6. Clean waste packaged in 30 cu. yd. containers
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove asbestos pipe insulation |  |  | 3072 |  | 291 | -30% | 378.3 | 0.46704 | 0.11 | crew hrs/ft | 337.92 | 2009 mean, p33, 02 82 13.43 1200 with glove bags | [11 empty] | 74.6526 | /foot | 0.12314 | cu. ft./ft
|  |  | Clean | Remove asbestos tile |  |  |  | 22357 | 637 | -30% | 828.1 | 1.0223 | 0.003 | crew hrs/sq. ft. | 67.071 | 2009 mean, p33, 02 82 13.43 5000 | [11 empty] | 2.036 | /sq ft | 0.03704 | cu. ft./sq.ft
|  |  | Clean | Fluorescent lights |  | 100 |  |  | 50 | 0% | 50 | 0.061728 | 0.25 | crew hrs/comp | 25 | Estimated
|  |  | Hazardous | Fluorescent light ballasts, lbs |  | 100 | 300 |  |  | 0% | 0 | 7.5 | 0.25 | crew hrs/comp | 25 | Estimated
|  |  | Lead | Lead core block |  | 1504 |  |  | 265 | -30% | 344.5 | 43.0625 | 0.25 | crew hrs/comp | 376 | Estimated
|  |  | Lead | Lead baskets |  | 6 |  |  | 0.12 | 0% | 0.12 | 0.015 | 0.25 | crew hrs/comp | 1.5 | Estimated
[11 empty] | 1601.02 | 52.1286 |  |  | 832.491
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 1256.4 | 1.5511 | 0 | 775.5556 | 5025.6 | 5801.1556
|  |  |  | Lead | 243990.96 | 344.62 | 43.0775 | 2800.0375 | 473.8525 | 121995.48 | 125269.37
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Fluorescent light ballasts, lbs |  | 60 | 7.5 | 487.5 | 82.5 | 150 | 720
|  | 1.10.1.3 | Remove systems and components |  |  |  |  | 1956.0505 |  | 1956.0505 | 0 | 397.595 | 0 | 0 | 0 | 125575.059 | 0 | 0 | 0 | 21203.7414 | 0 | 0 | 0 | 579815.7045 | 0 | 601019.4459
1. Clean waste packaged in 30 cu. yd. containers
2. Productivity factors are included in the rates, unless otherwise specified.
|  | 1.10.1.3.1 | Remove piping |  |  |  | A | 936.1364 | 1 | 936.1364 | 0 | 397.595 |  |  |  | 2262.359 |  |  | 0 | 21203.7414 |  |  |  | 10445.9539 |  | 31649.6953
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | 0 - 2" pipe, clean |  |  | 7430 |  | 230.33 | 0% | 230.33 | 0.28436 | 0.013333 | crew hrs/ft | 99.0667 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 2 - 3.5" pipe, clean |  |  | 4396 |  | 382.452 | 0% | 382.452 | 0.47216 | 0.017667 | crew hrs/ft | 77.6627 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 4 - 6" pipe, clean |  |  | 4321 |  | 1037.04 | 0% | 1037.04 | 1.2803 | 0.10667 | crew hrs/ft | 460.9067 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | 8 - 14" pipe, clean |  |  | 573 |  | 612.537 | 0% | 612.537 | 0.75622 | 0.178 | crew hrs/ft | 101.994 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Contaminated | 0 - 2" pipe, contam. |  |  | 296 |  | 9.176 | 0% | 9.176 | 0.095583 | 0.018 | crew hrs/ft | 5.328 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
|  |  | Contaminated | 2 - 3.5" pipe, contam. |  |  | 1477 |  | 128.499 | 0% | 128.499 | 1.3385 | 0.02385 | crew hrs/ft | 35.2265 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
|  |  | Contaminated | 4 - 6" pipe, contam. |  |  | 1083 |  | 259.92 | 0% | 259.92 | 2.7075 | 0.144 | crew hrs/ft | 155.952 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3. times 1.35 for pc and alara)
[11 empty] | 2659.954 | 6.9347 |  |  | 936.1364
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 2262.359 | 2.793 | 0 | 1396.5179 | 9049.436 | 10445.9539
|  |  |  | Contaminated |  | 397.595 | 4.1416 | 0 | 0 | 21203.7414 | 21203.7414
|  | 1.10.1.3.2 | Remove ventilation |  |  |  | A | 655.36 | 1 | 655.36 | 0 | 0 |  |  |  | 26058 |  |  | 0 | 0 |  |  |  | 120317.1852 |  | 120317.1852
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | HVAC equipment |  | 94 |  |  | 19808 | 0% | 19808 | 24.4543 | 4 | crew hrs/comp | 376 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Contaminated | HVAC equipment | [5 empty] | 0% | 0 | 0 | 7 | crew hrs/comp | 0 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | HVAC duct |  |  | 4656 |  | 12500 | 50% | 6250 | 7.716 | 0.06 | crew hrs/ft | 279.36 | UCF 69 - Remove Ductwork
[11 empty] | 26058 | 32.1704 |  |  | 655.36
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 26058 | 32.1704 | 0 | 16085.1852 | 104232 | 120317.1852
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.10.1.3.3 | Remove large equipment |  |  |  | A | 364.554 | 1 | 364.554 | 0 | 0 |  |  |  | 97254.7 |  |  | 0 | 0 |  |  |  | 449052.5654 |  | 449052.5654
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove tanks, 0 - 50 gals |  | 2 |  |  | 3.6 | 0% | 3.6 | 0.0044444 | 0.6319 | crew hrs/comp | 1.2638 | UCF 56 - Tanks <50 gals.
|  |  | Clean | Remove tanks, 50 - 300 gals |  | 2 |  |  | 38 | 0% | 38 | 0.046914 | 1.625 | crew hrs/comp | 3.25 | UCF 57 - Tanks 50 - 300 gals.
|  |  | Clean | Remove tanks, 300 - 4k gals |  | 6 |  |  | 425 | 0% | 425 | 0.52469 | 8.7567 | crew hrs/comp | 52.5402 | UCF 58 - Tanks 4k - 15k gals.
|  |  | Clean | Miscellaneous equipment |  | 123 |  |  | 96788.1 | 0% | 96788.1 | 119.4915 | 2.5 | crew hrs/comp | 307.5 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 97254.7 | 120.0675 |  |  | 364.554
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 97254.7 | 120.0675 | 0 | 60033.7654 | 389018.8 | 449052.5654
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.10.1.4 | Decontaminate Structure |  |  |  | A | 477.88 | 1 | 477.88 | 0 | 198.2 |  |  |  | 0 |  |  | 0 | 10570.006 |  |  |  | 0 |  | 10570.006 |  | 21.1255 | /sqft | 0 |  | 0.01291
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Remove storage tubes |  | 12 |  |  | 12.3 | 0% | 12.3 | 0.12813 | 16 | crew hrs/comp | 192 | Estimated
|  |  | Contaminated | Decon concrete surfaces |  |  |  | 7147 | 143 | -30% | 185.9 | 1.9365 | 0.04 | crew hr/sq. ft. | 285.88 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 198.2 | 2.0646 |  |  | 477.88
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 198.2 | 2.0646 | 0 | 0 | 10570.006 | 10570.006 | Packaged in B-25 boxes
|  | 1.10.1.5 | Final Survey of Structure |  |  |  | A | 320 | 1.595 | 510.4 | 0 | [7 empty] | 0 | [6 empty] | 0 |  | 22.5631 | /sqft
|  |  |  | Estimated Duration | 320 | hrs
|  | 1.10.2 | H Wing |  |  |  |  | 6326.4909 |  | 6708.8724 | 0 | 28676.174 | 0 | 45 | 0 | 90069.314 | 0 | 0 | 0 | 1529300.3594 | 540 | 0 | 0 | 415875.598 | 0 | 1945715.9574
|  |  |  | Remove systems and components | [5 empty] | 4496.7129 | [17 empty] | 64.6418
|  |  |  | Clean | [5 empty] | 2272.4734 | [17 empty] | 32.6676 | /sqft | 1.8955
|  |  |  | LLW | [5 empty] | 2242.9895 | [17 empty] | 32.2437 | /sqft |  |  | 0.60742
|  |  |  | Hazardous | [5 empty] | 0 | [17 empty] | 0 | /sqft |  | 0
|  |  |  | Mixed | [5 empty] | 0 | [17 empty] | 0 | /sqft |  |  |  | 0
|  | 1.10.2.1 | Remove Miscellaneous Material |  |  |  | A | 120 | 1 | 120 | 0 |  |  |  |  | 1288 |  |  | 0 |  |  |  | 0 | 5947.0617 |  | 5947.0617
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Miscellaneous equipment |  | 48 |  |  | 1288 | 0% | 1288 | 1.5901 | 2.5 | crew hrs/comp | 120 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 1288 | 1.5901 |  |  | 120
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 1288 | 1.5901 | 0 | 795.0617 | 5152 | 5947.0617
|  | 1.10.2.2 | Remove Asbestos & other hazardous material |  |  |  | A | 322.658 | 1.595 | 514.6395 | 0 |  |  | 45 | 0 | 582.2 |  |  | 0 |  | 540 |  | 0 | 2688.1827 |  | 3228.1827
1. Productivity factors are included in the rates, unless otherwise specified.
2. Asbestos volume will be increased 30% to account for packaging inefficiencies.
3. Asbestos will be double bagged and disposed of at a controlled landfill licensed to accept ACM
4. Fluorescent lights have PCB containing ballasts
5. Ballasts packaged in 55 gallon drums and disposed of as hazardous waste
6. Clean waste packaged in 30 cu. yd. containers
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove asbestos pipe insulation |  |  | 2545 |  | 246 | -30% | 319.8 | 0.39481 | 0.11 | crew hrs/ft | 279.95 | 2009 mean, p33, 02 82 13.43 1200 with glove bags | [11 empty] | 74.6526 | /foot | 0.12566 | cu. ft./ft
|  |  | Clean | Remove asbestos tile |  |  |  | 1736 | 173 | -30% | 224.9 | 0.27765 | 0.003 | crew hrs/sq. ft. | 5.208 | 2009 mean, p33, 02 82 13.43 5000 | [11 empty] | 2.036 | /sq ft | 0.12955 | cu. ft./sq.ft
|  |  | Clean | Fluorescent lights |  | 75 |  |  | 37.5 | 0% | 37.5 | 0.046296 | 0.25 | crew hrs/comp | 18.75 | Estimated
|  |  | Hazardous | Fluorescent light ballasts, lbs |  | 75 | 225 |  |  | 0% | 0 | 5.625 | 0.25 | crew hrs/comp | 18.75 | Estimated
[11 empty] | 582.2 | 6.3438 |  |  | 322.658
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 582.2 | 0.71877 | 0 | 359.3827 | 2328.8 | 2688.1827
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Fluorescent light ballasts, lbs |  | 45 | 5.625 | 365.625 | 61.875 | 112.5 | 540
|  | 1.10.2.3 | Remove systems and components |  |  |  |  | 4376.7129 |  | 4376.7129 | 0 | 27973.524 | 0 | 0 | 0 | 88199.114 | 0 | 0 | 0 | 1491828.0349 | 0 | 0 | 0 | 407240.3535 | 0 | 1899068.3885
1. Clean waste packaged in 30 cu. yd. containers
2. Productivity factors are included in the rates, unless otherwise specified.
|  | 1.10.2.3.1 | Remove piping |  |  |  | A | 1132.8135 | 1 | 1132.8135 | 0 | 1625.524 |  |  |  | 1614.114 |  |  | 0 | 86689.1949 |  |  |  | 7452.8227 |  | 94142.0176
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | 0 - 2" pipe, clean |  |  | 6511 |  | 197.253 | 0% | 197.253 | 0.24352 | 0.013333 | crew hrs/ft | 86.8133 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 2 - 3.5" pipe, clean |  |  | 2973 |  | 255.171 | 0% | 255.171 | 0.31503 | 0.017667 | crew hrs/ft | 52.523 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 4 - 6" pipe, clean |  |  | 3905 |  | 937.2 | 0% | 937.2 | 1.157 | 0.10667 | crew hrs/ft | 416.5333 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | 8 - 14" pipe, clean |  |  | 210 |  | 224.49 | 0% | 224.49 | 0.27715 | 0.178 | crew hrs/ft | 37.38 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | Excavate buried pipe - assume 4' wide & 4' deep |  |  | 481 |  |  | 0% | 0 |  | 0.01 | crew hr/cu. yd. | 2.8504 | UCF 12 - excavate below grade structures
|  |  | Clean | Buried pipe, clean - length to remove included above |  |  | 0 |  | 0 | 0% | 0 | 0 | 0.10667 | crew hrs/ft | 0 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 3.)
|  |  | Contaminated | Excavate buried pipe - assume 4' wide & 15' deep |  |  | 1235 |  |  | 0% | 0 |  | 0.01 | crew hr/cu. yd. | 27.4444 | UCF 12 - excavate below grade structures
|  |  | Contaminated | Buried pipe, contam. - length to remove included below |  |  | 0 |  | 0 | 0% | 0 | 0 | 0.144 | crew hrs/ft | 0 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3. times 1.35 for pc and alara)
|  |  | Contaminated | 0 - 2" pipe, contam. |  |  | 283 |  | 8.773 | 0% | 8.773 | 0.091385 | 0.018 | crew hrs/ft | 5.094 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
|  |  | Contaminated | 2 - 3.5" pipe, contam. |  |  | 1153 |  | 100.311 | 0% | 100.311 | 1.0449 | 0.02385 | crew hrs/ft | 27.4991 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
|  |  | Contaminated | 4 - 6" pipe, contam. |  |  | 1508 |  | 361.92 | 0% | 361.92 | 3.77 | 0.144 | crew hrs/ft | 217.152 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3. times 1.35 for pc and alara)
|  |  | Contaminated | 8 - 14" pipe, contam. |  |  | 1080 |  | 1154.52 | 0% | 1154.52 | 12.0262 | 0.2403 | crew hrs/ft | 259.524 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3. times 1.35 for pc and alara)
[11 empty] | 3239.638 | 18.9253 |  |  | 1132.8135
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 1614.114 | 1.9927 | 0 | 996.3667 | 6456.456 | 7452.8227
|  |  |  | Contaminated |  | 1625.524 | 16.9325 | 0 | 0 | 86689.1949 | 86689.1949
|  | 1.10.2.3.2 | Remove ventilation |  |  |  | A | 630.86 | 1 | 630.86 | 0 | 18596 |  |  |  | 7763 |  |  | 0 | 991724.68 |  |  |  | 35843.9753 |  | 1027568.6553
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | HVAC equipment |  | 13 |  |  | 1745 | 0% | 1745 | 2.1543 | 4 | crew hrs/comp | 52 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Contaminated | HVAC equipment |  | 52 |  |  | 18596 | 0% | 18596 | 193.7083 | 7 | crew hrs/comp | 364 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | HVAC duct |  |  | 3581 |  | 12036 | 50% | 6018 | 7.4296 | 0.06 | crew hrs/ft | 214.86 | UCF 69 - Remove Ductwork
[11 empty] | 26359 | 203.2923 |  |  | 630.86
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 7763 | 9.584 | 0 | 4791.9753 | 31052 | 35843.9753
|  |  |  | Contaminated |  | 18596 | 193.7083 | 0 | 0 | 991724.68 | 991724.68
|  | 1.10.2.3.3 | Remove large equipment |  |  |  | A | 2613.0394 | 1 | 2613.0394 | 0 | 7752 |  |  |  | 78822 |  |  | 0 | 413414.16 |  |  |  | 363943.5556 |  | 777357.7156
|  |  | 1.10.2.3.3.1 | Pickle area |  |  | A | 88.76 | 1 | 88.76 | 0 | 480 |  |  |  | 0 |  |  | 0 | 25598.4 |  |  |  | 0 |  | 25598.4
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Remove tanks, 50 - 300 gals |  | 12 |  |  | 180 | 0% | 180 | 1.875 | 2.937 | crew hrs/comp | 35.244 | UCF 57 - Tanks 50 - 300 gals.
|  |  | Contaminated | Remove tanks, 300 - 4k gals |  | 2 |  |  | 300 | 0% | 300 | 3.125 | 26.758 | crew hrs/comp | 53.516 | UCF 58 - Tanks 300 - 4k gals.
[11 empty] | 480 | 5 |  |  | 88.76
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 480 | 5 | 0 | 0 | 25598.4 | 25598.4
|  |  | 1.10.2.3.3.2 | Retention tanks |  |  | A | 53.516 | 1 | 53.516 | 0 | 222 |  |  |  | 0 |  |  | 0 | 11839.26 |  |  |  | 0 |  | 11839.26
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Remove tanks, 300 - 4k gals |  | 2 |  |  | 222 | 0% | 222 | 2.3125 | 26.758 | crew hrs/comp | 53.516 | UCF 58 - Tanks 300 - 4k gals.
[11 empty] | 222 | 2.3125 |  |  | 53.516
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 222 | 2.3125 | 0 | 0 | 11839.26 | 11839.26
|  |  | 1.10.2.3.3.3 | Grinding Area |  |  | A | 400 | 1 | 400 | 0 | 1554 |  |  |  | 0 |  |  | 0 | 82874.82 |  |  |  | 0 |  | 82874.82
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Miscellaneous equipment |  | 100 |  |  | 1554 | 0% | 1554 | 16.1875 | 4 | crew hrs/comp | 400 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 1554 | 16.1875 |  |  | 400
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 1554 | 16.1875 | 0 | 0 | 82874.82 | 82874.82
|  |  | 1.10.2.3.3.4 | Hot Shop |  |  | A | 400 | 1 | 400 | 0 | 2520 |  |  |  | 0 |  |  | 0 | 134391.6 |  |  |  | 0 |  | 134391.6
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Miscellaneous equipment |  | 100 |  |  | 2520 | 0% | 2520 | 26.25 | 4 | crew hrs/comp | 400 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 2520 | 26.25 |  |  | 400
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 2520 | 26.25 | 0 | 0 | 134391.6 | 134391.6
|  |  | 1.10.2.3.3.5 | Remainder of building |  |  | A | 1670.7634 | 1 | 1670.7634 | 0 | 2976 |  |  |  | 78822 |  |  | 0 | 158710.08 |  |  |  | 363943.5556 |  | 522653.6356
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove tanks, 0 - 50 gals | [5 empty] | 0% | 0 | 0 | 0.6319 | crew hrs/comp | 0 | UCF 56 - Tanks <50 gals.
|  |  | Clean | Remove tanks, 50 - 300 gals |  | 2 |  |  | 44 | 0% | 44 | 0.054321 | 1.625 | crew hrs/comp | 3.25 | UCF 57 - Tanks 50 - 300 gals.
|  |  | Clean | Remove tanks, 300 - 4k gals |  | 2 |  |  | 228 | 0% | 228 | 0.28148 | 8.7567 | crew hrs/comp | 17.5134 | UCF 58 - Tanks 300 - 4k gals.
|  |  | Clean | Miscellaneous equipment |  | 500 |  |  | 78550 | 0% | 78550 | 96.9753 | 2.5 | crew hrs/comp | 1250 | UCF 64 - 300 to 1,000 lbs
|  |  | Contaminated | Miscellaneous equipment |  | 100 |  |  | 2976 | 0% | 2976 | 31 | 4 | crew hrs/comp | 400 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 81798 | 128.3111 |  |  | 1670.7634
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 78822 | 97.3111 | 0 | 48655.5556 | 315288 | 363943.5556
|  |  |  | Contaminated |  | 2976 | 31 | 0 | 0 | 158710.08 | 158710.08
|  | 1.10.2.4 | Decontaminate Structure |  |  |  |  | 1187.12 |  | 1187.12 | 0 | 702.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37472.3245 | 0 | 0 | 0 | 0 | 0 | 37472.3245 |  | 17.0653 | /sqft | 0 |  | 0.014883
|  | 1.10.2.4.1 | Pickle room |  |  |  | A | 683.2 | 1 | 683.2 | 0 | 457.6 |  |  |  | 0 |  |  | 0 | 24403.808 |  |  |  | 0 |  | 24403.808
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Decontaminate brick - 2" |  |  |  | 1000 | 170 | -30% | 221 | 2.3021 | 0.32 | crew hr/sq. ft. | 320 | Average UCF 7 & 8 - Concrete surfaces 2" deep
|  |  | Contaminated | Decontaminate brick - 1/4" |  |  |  | 600 | 12 | -30% | 15.6 | 0.1625 | 0.04 | crew hr/sq. ft. | 24 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
|  |  | Contaminated | Decon concrete and block surfaces - 1" |  |  |  | 2120 | 170 | -30% | 221 | 2.3021 | 0.16 | crew hr/sq. ft. | 339.2 | Average UCF 7 & 8 - Concrete surfaces 1" deep
[11 empty] | 457.6 | 4.7667 |  |  | 683.2
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 457.6 | 4.7667 | 0 | 0 | 24403.808 | 24403.808 | Packaged in B-25 boxes
|  | 1.10.2.4.2 | Retention Tank Room |  |  |  | A | 53.76 | 1 | 53.76 | 0 | 35.1 |  |  |  | 0 |  |  | 0 | 1871.883 |  |  |  | 0 |  | 1871.883
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Decon concrete and block surfaces - 1" |  |  |  | 336 | 27 | -30% | 35.1 | 0.36563 | 0.16 | crew hr/sq. ft. | 53.76 | Average UCF 7 & 8 - Concrete surfaces 1" deep
[11 empty] | 35.1 | 0.36563 |  |  | 53.76
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 35.1 | 0.36563 | 0 | 0 | 1871.883 | 1871.883 | Packaged in B-25 boxes
|  | 1.10.2.4.3 | Tool Crib |  |  |  | A | 236.32 | 1 | 236.32 | 0 | 140.4 |  |  |  | 0 |  |  | 0 | 7487.532 |  |  |  | 0 |  | 7487.532
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Decontaminate concrete - 1/4" |  |  |  | 2548 | 41 | -30% | 53.3 | 0.55521 | 0.04 | crew hr/sq. ft. | 101.92 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
|  |  | Contaminated | Decon concrete and block surfaces - 1" |  |  |  | 840 | 67 | -30% | 87.1 | 0.90729 | 0.16 | crew hr/sq. ft. | 134.4 | Average UCF 7 & 8 - Concrete surfaces 1" deep
[11 empty] | 140.4 | 1.4625 |  |  | 236.32
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 140.4 | 1.4625 | 0 | 0 | 7487.532 | 7487.532 | Packaged in B-25 boxes
|  | 1.10.2.4.4 | Grinding Room |  |  |  | A | 62.16 | 1 | 62.16 | 0 | 20.15 |  |  |  | 0 |  |  | 0 | 1074.5995 |  |  |  | 0 |  | 1074.5995
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Decon concrete and block surfaces - .5" |  |  |  | 777 | 15.5 | -30% | 20.15 | 0.2099 | 0.08 | crew hr/sq. ft. | 62.16 | Average UCF 7 & 8 - Concrete surfaces 1/2" deep
[11 empty] | 20.15 | 0.2099 |  |  | 62.16
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 20.15 | 0.2099 | 0 | 0 | 1074.5995 | 1074.5995 | Packaged in B-25 boxes
|  | 1.10.2.4.5 | SMS Storage Room |  |  |  | A | 13.44 | 1 | 13.44 | 0 | 4.42 |  |  |  | 0 |  |  | 0 | 235.7186 |  |  |  | 0 |  | 235.7186
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Decon concrete and block surfaces - .25" |  |  |  | 336 | 3.4 | -30% | 4.42 | 0.046042 | 0.04 | crew hr/sq. ft. | 13.44 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 4.42 | 0.046042 |  |  | 13.44
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 4.42 | 0.046042 | 0 | 0 | 235.7186 | 235.7186 | Packaged in B-25 boxes
|  | 1.10.2.4.6 | HiBay |  |  |  | A | 138.24 | 1 | 138.24 | 0 | 44.98 |  |  |  | 0 |  |  | 0 | 2398.7834 |  |  |  | 0 |  | 2398.7834
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Decon concrete and block surfaces - .5" |  |  |  | 1728 | 34.6 | -30% | 44.98 | 0.46854 | 0.08 | crew hr/sq. ft. | 138.24 | Average UCF 7 & 8 - Concrete surfaces 1/2" deep
[11 empty] | 44.98 | 0.46854 |  |  | 138.24
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 44.98 | 0.46854 | 0 | 0 | 2398.7834 | 2398.7834 | Packaged in B-25 boxes
|  | 1.10.2.5 | Final Survey of Structure |  |  |  | A | 320 | 1.595 | 510.4 | 0 | [7 empty] | 0 | [6 empty] | 0 |  | 7.3372 | /sqft
|  |  |  | Estimated Duration | 320 | hrs
|  | 1.10.3 | F Wing |  |  |  |  | 3708.9365 |  | 4069.347 | 0 | 5344.4774 | 0 | 45 | 0 | 7961.4179 | 2.2 | 0 | 0 | 285020.9806 | 540 | 0 | 0 | 88700.3934 | 0 | 374261.374
Remove systems and components
|  |  |  | Clean | [5 empty] | 1098.6827 | [17 empty] | 10.3762 | /sqft | 0.10362
|  |  |  | LLW | [5 empty] | 744.7818 | [17 empty] | 7.0339 | /sqft |  |  | 0.069979
|  |  |  | Hazardous | [5 empty] | 0 | [17 empty] | 0 | /sqft |  | 0
|  |  |  | Mixed | [5 empty] | 0 | [17 empty] | 0 | /sqft |  |  |  | 0
|  | 1.10.3.1 | Remove Miscellaneous Material |  |  |  | A | 265 | 1 | 265 | 0 | 1524 |  |  |  | 1194 |  |  | 0 | 81274.92 |  |  | 0 | 5513.037 |  | 86787.957
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Miscellaneous equipment |  | 42 |  |  | 1194 | 0% | 1194 | 1.4741 | 2.5 | crew hrs/comp | 105 | UCF 64 - 300 to 1,000 lbs
|  |  | Contaminated | Miscellaneous equipment |  | 40 |  |  | 1524 | 0% | 1524 | 15.875 | 4 | crew hrs/sq. ft. | 160 | 2009 mean, p33, 02 82 13.43 5000
[11 empty] | 2718 | 17.3491 |  |  | 265
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 1194 | 1.4741 | 0 | 737.037 | 4776 | 5513.037
|  |  |  | Contaminated |  | 1524 | 15.875 | 0 | 0 | 81274.92 | 81274.92
|  | 1.10.3.2 | Remove Asbestos & other hazardous material |  |  |  | A | 285.732 | 1.595 | 455.7425 | 0 | 10.79 |  | 45 | 0 | 514.99 | 2.2 |  | 0 | 575.4307 | 540 |  | 0 | 2377.8551 | 0 | 3493.2858
1. Productivity factors are included in the rates, unless otherwise specified.
2. Asbestos volume will be increased 30% to account for packaging inefficiencies.
3. Asbestos will be double bagged and disposed of at a controlled landfill licensed to accept ACM
4. Fluorescent lights have PCB containing ballasts
5. Ballasts packaged in 55 gallon drums and disposed of as hazardous waste
6. Clean waste packaged in 30 cu. yd. containers
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove asbestos pipe insulation |  |  | 2014 |  | 264 | -30% | 343.2 | 0.4237 | 0.11 | crew hrs/ft | 221.54 | 2009 mean, p33, 02 82 13.43 1200 with glove bags | [11 empty] | 74.6526 | /foot | 0.17041 | cu. ft./ft
|  |  | Clean | Remove asbestos tile |  |  |  | 5148 | 103.3 | -30% | 134.29 | 0.16579 | 0.003 | crew hrs/sq. ft. | 15.444 | 2009 mean, p33, 02 82 13.43 5000 | [11 empty] | 2.036 | /sq ft | 0.026075 | cu. ft./sq.ft
|  |  | Contaminated | Remove asbestos tile |  |  |  | 416 | 8.3 | -30% | 10.79 | 0.1124 | 0.003 | crew hrs/sq. ft. | 1.248 | 2009 mean, p33, 02 82 13.43 5000
|  |  | Clean | Fluorescent lights |  | 75 |  |  | 37.5 | 0% | 37.5 | 0.046296 | 0.25 | crew hrs/comp | 18.75 | Estimated
|  |  | Hazardous | Fluorescent light ballasts, lbs |  | 75 | 225 |  |  | 0% | 0 | 5.625 | 0.25 | crew hrs/comp | 18.75 | Estimated
|  |  | Lead | Lead weights |  | 40 |  |  | 2.2 | 0% | 2.2 | 0.275 | 0.25 | crew hrs/comp | 10 | Estimated
[11 empty] | 527.98 | 6.6482 |  |  | 285.732
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 514.99 | 0.63579 | 0 | 317.8951 | 2059.96 | 2377.8551
|  |  |  | Lead | 1557.6 | 2.2 | 0.275 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 10.79 | 0.1124 | 0 | 0 | 575.4307 | 575.4307
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Fluorescent light ballasts, lbs |  | 45 | 5.625 | 365.625 | 61.875 | 112.5 | 540
|  | 1.10.3.3 | Remove systems and components |  |  |  |  | 1558.4665 |  | 1558.4665 | 0 | 3504.676 | 0 | 0 | 0 | 6252.4279 | 0 | 0 | 0 | 186904.3711 | 0 | 0 | 0 | 80809.5013 | 0 | 267713.8723
1. Clean waste packaged in 30 cu. yd. containers
2. Productivity factors are included in the rates, unless otherwise specified.
|  | 1.10.3.3.1 | Remove piping |  |  |  | A | 902.5238 | 1 | 902.5238 | 0 | 495.676 |  |  |  | 2306.523 |  |  | 0 | 26434.4011 |  |  |  | 10649.8716 |  | 37084.2727
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | 0 - 2" pipe, clean |  |  | 7942 |  | 246.202 | 0% | 246.202 | 0.30395 | 0.013333 | crew hrs/ft | 105.8933 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 2 - 3.5" pipe, clean |  |  | 2672 |  | 232.464 | 0% | 232.464 | 0.28699 | 0.017667 | crew hrs/ft | 47.2053 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 4 - 6" pipe, clean |  |  | 3104 |  | 744.96 | 0% | 744.96 | 0.9197 | 0.10667 | crew hrs/ft | 331.0933 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | 8 - 14" pipe, clean |  |  | 1013 |  | 1082.897 | 0% | 1082.897 | 1.3369 | 0.178 | crew hrs/ft | 180.314 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | Excavate buried pipe - assume 4' wide & 4' deep | [5 empty] | 0% | 0 |  | 0.01 | crew hr/cu. yd. | 0 | UCF 12 - excavate below grade structures
|  |  | Clean | Buried pipe, clean - length to remove included above |  |  | 0 |  | 0 | 0% | 0 | 0 | 0.10667 | crew hrs/ft | 0 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 3.)
|  |  | Contaminated | Excavate buried pipe - assume 4' wide & 15' deep |  |  | 82 |  |  | 0% | 0 |  | 0.01 | crew hr/cu. yd. | 1.8222 | UCF 12 - excavate below grade structures
|  |  | Contaminated | Buried pipe, contam. - length to remove included below |  |  | 0 |  | 0 | 0% | 0 | 0 | 0.144 | crew hrs/ft | 0 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3. times 1.35 for pc and alara)
|  |  | Contaminated | 0 - 2" pipe, contam. |  |  | 207 |  | 6.417 | 0% | 6.417 | 0.066844 | 0.018 | crew hrs/ft | 3.726 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
|  |  | Contaminated | 2 - 3.5" pipe, contam. |  |  | 655 |  | 56.985 | 0% | 56.985 | 0.59359 | 0.02385 | crew hrs/ft | 15.6218 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
|  |  | Contaminated | 4 - 6" pipe, contam. |  |  | 1329 |  | 318.96 | 0% | 318.96 | 3.3225 | 0.144 | crew hrs/ft | 191.376 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3. times 1.35 for pc and alara)
|  |  | Contaminated | 8 - 14" pipe, contam. |  |  | 106 |  | 113.314 | 0% | 113.314 | 1.1804 | 0.2403 | crew hrs/ft | 25.4718 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3. times 1.35 for pc and alara)
[11 empty] | 2802.199 | 8.0109 |  |  | 902.5238
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 2306.523 | 2.8476 | 0 | 1423.7796 | 9226.092 | 10649.8716
|  |  |  | Contaminated |  | 495.676 | 5.1633 | 0 | 0 | 26434.4011 | 26434.4011
|  | 1.10.3.3.2 | Remove ventilation |  |  |  | A | 481.42 | 1 | 481.42 | 0 | 2593 |  |  |  | 3932 |  |  | 0 | 138284.69 |  |  |  | 18155.1605 |  | 156439.8505
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | HVAC equipment |  | 19 |  |  | 1892 | 0% | 1892 | 2.3358 | 4 | crew hrs/comp | 76 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Contaminated | HVAC equipment |  | 36 |  |  | 2593 | 0% | 2593 | 27.0104 | 7 | crew hrs/comp | 252 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | HVAC duct |  |  | 2557 |  | 4080 | 50% | 2040 | 2.5185 | 0.06 | crew hrs/ft | 153.42 | UCF 69 - Remove Ductwork
[11 empty] | 6525 | 31.8647 |  |  | 481.42
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 3932 | 4.8543 | 0 | 2427.1605 | 15728 | 18155.1605
|  |  |  | Contaminated |  | 2593 | 27.0104 | 0 | 0 | 138284.69 | 138284.69
|  | 1.10.3.3.3 | Remove large equipment |  |  |  | A | 174.5227 | 1 | 174.5227 | 0 | 416 |  |  |  | 13.9049 |  |  | 0 | 22185.28 |  |  |  | 52004.4691 |  | 74189.7491
|  |  | 1.11.3.3.3.1 | All Areas |  |  | A | 174.5227 | 1 | 174.5227 | 0 | 416 |  |  |  | 13.9049 |  |  | 0 | 22185.28 |  |  |  | 52004.4691 |  | 74189.7491
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove tanks, 50 - 300 gals |  | 6 |  |  | 27 | 0% | 27 | 0.033333 | 1.625 | crew hrs/comp | 9.75 | UCF 50 - Tanks 57 - 300 gals.
|  |  | Clean | Remove tanks, 300 - 4k gals |  | 1 |  |  | 57 | 0% | 57 | 0.07037 | 8.7567 | crew hrs/comp | 8.7567 | UCF 58 - Tanks 300 - 4k gals.
|  |  | Contaminated | Remove tanks, 300 - 4k gals |  | 2 |  |  | 176 | 0% | 176 | 1.8333 | 26.758 | crew hrs/comp | 53.516 | UCF 58 - Tanks 300 - 4k gals.
|  |  | Contaminated | Miscellaneous equipment |  | 10 |  |  | 240 | 0% | 240 | 2.5 | 4 | crew hrs/comp | 40 | UCF 64 - 300 to 1,000 lbs
|  |  | Clean | Miscellaneous equipment |  | 25 |  |  | 11179 | 0% | 11179 | 13.8012 | 2.5 | crew hrs/comp | 62.5 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 11679 | 18.2383 |  |  | 174.5227
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 11263 | 13.9049 | 0 | 6952.4691 | 45052 | 52004.4691
|  |  |  | Contaminated |  | 416 | 4.3333 | 0 | 0 | 22185.28 | 22185.28
|  |  | 2.11.2.3.3.2 | Retention tanks |  |  | A | 0 | 1 | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 |  | 0
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove tanks, 0 - 50 gals | [5 empty] | 0% | 0 | 0 | 1 | crew hrs/comp | 0 | UCF 49 - Tanks <50 gals.
|  |  | Contaminated | Remove tanks, 50 - 300 gals | [5 empty] | 0% | 0 | 0 | 3 | crew hrs/comp | 0 | UCF 57 - Tanks 50 - 300 gals.
|  |  | Contaminated | Remove tanks, 300 - 4k gals | [5 empty] | 0% | 0 | 0 | 27 | crew hrs/comp | 0 | UCF 58 - Tanks 300 - 4k gals.
|  |  | Clean | Miscellaneous equipment | [5 empty] | 0% | 0 | 0 | 2.5 | crew hrs/comp | 0 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 0 | 0 |  |  | 0
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.11.2.3.3.3 | Grinding Area |  |  | A | 0 | 1 | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 |  | 0
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove tanks, 0 - 50 gals | [5 empty] | 0% | 0 | 0 | 1 | crew hrs/comp | 0 | UCF 49 - Tanks <50 gals.
|  |  | Contaminated | Remove tanks, 50 - 300 gals | [5 empty] | 0% | 0 | 0 | 3 | crew hrs/comp | 0 | UCF 57 - Tanks 50 - 300 gals.
|  |  | Contaminated | Remove tanks, 300 - 4k gals | [5 empty] | 0% | 0 | 0 | 27 | crew hrs/comp | 0 | UCF 58 - Tanks 300 - 4k gals.
|  |  | Contaminated | Miscellaneous equipment | [5 empty] | 0% | 0 | 0 | 4 | crew hrs/comp | 0 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 0 | 0 |  |  | 0
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.11.2.3.3.4 | Hot Shop |  |  | A | 0 | 1 | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 |  | 0
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove tanks, 0 - 50 gals | [5 empty] | 0% | 0 | 0 | 1 | crew hrs/comp | 0 | UCF 49 - Tanks <50 gals.
|  |  | Contaminated | Remove tanks, 50 - 300 gals | [5 empty] | 0% | 0 | 0 | 3 | crew hrs/comp | 0 | UCF 57 - Tanks 50 - 300 gals.
|  |  | Contaminated | Remove tanks, 300 - 4k gals | [5 empty] | 0% | 0 | 0 | 27 | crew hrs/comp | 0 | UCF 58 - Tanks 300 - 4k gals.
|  |  | Contaminated | Miscellaneous equipment | [5 empty] | 0% | 0 | 0 | 4 | crew hrs/comp | 0 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 0 | 0 |  |  | 0
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2.11.2.3.3.5 | Remainder of building |  |  | A | 0 | 1 | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 |  | 0
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove tanks, 0 - 50 gals | [5 empty] | 0% | 0 | 0 | 1 | crew hrs/comp | 0 | UCF 49 - Tanks <50 gals.
|  |  | Clean | Remove tanks, 50 - 300 gals | [5 empty] | 0% | 0 | 0 | 2 | crew hrs/comp | 0 | UCF 50 - Tanks 50 - 300 gals.
|  |  | Clean | Remove tanks, 4k - 15k gals | [5 empty] | 0% | 0 | 0 | 27 | crew hrs/comp | 0 | UCF 52 - Tanks 4k - 15k gals.
|  |  | Clean | Miscellaneous equipment | [5 empty] | 0% | 0 | 0 | 2.5 | crew hrs/comp | 0 | UCF 64 - 300 to 1,000 lbs
|  |  | Contaminated | Miscellaneous equipment | [5 empty] | 0% | 0 | 0 | 4 | crew hrs/comp | 0 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 0 | 0 |  |  | 0
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.10.3.4 | Decontaminate Structure |  |  |  |  | 1279.738 |  | 1279.738 | 0 | 305.0114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16266.2589 | 0 | 0 | 0 | 0 | 0 | 16266.2589 |  | 2.6848 | /sqft | 0 |  | 0.0014974
|  | 1.10.3.4.1 | F105, 106, 114, 115, 108 & GB |  |  |  | A | 35.2 | 1 | 35.2 | 0 | 23.4 |  |  |  | 0 |  |  | 0 | 1247.922 |  |  |  | 0 |  | 1247.922
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Decontaminate brick - 2" | [5 empty] | -30% | 0 | 0 | 0.32 | crew hr/sq. ft. | 0 | Average UCF 7 & 8 - Concrete surfaces 2" deep
|  |  | Contaminated | Decontaminate brick - 1/4" |  |  |  | 880 | 18 | -30% | 23.4 | 0.24375 | 0.04 | crew hr/sq. ft. | 35.2 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
|  |  | Contaminated | Decon concrete and block surfaces - 1" | [5 empty] | -30% | 0 | 0 | 0.16 | crew hr/sq. ft. | 0 | Average UCF 7 & 8 - Concrete surfaces 1" deep
[11 empty] | 23.4 | 0.24375 |  |  | 35.2
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 23.4 | 0.24375 | 0 | 0 | 1247.922 | 1247.922 | Packaged in B-25 boxes
|  | 1.10.3.4.2 | F109, 117, 117B, 118 & 118A/B |  |  |  | A | 70.08 | 1 | 70.08 | 0 | 45.5 |  |  |  | 0 |  |  | 0 | 2426.515 |  |  |  | 0 |  | 2426.515
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Decontaminate brick - 1/4" |  |  |  | 1752 | 35 | -30% | 45.5 | 0.47396 | 0.04 | crew hr/sq. ft. | 70.08 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 45.5 | 0.47396 |  |  | 70.08
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 45.5 | 0.47396 | 0 | 0 | 2426.515 | 2426.515 | Packaged in B-25 boxes
|  | 1.10.3.4.3 | F113 |  |  |  | A | 42.2 | 1 | 42.2 | 0 | 27.3 |  |  |  | 0 |  |  | 0 | 1455.909 |  |  |  | 0 |  | 1455.909
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Decontaminate concrete - 1/4" |  |  |  | 1055 | 21 | -30% | 27.3 | 0.28437 | 0.04 | crew hr/sq. ft. | 42.2 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
|  |  | Contaminated | Decon concrete and block surfaces - 1" | [5 empty] | -30% | 0 | 0 | 0.16 | crew hr/sq. ft. | 0 | Average UCF 7 & 8 - Concrete surfaces 1" deep
[11 empty] | 27.3 | 0.28437 |  |  | 42.2
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 27.3 | 0.28437 | 0 | 0 | 1455.909 | 1455.909 | Packaged in B-25 boxes
|  | 1.10.3.4.4 | Doors magnitite |  |  |  | A | 5.6 | 1 | 5.6 | 0 | 3.64 |  |  |  | 0 |  |  | 0 | 194.1212 |  |  |  | 0 |  | 194.1212
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Decon concrete and block surfaces - 1" |  |  |  | 35 | 2.8 | -30% | 3.64 | 0.037917 | 0.16 | crew hr/sq. ft. | 5.6 | Average UCF 7 & 8 - Concrete surfaces 1" deep
[11 empty] | 3.64 | 0.037917 |  |  | 5.6
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 3.64 | 0.037917 | 0 | 0 | 194.1212 | 194.1212 | Packaged in B-25 boxes
|  | 1.10.3.4.5 | Doors - Steel (Shot Blast) |  |  |  | A | 131.2 | 1 | 131.2 | 0 | 7.761 |  |  |  | 0 |  |  | 0 | 413.8941 |  |  |  | 0 |  | 413.8941
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Shot Blast surfaces - .125" |  | 8 |  | 335 | 5.97 | -30% | 7.761 | 0.080844 | 8 | crew hr/comp. | 131.2 | Estimated, includes 2.05 PLF
[11 empty] | 7.761 | 0.080844 |  |  | 131.2
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 7.761 | 0.080844 | 0 | 0 | 413.8941 | 413.8941 | Packaged in B-25 boxes
|  | 1.10.3.4.6 | Hot Cell |  |  |  | A | 995.458 | 1 | 995.458 | 0 | 197.4104 |  |  |  | 0 |  |  | 0 | 10527.8975 |  |  |  | 0 |  | 10527.8975 |  | 9.4013 | /sqft | 0 |  | 0.0027472
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Area, sq. ft. | Volume, cu. Ft. | Weight, lbs | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Remove Storage Tubes |  | 47 |  | 90 | 20880 | -30% | 117 | 1.2188 | 16 | crew hrs/core | 752 | Estimated
|  |  | Contaminated | Decon liners (Shot Blast)- .125" |  |  | 5938 | 61.8542 |  | -30% | 80.4104 | 0.83761 | 0.02 | crew hr/sq. ft. | 243.458 | 2009 mean, p281, 09 05 05.20 8100 X plf of 2.05
[11 empty] | 197.4104 | 2.0564 |  |  | 995.458
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 197.4104 | 2.0564 | 0 | 0 | 10527.8975 | 10527.8975 | Packaged in B-25 boxes
|  | 1.10.3.5 | Final Survey of Structure |  |  |  | A | 320 | 1.595 | 510.4 | 0 | [7 empty] | 0 | [6 empty] | 0 |  | 18.9656 | /sqft
|  |  |  | Estimated Duration | 320 | hrs
|  | 1.10.4 | Fallout Shelter |  |  |  |  | 693.1216 |  | 890.4676 | 0 | 0 | 0 | 10.2 | 0 | 36518.594 | 0 | 0 | 0 | 0 | 122.4 | 0 | 0 | 168616.718 | 0 | 168739.118
|  |  |  | Remove systems and components | [5 empty] | 361.4476 | [17 empty] | 13.4308 | /sqft | 1.9975 | 0 | 0 | 0
|  | 1.10.4.1 | Remove Asbestos & other hazardous material |  |  |  | A | 11.674 | 1.595 | 18.62 | 0 |  |  | 10.2 |  | 35.8 |  |  | 0 |  | 122.4 |  |  | 165.2988 |  | 287.6988
1. Productivity factors are included in the rates, unless otherwise specified.
2. Asbestos volume will be increased 30% to account for packaging inefficiencies.
3. Asbestos will be double bagged and disposed of at a controlled landfill licensed to accept ACM
4. Fluorescent lights have PCB containing ballasts
5. Ballasts packaged in 55 gallon drums and disposed of as hazardous waste
6. Clean waste packaged in 30 cu. yd. containers
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove asbestos tile |  |  |  | 1058 | 21 | -30% | 27.3 | 0.033704 | 0.003 | crew hrs/sq. ft. | 3.174 | 2009 mean, p33, 02 82 13.43 5000 | [11 empty] | 2.036 | /sq ft | 0.025803 | cu. ft./sq.ft
|  |  | Clean | Fluorescent lights |  | 17 |  |  | 8.5 | 0% | 8.5 | 0.010494 | 0.25 | crew hrs/comp | 4.25 | Estimated
|  |  | Hazardous | Fluorescent light ballasts, lbs |  | 17 | 51 |  |  | 0% | 0 | 1.275 | 0.25 | crew hrs/comp | 4.25 | Estimated
[11 empty] | 35.8 | 1.3192 |  |  | 11.674
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 35.8 | 0.044198 | 0 | 22.0988 | 143.2 | 165.2988
|  |  |  | Fluorescent light ballasts, lbs |  | 10.2 | 1.275 | 82.875 | 14.025 | 25.5 | 122.4
|  | 1.10.4.2 | Remove systems and components |  |  |  |  | 361.4476 |  | 361.4476 | 0 | 0 | 0 | 0 | 0 | 36482.794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168451.4192 | 0 | 168451.4192
1. Clean waste packaged in 30 cu. yd. containers
2. Productivity factors are included in the rates, unless otherwise specified.
|  | 1.10.4.2.1 | Remove piping |  |  |  | A | 203.0905 | 1 | 203.0905 | 0 |  |  |  |  | 614.944 |  |  | 0 |  |  |  |  | 2839.3711 |  | 2839.3711
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | 0 - 2" pipe, clean |  |  | 2337 |  | 72.447 | 0% | 72.447 | 0.089441 | 0.013333 | crew hrs/ft | 31.16 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 2 - 3.5" pipe, clean |  |  | 1194 |  | 103.878 | 0% | 103.878 | 0.12824 | 0.017667 | crew hrs/ft | 21.094 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 4 - 6" pipe, clean |  |  | 1155 |  | 277.2 | 0% | 277.2 | 0.34222 | 0.10667 | crew hrs/ft | 123.2 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | 8 - 14" pipe, clean |  |  | 151 |  | 161.419 | 0% | 161.419 | 0.19928 | 0.178 | crew hrs/ft | 26.878 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | Excavate buried pipe - assume 4' wide & 4' deep |  |  | 128 |  |  | 0% | 0 |  | 0.01 | crew hr/cu. yd. | 0.75852 | UCF 12 - excavate below grade structures
[11 empty] | 614.944 | 0.75919 |  |  | 203.0905
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 614.944 | 0.75919 | 0 | 379.5951 | 2459.776 | 2839.3711
|  | 1.10.4.2.2 | Remove ventilation |  |  |  | A | 69.82 | 1 | 69.82 | 0 |  |  |  |  | 677.85 |  |  | 0 |  |  |  |  | 3129.8259 |  | 3129.8259
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | HVAC equipment |  | 10 |  |  | 315 | 0% | 315 | 0.38889 | 4 | crew hrs/comp | 40 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | HVAC duct |  |  | 497 |  | 725.7 | 50% | 362.85 | 0.44796 | 0.06 | crew hrs/ft | 29.82 | UCF 69 - Remove Ductwork
[11 empty] | 677.85 | 0.83685 |  |  | 69.82
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 677.85 | 0.83685 | 0 | 418.4259 | 2711.4 | 3129.8259
|  | 1.10.4.2.3 | Remove large equipment |  |  |  | A | 88.537 | 1 | 88.537 | 0 |  |  |  |  | 35190 |  |  | 0 |  |  |  |  | 162482.2222 |  | 162482.2222
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove tanks, 4k - 15k gals |  | 2 |  |  | 2010 | 0% | 2010 | 2.4815 | 27 | crew hrs/comp | 54 | UCF 52 - Tanks 4k - 15k gals.
|  |  | Clean | Excavate buried tanks |  |  |  |  | 32500 | 0% | 32500 | 40.1235 | 0.01 | crew hr/cu. yd. | 12.037 | UCF 12 - excavate below grade structures
|  |  | Clean | Miscellaneous equipment |  | 9 |  |  | 680 | 0% | 680 | 0.83951 | 2.5 | crew hrs/comp | 22.5 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 35190 | 43.4444 |  |  | 88.537
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 35190 | 43.4444 | 0 | 21722.2222 | 140760 | 162482.2222
|  | 1.10.4.3 | Final Survey of Structure |  |  |  | A | 320 | 1.595 | 510.4 | 0 | [7 empty] | 0 | [6 empty] | 0 |  | 18.9656 | /sq ft
|  |  |  | Estimated Duration | 320 | hrs
| 1.11 | Demolition Readiness Review (Labor costs included in Undistributed costs) |  |  |  |  | B | 80 | 1 | 80 | 0 | [7 empty] | 0 | [6 empty] | 0
| 1.12 | Remove building (Labor costs included in Undistributed costs) | [5 empty] | 3373.7492 |  | 3373.7492 | 0 | 168 | 19591.0394 | 0 | 0 | 404711.66 | 0 | 650022.1 | 0 | 8959.44 | 161340.2496 | 0 | 0 | 1846042.0946 | 0 | 2666363.8842
|  | 1.12.1 | G Wing |  |  |  |  | 940.824 |  | 940.824 | 0 | 0 | 0 | 0 | 0 | 155582.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719688.4619 | 0 | 719688.4619 |  | 41.5906 |  | 10.1343
|  | 1.12.1.1 | Remove Interior walls |  |  |  |  | 112.8178 |  | 112.8178 | 0 | 0 | 0 | 0 | 0 | 24749.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108254.7921 | 0 | 108254.7921
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
3. For building removal use 2009 Means pg 28, 02 41 19.16 1450, 70 c. f. per day. This rate assumes a crew of 4 laborers and hand tools. This rate is assumed to be doubled for demolition using an excavator, not hand tools.
|  | 1.12.1.1.1 | Ground floor |  |  |  | A | 71.8341 | 1 | 71.8341 | 0 |  |  |  |  | 15758.6 |  |  | 0 |  |  |  |  | 68926.5937 |  | 68926.5937
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove concrete block |  |  |  | 11072 | 1605440 | -30% | 14393.6 | 40.136 | 50 | cu. yd./day | 65.6119 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove brick |  |  |  | 791 | 114695 | -30% | 1028.3 | 2.8674 | 50 | cu. yd./day | 4.6874 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Gypsum wall |  |  |  | 259 |  | -30% | 336.7 | 0.41568 | 50 | cu. yd./day | 1.5348 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 12122 | 1720135 |  | 15758.6 | 43.4191 |  |  | 71.8341
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 15758.6 | 1720135 | 43.4191 | 0 | 21709.527 | 47217.0667 | 68926.5937
|  | 1.12.1.1.2 | Second floor |  |  |  | A | 40.9837 | 1 | 40.9837 | 0 |  |  |  |  | 8990.8 |  |  | 0 |  |  |  |  | 39328.1985 |  | 39328.1985
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove concrete block |  |  |  | 6758 | 979910 | -30% | 8785.4 | 24.4977 | 50 | cu. yd./day | 40.0474 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Gypsum wall |  |  |  | 158 |  | -30% | 205.4 | 0.25358 | 50 | cu. yd./day | 0.9363 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 6916 | 979910 |  | 8990.8 | 24.7513 |  |  | 40.9837
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 8990.8 | 979910 | 24.7513 | 0 | 12375.6651 | 26952.5333 | 39328.1985
|  | 1.12.1.2 | Remove 212 G Wing |  |  |  | A | 828.0062 | 1 | 828.0062 | 0 |  |  |  |  | 130832.65 |  |  | 0 |  |  |  |  | 611433.6697 |  | 611433.6697
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Width | Depth | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove brick |  |  |  | 13079 | 1896455 | -30% | 17002.7 | 47.4114 | 50 | cu. yd./day | 77.5052 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  | 21219 | 3076755 | -30% | 27584.7 | 76.9189 | 50 | cu. yd./day | 125.7422 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 43923.5 | 6588525 | -30% | 57100.55 | 164.7131 | 50 | cu. yd./day | 260.2874 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  | 14823 | 2223450 | -30% | 19269.9 | 55.5862 | 50 | cu. yd./day | 87.84 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove structural steel |  |  |  |  | 661766 | 0% | 0 | 16.5442 | 0.7 | crew hr/ton | 231.6181 | UCF 8 - structural steel
|  |  | Clean | Gypsum wall | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove insulation |  |  |  | 7147 |  | -30% | 9291.1 | 11.4705 | 50 | cu. yd./day | 42.3526 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove metal deck |  |  |  | 449 |  | -30% | 583.7 | 0.72062 | 50 | cu. yd./day | 2.6607 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 130832.65 | 373.3649 |  |  | 828.0062
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 130832.65 | 14446951 | 373.3649 | 0 | 186682.4431 | 424751.2267 | 611433.6697
|  | 1.12.2 | H Wing |  |  |  |  | 733.3896 |  | 733.3896 | 0 | 0 | 0 | 0 | 0 | 112611.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482553.5581 | 0 | 482553.5581 |  | 10.5427 |  | 2.3853
|  | 1.12.2.1 | Remove Interior walls |  |  |  |  | 69.5941 |  | 69.5941 | 0 | 0 | 0 | 0 | 0 | 15267.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66696.1333 | 0 | 66696.1333
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
3. For building removal use 2009 Means pg 28, 02 41 19.16 1450, 70 c. f. per day. This rate assumes a crew of 4 laborers and hand tools. This rate is assumed to be doubled for demolition using an excavator, not hand tools.
|  | 1.12.2.1.1 | Ground floor |  |  |  | A | 50.6844 | 1 | 50.6844 | 0 |  |  |  |  | 11118.9 |  |  | 0 |  |  |  |  | 48573.9125 |  | 48573.9125
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove concrete block |  |  |  | 7702 | 1116790 | -30% | 10012.6 | 27.9198 | 50 | cu. yd./day | 45.6415 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 851 | 123395 | -30% | 1106.3 | 3.0849 | 50 | cu. yd./day | 5.043 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Gypsum wall | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 8553 | 1240185 |  | 11118.9 | 31.0046 |  |  | 50.6844
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 11118.9 | 1240185 | 31.0046 | 0 | 15502.3125 | 33071.6 | 48573.9125
|  | 1.12.2.1.2 | Second floor |  |  |  | A | 18.9096 | 1 | 18.9096 | 0 |  |  |  |  | 4148.3 |  |  | 0 |  |  |  |  | 18122.2208 |  | 18122.2208
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove concrete block |  |  |  | 3191 | 462695 | -30% | 4148.3 | 11.5674 | 50 | cu. yd./day | 18.9096 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Gypsum wall | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 3191 | 462695 |  | 4148.3 | 11.5674 |  |  | 18.9096
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 4148.3 | 462695 | 11.5674 | 0 | 5783.6875 | 12338.5333 | 18122.2208
|  | 1.12.2.2 | Remove 212 H Wing |  |  |  | A | 663.7955 | 1 | 663.7955 | 0 |  |  |  |  | 97344 |  |  | 0 |  |  |  |  | 415857.4247 |  | 415857.4247
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Width | Depth | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove brick |  |  |  | 116 | 16820 | -30% | 150.8 | 0.4205 | 50 | cu. yd./day | 0.68741 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 41565 | 6234750 | -30% | 54034.5 | 155.8688 | 50 | cu. yd./day | 246.3111 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  | 23605 | 3540750 | -30% | 30686.5 | 88.5187 | 50 | cu. yd./day | 139.8815 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove structural steel |  |  |  |  | 628749 | 0% | 0 | 15.7187 | 0.7 | crew hr/ton | 220.0622 | UCF 8 - structural steel
|  |  | Clean | Wood wall |  |  |  | 977 |  | -30% | 1270.1 | 1.568 | 50 | cu. yd./day | 5.7896 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove insulation |  |  |  | 8503 |  | -30% | 11053.9 | 13.6468 | 50 | cu. yd./day | 50.3881 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove metal deck |  |  |  | 114 |  | -30% | 148.2 | 0.18296 | 50 | cu. yd./day | 0.67556 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 97344 | 275.9245 |  |  | 663.7955
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 97344 | 10421069 | 275.9245 | 0 | 137962.2514 | 277895.1733 | 415857.4247
|  | 1.12.3 | F Wing |  |  |  |  | 1599.4604 |  | 1599.4604 | 0 | 168 | 19591.0394 | 0 | 0 | 118795.9 | 0 | 650022.1 | 0 | 8959.44 | 161340.2496 | 0 | 0 | 561809.5984 | 0 | 1382131.388 |  | 5.0638 |  | 1.5309
|  | 1.12.3.1 | Remove Hot Cells (Labor costs included in Undistributed costs) |  |  |  |  | 1063.284 |  | 1063.284 | 0 | 168 | 19591.0394 | 0 | 0 | 8782 | 0 | 650022.1 | 0 | 8959.44 | 161340.2496 | 0 | 0 | 77184.5178 | 0 | 897506.3074
|  |  | Assumptions: |  |  |  |  | Clean |  | 965.284 | [17 empty] | 9.1163 | /sqft | 0.12221
|  |  | 1. All waste will be disposed of at the local landfill - considered a controlled landfill |  |  |  |  | LLW |  | 10 | [17 empty] | 0.094442 | /sqft |  |  | 0.0023379
|  |  | 2. Productivity factors are included in the rates, unless otherwise specified. |  |  |  |  | Hazardous |  | 88 | [17 empty] | 0.83109 | /sqft |  | 0.27263
3. For building removal use 2009 Means pg 28, 02 41 19.16 1450, 70 c. f. per day. This rate assumes a crew of 4 laborers and hand tools. This rate is assumed to be doubled for demolition using an excavator, not hand tools.
4. Truck shipments are limited to 40,000 lbs.
5. Concrete density = 150lbs/cu.ft., Block density = 145lbs/cu.ft. & Magnitite Concrete = 232lbs./cu.ft.
6. Lead glass windows are assumed to weigh 6,000 lbs ea. They will be packaged in B-25 containers for transport. Each window will be disposed of as hazardous waste at $0.50 per lb.
7. Fluid in the Lead glass windows has a density of 19.2 lbs / gallon(Tech Sheets from Chemtura, 07/03/08). The fluid will be packaged in 55 gallon drums for transport. The fluid will be disposed of as hazardous waste at $0.50 per lb.
8. Magnitite concrete will by segmented into approximately 20,000 lb blocks, (6'x5') by using diamond wire saw. Blocks will be shipped to the controlled landfill, 2 blocks per shipment.
9. Diamond wire cutting is approximately $79.30/cu. ft. (see calculation). This cost includes equipment and labor, from Bluegrass.
10. Density of lead glass window is 143 lbs/cu. ft. from the bldg 200 estimate.
|  | 1.12.3.1.1 | Hot Cells - Diamond wire cutting |  |  |  | A | 426.244 | 1 | 426.244 | 0 |  |  |  |  | 8197 |  | 650022.1 | 0 |  |  |  |  | 74483.4067 |  | 724505.5067
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Gallons | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | Containers
|  |  | Clean | Remove magnitite concrete |  |  |  | 8197 | 1901704 | 0% | 8197 | 47.5426 | 0.052 | crew hrs/cu ft | 426.244 | See calculation for diamond wire cutting
[9 empty] | 1901704 |  | 8197 | 47.5426 |  |  | 426.244
[12 empty] | Diamond Wire | Diamond Wire
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $ | cutting $/cuft | cutting
|  |  |  | Clean | 8197 | 1901704 | 47.5426 | 0 | 23771.3 | 50712.1067 | 74483.4067 | 79.3 | 650022.1
|  | 1.12.3.1.2 | Hot Cell |  |  |  | A | 637.04 | 1 | 637.04 | 0 | 168 | 19591.0394 |  |  | 585 |  | 0 | 0 | 8959.44 | 161340.2496 |  |  | 2701.1111 |  | 173000.8007
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory | Area, sq. ft. | Number | Gallons | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | Containers
|  |  | Clean | Remove metal liner | 5938 |  |  | 245 |  | 0% | 245 | 0.30247 | 0.08 | hrs/Sq. Ft. | 475.04 | UCF 1 - Clean steel liner removal
|  |  | Contaminated | Plexiglass |  | 5 |  | 168 |  | 0% | 168 | 1.75 | 2 | hrs/window | 10 | Estimated
|  |  | Clean | Remove steel doors |  | 8 |  | 340 |  | 0% | 340 | 0.41975 | 8 | hrs/door | 64 | Estimated
|  |  | Hazardous | Remove fluid from lead windows |  | 11 | 2528.24 | 18911.2352 | 48542.208 | 0% | 18911.2352 | 882.5856 | 4 | hrs/window | 44 | Estimated
|  |  | Hazardous | Lead glass windows |  | 11 |  | 679.8042 | 97212 | 0% | 679.8042 | 9.7212 | 4 | hrs/window | 44 | Estimated
[9 empty] | 145754.208 |  | 20344.0394 | 894.779 |  |  | 637.04
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 585 | 0 | 0.72222 | 0 | 361.1111 | 2340 | 2701.1111
|  |  |  | Contaminated | 168 | 0 | 1.75 | 0 | 0 | 8959.44 | 8959.44 | Packaged in B-25 boxes
|  |  |  | Hazardous - L | 18911.2352 | 48542.208 | 882.5856 | 57368.064 | 9708.4416 | 24271.104 | 91347.6096
|  |  |  | Hazardous - W | 679.8042 | 97212 | 9.7212 | 13609.68 | 7776.96 | 48606 | 69992.64
|  | 1.12.3.2 | Remove Interior walls |  |  |  |  | 51.363 |  | 51.363 | 0 | 0 | 0 | 0 | 0 | 9208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39723.2994 | 0 | 39723.2994
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
3. For building removal use 2009 Means pg 28, 02 41 19.16 1450, 70 c. f. per day. This rate assumes a crew of 4 laborers and hand tools. This rate is assumed to be doubled for demolition using an excavator, not hand tools.
|  | 1.12.3.2.1 | Ground floor |  |  |  | A | 36.3111 | 1 | 36.3111 | 0 |  |  |  |  | 5906 |  |  | 0 |  |  |  |  | 25298.216 |  | 25298.216
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | Containers
|  |  | Clean | Remove concrete block |  |  |  | 4440 | 643800 | -30% | 5772 | 16.095 | 50 | cu. yd./day | 26.3111 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Plexiglass |  | 5 |  | 134 |  | 0% | 134 | 0.16543 | 2 | hrs/window | 10 | Estimated
|  |  | Clean | Gypsum wall | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 4574 | 643800 |  | 5906 | 16.2604 |  |  | 36.3111
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 5906 | 643800 | 16.2604 | 0 | 8130.216 | 17168 | 25298.216
|  | 1.12.3.2.2 | Second floor |  |  |  | A | 15.0519 | 1 | 15.0519 | 0 |  |  |  |  | 3302 |  |  | 0 |  |  |  |  | 14425.0833 |  | 14425.0833
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove concrete block |  |  |  | 2540 | 368300 | -30% | 3302 | 9.2075 | 50 | cu. yd./day | 15.0519 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Gypsum wall | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 2540 | 368300 |  | 3302 | 9.2075 |  |  | 15.0519
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 3302 | 368300 | 9.2075 | 0 | 4603.75 | 9821.3333 | 14425.0833
|  | 1.12.3.3 | Remove 212 F Wing |  |  |  | A | 484.8135 | 1 | 484.8135 | 0 |  |  |  |  | 100805.9 |  |  | 0 |  |  |  |  | 444901.7812 |  | 444901.7812
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Width | Depth | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove brick |  |  |  | 2933 | 425285 | -30% | 3812.9 | 10.6321 | 50 | cu. yd./day | 17.3807 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  | 6840 | 991800 | -30% | 8892 | 24.795 | 50 | cu. yd./day | 40.5333 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 29557 | 4433550 | -30% | 38424.1 | 110.8388 | 50 | cu. yd./day | 175.1526 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  | 35930 | 5389500 | -30% | 46709 | 134.7375 | 50 | cu. yd./day | 212.9185 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove structural steel |  |  |  |  | 72284 | 0% | 0 | 1.8071 | 0.7 | crew hr/ton | 25.2994 | UCF 8 - structural steel
|  |  | Clean | Wood wall | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove insulation |  |  |  | 2283 |  | -30% | 2967.9 | 3.6641 | 50 | cu. yd./day | 13.5289 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove metal deck | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 100805.9 | 286.4745 |  |  | 484.8135
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 100805.9 | 11312419 | 286.4745 | 0 | 143237.2745 | 301664.5067 | 444901.7812
|  | 1.12.4 | Fallout Shelter |  |  |  |  | 100.0752 |  | 100.0752 | 0 | 0 | 0 | 0 | 0 | 17722.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81990.4764 | 0 | 81990.4764 |  | 3.7186 |  | 0.97035
|  | 1.12.4.1 | Remove Interior walls |  |  |  |  | 4.6679 |  | 4.6679 | 0 | 0 | 0 | 0 | 0 | 1024.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4367.5872 | 0 | 4367.5872
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
3. For building removal use 2009 Means pg 28, 02 41 19.16 1450, 70 c. f. per day. This rate assumes a crew of 4 laborers and hand tools. This rate is assumed to be doubled for demolition using an excavator, not hand tools.
|  | 1.12.4.1.1 | Ground floor |  |  |  | A | 4.6679 | 1 | 4.6679 | 0 |  |  |  |  | 1024.01 |  |  | 0 |  |  |  |  | 4367.5872 |  | 4367.5872
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove concrete block |  |  |  | 290 | 42050 | -30% | 377 | 1.0513 | 50 | cu. yd./day | 1.7185 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 379.7 | 56955 | -30% | 493.61 | 1.4239 | 50 | cu. yd./day | 2.2501 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Metal wall |  |  |  | 19 |  | -30% | 24.7 | 0.030494 | 50 | cu. yd./day | 0.11259 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove insulation |  |  |  | 23 |  | -30% | 29.9 | 0.036914 | 50 | cu. yd./day | 0.1363 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Acoustical tile |  |  |  | 76 |  | -30% | 98.8 | 0.12198 | 50 | cu. yd./day | 0.45037 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 787.7 | 99005 |  | 1024.01 | 2.6645 |  |  | 4.6679
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 1024.01 | 99005 | 2.6645 | 0 | 1332.2539 | 3035.3333 | 4367.5872
|  | 1.12.4.2 | Remove Fallout Shelter |  |  |  | A | 95.4074 | 1 | 95.4074 | 0 |  |  |  |  | 16698.5 |  |  | 0 |  |  |  |  | 77622.8892 |  | 77622.8892
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Width | Depth | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove brick |  |  |  | 0 | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  | 0 | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 3713 | 556950 | -30% | 4826.9 | 13.9238 | 50 | cu. yd./day | 22.003 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  | 9132 | 1369800 | -30% | 11871.6 | 34.245 | 50 | cu. yd./day | 54.1156 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove structural steel |  |  |  |  | 55111 | 0% | 0 | 1.3778 | 0.7 | crew hr/ton | 19.2889 | UCF 8 - structural steel
|  |  | Clean | Gypsum wall | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove insulation |  |  |  | 0 |  | -30% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove metal deck |  |  |  | 0 |  | -30% | 0 | 0 | 50 | cu. yd./day | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 16698.5 | 49.5465 |  |  | 95.4074
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 16698.5 | 1981861 | 49.5465 | 0 | 24773.2625 | 52849.6267 | 77622.8892
| 1.13 | Final release survey - ORISE (Labor costs included in Undistributed costs) |  |  |  |  | B | 80 | 1 | 80 | 0 | [7 empty] | 0 | [6 empty] | 0
| 1.14 | Backfill, grade and seed (Labor costs included in Undistributed costs) |  |  |  |  | A | 51.3564 | 1 | 51.3564 | 0 | [6 empty] | 27861.4222 | 0 | [6 empty] | 27861.4222
|  |  | Assumptions: | [12 empty] | Grade and seed |  | 30121.819 | [6 empty] | 0.36941 | /sqft
|  |  | 1. Grade and see area 104' x 93', plus 10%. | [12 empty] | Backfill |  | 4731.6998 | [6 empty] | 0.1828 | /cuft
2. Productivity factors are included in the rates, unless otherwise specified.
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Width | Depth | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Grade |  |  |  | 81540.8 |  | 0% | 0 | 0 | 18000 | sq ft/8 hr day | 36.2404 | 2009 RS Means 31 22 16.10 0100
|  |  |  | Seed |  |  |  | 81540.8 |  | 0% | 0 | 0 | 80100 | sq ft/8 hr day | 8.1439 | 2009 RS Means 32 92 19.13 1000
|  |  |  | Backfill |  |  |  |  | 25884 | 0% | 25884 | 0 | 1100 | cu. yd./day | 6.9721 | 2009 RS Means 31 23 23.14 2000
|  |  |  | Gravel base layer | [5 empty] | 0% | 0 | 0 | 4200 | sq yd/8 hr day | 0 | 2009 RS Means 32 11 23.23 0300
|  |  |  | Pavement - binder course - 4" | [5 empty] | 0% | 0 | 0 | 10800 | sq ft/8 hr day | 0 | 2009 RS Means 32 12 16.14 0600
|  |  |  | Pavement - finish course - 2" | [5 empty] | 0% | 0 | 0 | 34000 | sq ft/8 hr day | 0 | 2009 RS Means 32 12 16.14 0900
[11 empty] | 25884 | 0 |  |  | 51.3564
|  |  |  | Waste | Area, sq. ft. | Installation, $/SF | Material, $/SY | Equipment, $/SY | Volume, cu. Ft. | Cost, $/cu. yd. | Total, $
|  |  |  | Seed and equipment | 81540.8 |  | 0.18 | 0.07 |  |  | 2265.0222 | 2009 RS Means 32 92 19.13 1000
|  |  |  | Structural fill |  |  |  |  | 25884 | 26.7 | 25596.4 | 2009 RS Means 31 05 16.10 0600 + 0900 & 31 23 23.24 0400
27861.4222
| 1.15 | Site Demobilization (Labor costs included in Undistributed costs) | [5 empty] | 80 |  |  | 1920 | [6 empty] | 9600 | 0 | [6 empty] | 9600
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Project Manager |  | 0 | 0
|  |  | 1 | Project Safety Manager |  | 0 | 0
|  |  | 1 | Project Specialist |  | 0 | 0
|  |  | 1 | Health Physicist |  | 0 | 0
|  |  | 1 | Chief HP Tech |  | 0 | 0
|  |  | 1 | Building Maintenance |  | 0 | 0
|  |  | 1 | Secretary |  | 0 | 0
|  |  | 1 | Project Control Specialist |  | 0 | 0
|  |  | 4 | HP Tech |  | 0 | 0
|  |  | 12 | Decon Techs |  | 0 | 0
|  |  | 24 |  |  |  | 0
|  |  | Return rented equipment, including trailers |  |  | 24 | hr
|  |  | Dispose of unused material |  |  | 24 | hr
|  |  | General site cleanup |  |  | 24 | hr
|  |  | Travel home |  |  | 8
[6 empty] | 80 | hr
|  |  | Total Cost = |  | 80 | x | 0 | 0
|  |  | Travel cost = |  | 24 | x | 400 | 9600
| 1.16 | Final Project Report - Offsite |  |  |  |  | A | 240 | 1.1 | 264 | 440 | [7 empty] | 41360 | [6 empty] | 41360
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 85 | 160 | 1.1 | 29920 | 352
|  |  | Project Manager |  |  | 1 | 130 | 80 | 1.1 | 11440 | 88
[6 empty] | 3 |  | 240 |  | 41360 | 440
| Staff |  | Number | Rate
| Decon Techs |  | 12 | 56.555 | 678.66
Remove systems and components
|  |  |  | Clean | [23 empty] | 37.8194 | /sq ft | 3.107
|  |  |  | LLW | [23 empty] | 15.9882 | /sq ft |  |  | 0.17582
|  |  |  | Hazardous | [23 empty] | 0 | /sq ft |  | 0
|  |  |  | Mixed | [23 empty] | 0 | /sq ft |  |  |  | 0
|  |  |  | Remove asbestos pipe insulation | [23 empty] | 74.6526 | /foot | 0.13974 | cu. ft./ft
|  |  |  | Remove asbestos tile | [23 empty] | 2.036 | /sq ft | 0.064222 | cu. ft./sq.ft
|  |  |  | Decontaminate Structure | [23 empty] | 13.6252 | /sq ft |  |  | 0.0097637
Hot Cell
|  |  |  | Clean | [23 empty] | 9.1163 |  | 0.12221
|  |  |  | contaminated | [23 empty] | 4.7479 |  |  |  | 0.0025425
|  |  |  | Hazardous | [23 empty] | 0.83109 |  |  | 0.27263
|  |  |  | Final Survey of Structure | [23 empty] | 16.9579 | /sq ft
|  |  |  | Remove building | [23 empty] | 15.2289 | /sq ft | 3.7552

## Building 3 - 2010 (hidden)
[15 empty] | Mixed | Clean | Lead | Materials, |  |  | Hazardous |  | Mixed | Clean | Lead
Total Floor area |  | 65787 | [5 empty] | Uncorrected Duration |  | Adjusted |  | LSA Waste | Hazardous | Ballast | Waste | Waste | Waste | Consumables, |  | LSA Waste | Waste | >LSA Waste | Waste | Waste | Waste |  |  |  |  | Clean | Hazardous | LLW | Mixed
[7 empty] | Crew | (No. of Hours) | Prod. Factor | Duration | Man-hours | Disp. Vol (cf) | Waste Vol (cf) | Volume (cf) | Volume (cf) | Volume (cf) | Volume (cf) | & Equipment | Labor Cost | Cost | Cost | Cost | Cost | Cost | Cost | Total Cost |  | Removal |  | Waste | Waste | Waste | Waste
[28 empty] | Unit Rate |  | Volume | Volume | Volume | Volume
| Grand Total Building 200 MA/MB wings | [24 empty] | 28790464.3038
| Contingency = |  | 40% | [22 empty] | 8225846.9439
2 | Total Building 200 MA/MB wings | [24 empty] | 20564617.3599
| ANL Oversight @ 24% | [22 empty] | 24% |  | 3980248.5213
ANL Tax | General and Administration | [22 empty] | 2.9% |  | 99522.2593
ANL Tax | IGPP/IGPE | [22 empty] | 2.7% |  | 90222.6438
ANL Tax | Service Center | [22 empty] | 18.5% |  | 2414813.2389 | On total
ANL Tax | Material and Subcontracts Tax | [22 empty] | 7.1% |  | 926766.162 | On total
2 | Building 200 | [9 empty] | 108921.1429 | 8626.852 | 69936 | 60 | 0 | 150531.9294 | 9.6 | 3564583.3316 | 7723690 | 460070.0172 | 505924.3636 | 0 | 0 | 795287.2222 | 3489.6 | 13053044.5346
UNDISTRIBUTED COSTS | [10 empty] | 102857.1429 | [6 empty] | 1690181.5983 | 7569690 | 0 | 0 | 0 | 0 | 0 |  | 9259871.5983
|  | Project duration = |  |  | 830 | days/7days/wk = | 118.5714 | See Project Schedule - Starts with Site Mobilization and ends with Site Demobilization
[5 empty] | 592.8571 | working days
|  | Labor cost = |  | 2752298.2857 | (Used to determine small tool costs and HP Supplies)
| 2.1 | Project Management | [8 empty] | 56914.2857 | [7 empty] | 4125621.7143 | [6 empty] | 4125621.7143
|  | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
|  | Project Manager |  |  | 1 | 130 | 592.8571 | 100% | 616571.4286 | 4742.8571
|  | Project Safety Manager |  |  | 1 | 100 | 592.8571 | 100% | 474285.7143 | 4742.8571
|  | Project Specialist |  |  | 1 | 85 | 592.8571 | 100% | 403142.8571 | 4742.8571
|  | Health Physicist |  |  | 1 | 120 | 592.8571 | 100% | 569142.8571 | 4742.8571
|  | Chief HP Tech |  |  | 1 | 57.77 | 592.8571 | 100% | 273994.8571 | 4742.8571
|  | Building Maintenance |  |  | 1 | 51.38 | 592.8571 | 100% | 243688 | 4742.8571
|  | Secretary |  |  | 1 | 31.79 | 592.8571 | 100% | 150775.4286 | 4742.8571
|  | Project Control Specialist |  |  | 1 | 97.64 | 592.8571 | 100% | 463092.5714 | 4742.8571
|  | HP Tech |  |  | 4 | 49.07 | 592.8571 | 100% | 930928 | 18971.4286
[5 empty] | 12 |  |  |  | 4125621.7143 | 56914.2857
| 2.2 | Project Management Per Diem | [16 empty] | 845770 | [6 empty] | 845770
[6 empty] | Per Diem | Number of
|  | Staff |  |  | Number | Rate, $/day | Days | Total
|  | Project Manager |  |  | 1 | 161 | 830 | 133630
|  | Project Safety Manager |  |  | 1 | 161 | 830 | 133630
|  | Project Specialist |  |  | 1 | 161 | 830 | 133630
|  | Health Physicist |  |  | 1 | 161 | 830 | 133630
|  | Chief HP Tech |  |  | 1 | 75 | 830 | 62250
|  | HP Tech |  |  | 4 | 75 | 830 | 249000
[5 empty] | 9 |  |  | 845770
| 2.3 | Crew cost - 4 crews from mobilization through final survey | [8 empty] | 34971.4286 | [7 empty] | 1977809.1429 | [6 empty] | 1977809.1429
|  | Duration | 510 | days/7days/wk = | 72.8571 | 364.2857 | working days | See Project Schedule - Starts with Site Mobilization and ends with Final Survey
|  | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
|  | Decon Techs |  |  | 12 | 56.555 | 364.2857 | 100% | 1977809.1429 | 34971.4286
[5 empty] | 12 |  |  |  | 1977809.1429 | 34971.4286
| 2.4 | Crew cost - 2 crews from final survey through site demobilization | [8 empty] | 10971.4286 | [7 empty] | 620489.1429 | [6 empty] | 620489.1429
|  | Duration | 320 | days/7days/wk = | 45.7143 | 228.5714 | working days | See Project Schedule - Starts with Final Survey and ends with Site Demobilization
|  | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
|  | Decon Techs |  |  | 6 | 56.555 | 228.5714 | 100% | 620489.1429 | 10971.4286
[5 empty] | 6 |  |  |  | 620489.1429 | 10971.4286
| 2.5 | Equipment & Materials | [15 empty] | 1690181.5983 | [7 empty] | 1690181.5983
|  | Equipment |  |  | Quantity | Rate | Cost
|  | HEPA filter systems |  |  | 2 | 3598.14 | 7196.28
|  | Replacement filters |  |  | 24 | 581.07 | 13945.68
|  | Respirator |  |  | 30 | 259 | 7770
|  | Rad/Vac wet-dry high eff. vacuum |  |  | 4 | 3879 | 15516
|  | Rad/Vac wet-dry high eff. vacuum filters |  |  | 10 | 412 | 4120
|  | Reciprocating Saws |  |  | 6 | 1252.26 | 7513.56
|  | Pneumatic chipping hammers |  |  | 2 | 1606.71 | 3213.42
|  | Chipping hammer blades |  |  | 20 | 27.42 | 548.4
|  | Purchase an air compressor: |  |  | 4 | 1723.44 | 6893.76
|  | Jackhammer |  |  | 2 | 1417.11 | 2834.22
|  | Jackhammer Chisels |  |  | 20 | 24.35 | 487
|  | Safety glasses |  |  | 150 | 8.6 | 1290
|  | Fall protection - harness |  |  | 12 | 208 | 2496
|  | Fall protection - lanyard |  |  | 12 | 367 | 4404
|  | Hardhats |  |  | 40 | 35.5 | 1420
|  | Hard hat hearing protection |  |  | 40 | 37.6 | 1504
|  | Trailer rental |  |  | 2 | 416 | 22688.424
|  | Phone and computer hook-up |  |  | 1 | 250 | 6817.4351
|  | Industrial hygiene instrumentation, calibration and hygienists - 1% of total activity $. |  |  |  |  | 63914.7122
|  | Tractor loader, wheeled |  |  | 1 | 7160.5905 | 175740.6999
|  | Wheeled Skid steer with conc. Hammer |  |  | 2 | 4421.3693 | 49099.4247
|  | Excavator |  |  | 2 | 28738.389 | 105750.725
|  | Floor Shaver |  |  | 2 | 8000 | 88840.2147
|  | Wall Shaver |  |  | 2 | 15000 | 166575.4025
|  | Core Drill & Bits |  |  | 1 | 10000 | 10000
|  | Man lift |  |  | 2 | 4727.44 | 151282.2219
|  | Crane rental for building removal |  |  | 1 | 15600 | 28702.2232
950563.8033
|  | Consumables |  | Quantity |  | Duration |  | # workers | quantity | Unit Qty | Unit Cost | Cost
|  | Coveralls |  | 2 | /man/day | 592.8571 | days | 16 | 18971.4286 | 1 | 8.7 | 165051.4286 | 4 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Hoods |  | 0.5 | /man/day | 592.8571 | days | 16 | 4742.8571 | 1 | 0.93333 | 4426.6667 | 4 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Shoe covers |  | 4 | /man/day | 592.8571 | days | 16 | 37942.8571 | 1 | 0.37 | 14038.8571 | 4 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Latex gloves |  | 4 | /man/day | 592.8571 | days | 16 | 37942.8571 | 1 | 2 | 75885.7143 | 4 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Rubber overshoes |  | 0.01 | /man/day | 592.8571 | days | 16 | 94.8571 | 1 | 3 | 284.5714 | 4 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Gloves |  | 0.5 | /man/day | 592.8571 | days | 16 | 4742.8571 | 1 | 1.63 | 7730.8571 | 4 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Dosimeters |  | 1 | /man/year | 2.2802 | year | 24 | 54.7253 | 1 | 197.125 | 10787.7198
|  | TLDs |  | 1 | /man/mo | 27.3837 | month | 24 | 657.2088 | 1 | 3 | 1971.6265
|  | Bioassays |  | 2 | /man/year | 2.2802 | year | 24 | 109.4505 | 1 | 25 | 2736.2637
|  | (Bioassays for aver. crew & management) | [9 empty] | 282913.7053
|  | Small Tools - 2% of total labor costs = |  |  |  | 2752298.2857 | labor costs x | 2% | = | 55045.9657
|  | HP Equipment Replacement - 5% of total labor |  |  |  | 2752298.2857 | labor costs x | 5% | = | 137614.9143
|  | DGC OH &P on equipment and materials |  |  |  | 3300540.1219 |  | 8% | = | 264043.2098
ACTIVITIES | [7 empty] | 9395.9104 |  | 9663.3274 | 6064 | 8626.852 | 69936 | 60 | 0 | 150531.9294 | 9.6 | 1874401.7333 | 154000 | 460070.0172 | 505924.3636 | 0 | 0 | 795287.2222 | 3489.6 | 3793172.9363
| 2.6 | Procedure Development and Review - Offsite | [5 empty] | 320 | 1.1 | 352 | 616 | [7 empty] | 56320 | [6 empty] | 56320
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 85 | 240 | 1.1 | 44880 | 528
|  |  | Project Manager |  |  | 1 | 130 | 80 | 1.1 | 11440 | 88
[6 empty] | 3 |  | 320 |  | 56320 | 616
| 2.7 | Preparation of QA and Safety Documents - Offsite | [5 empty] | 320 | 1.1 | 352 | 616 | [7 empty] | 56320 | [6 empty] | 56320
|  |  | Staff |  |  | Number | Rate | Duration | PLF |  | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 85 | 240 | 1.1 |  | 44880 | 528
|  |  | Project Manager |  |  | 1 | 130 | 80 | 1.1 |  | 11440 | 88
[6 empty] | 3 |  | 320 |  |  | 56320 | 616
| 2.8 | Site Mobilization and General Employee Training (GET) | [5 empty] | 88 | 1 | 88 | 2472 | [6 empty] | 40800 | 0 | [6 empty] | 40800
|  | 2.8.1 | Site Mobilization |  |  |  |  | 48 |  |  | 1152 | [6 empty] | 9600 | 0 | [6 empty] | 9600
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Project Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Safety Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Health Physicist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Chief HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Building Maintenance |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Secretary |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Control Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 4 | HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 12 | Decon Techs |  | 0 | 0 | With Undistributed Costs
|  |  | 24 |  |  |  | 0
|  |  | Travel to site |  |  | 8 | hr
|  |  | Receipt of material and equipment |  |  | 16 | hr
|  |  | Staging of equipment |  |  | 8 | hr
|  |  | Set up office and amenities |  |  | 12 | hr
|  |  | Familiarize staff with facility |  |  | 4 | hr
[6 empty] | 48 | hr
|  |  | Labor Cost = |  | 48 | x | 0 | 0
|  |  | Travel cost = |  | 24 | x | 400 | 9600
|  | 2.8.2 | General Employee Training (All proj. manag. & 4 crews of 4) (1 HP Tech & 3 Decon Techs) |  |  |  |  | 40 | 1 |  | 1320 | [6 empty] | 31200 | 0 | [6 empty] | 31200
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Project Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Safety Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Health Physicist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Chief HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Building Maintenance |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Secretary |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Control Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 4 | HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 12 | Decon Techs |  | 0 | 0 | With Undistributed Costs
|  |  | 24 |  |  |  | 0
[8 empty] | Number | Test | Labor | Total
[7 empty] | Unit Cost | Required | Cost | Costs | Cost
|  |  | In-Vivo |  |  |  | 600 | 24 | 14400 |  | 14400
|  |  | In-Vitro |  |  |  | 350 | 24 | 8400 |  | 8400
|  |  | Physical @ |  | 4 | hour and | 150 | 24 | 3600 | 0 | 3600
|  |  | Resp. Tests |  | 1 | hour and | 50 | 24 | 1200 | 0 | 1200
|  |  | Resp Fit Tests |  | 1 | hour and | 25 | 24 | 600 | 0 | 600
|  |  | Blood Tests |  | 1 | hour and | 125 | 24 | 3000 | 0 | 3000
|  |  | OSHA recertification |  | 8 | hour |  |  |  | 0 | 0
|  |  | Site specific 1 week of training |  | 40 | hour |  |  |  | 0 | 0
[5 empty] | 55 |  |  |  | 31200 | 0 | 31200
| 2.9 | Decontamination Readiness Review |  |  |  |  | B | 80 | 1 | 80 | 0 | [7 empty] | 0 | [6 empty] | 0
| 2.1 | Site Preparation (Labor costs included in Undistributed costs) |  |  |  |  | B | 192 | 1.21 | 227.04 | 0 | 0 | 0 | 0 | 0 | 0 |  | 17000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 17000
|  | 2.10.1 | Initial Site Survey |  |  |  | B | 16 | 1.21 | 19.36 | 0 | [7 empty] | 0 | [6 empty] | 0
|  |  |  | Estimated Duration | 16 | hrs
|  | 2.10.2 | Setup work areas |  |  |  |  | 32 |  | 37.84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000 | 0 | [6 empty] | 1000
|  | 2.10.2.1 | Setup boundaries, install HEPA filters & seal off ventilation openings |  |  |  | B | 24 | 1.21 | 29.04 | 0 | 0 | 0 |  |  |  |  | 1000 | 0 | [6 empty] | 1000
(estimated)
|  | 2.10.2.2 | Establish staging area |  |  |  | B | 8 | 1.1 | 8.8 | 0 | 0 | 0 | [5 empty] | 0 | [6 empty] | 0
|  | 2.10.3 | Setup Rad. and Non-Rad. segregation and packaging stations |  |  |  | B | 40 | 1.1 | 44 | 0 |  |  |  | 0 |  |  | 1000 | 0 | [6 empty] | 1000
|  | 2.10.4 | Isolate MA/MB wings from rest of Bldg |  |  |  |  | 104 |  | 125.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
|  | 2.10.4.1 | Electrical |  |  |  | B | 24 | 1.21 | 29.04 | 0 |  |  |  | 0 |  |  | 5000 | 0 | [6 empty] | 5000
(new material allowance)
|  | 2.10.4.2 | Piping |  |  |  | B | 40 | 1.21 | 48.4 | 0 |  |  |  | 0 |  |  | 5000 | 0 | [6 empty] | 5000
|  | 2.10.4.3 | Seal accesses to M wing |  |  |  | B | 40 | 1.21 | 48.4 | 0 |  |  |  | 0 |  |  | 5000 | 0 | [6 empty] | 5000
| 2.11 | Decontaminate Cells (Labor costs included in Undistributed costs) | [5 empty] | 1542.7621 |  | 1542.7621 | 0 | 1007.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 53729.975 | 0 | 0 | 0 | 0 |  | 53729.975
Assumptions:
1. Productivity factors are included in the rates, unless otherwise specified.
2. Scabbled concrete volume will be increased 30% to account for packaging inefficiencies.
|  | 2.11.1 | Service Floor |  |  |  | A | 734.12 | 1 | 734.12 | 0 | 483.47 | [6 empty] | 0 | 25783.4551 | [5 empty] | 25783.4551
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Decon concrete floor surfaces - 1 inch deep |  |  |  | 1422 | 113.6 | -30% | 147.68 | 1.5383 | 0.16 | crew hr/sq. ft. | 227.52 | Average UCF 7 & 8 - Concrete surfaces 1" deep
|  |  |  | Decon M1 cell concrete floor surface - 6 inches deep |  |  |  | 238 | 119 | -30% | 154.7 | 1.6115 | 0.96 | crew hr/sq. ft. | 228.48 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
|  |  |  | Decon concrete wall and ceiling surfaces - 1/4 inch deep |  |  |  | 6953 | 139.3 | -30% | 181.09 | 1.8864 | 0.04 | crew hr/sq. ft. | 278.12 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 483.47 | 5.0361 |  |  | 734.12
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Contaminated |  | 483.47 | 5.0361 | 0 | 0 | 25783.4551 | 25783.4551
|  | 2.11.2 | Main Floor |  |  |  | A | 808.6421 | 1 | 808.6421 | 0 | 524.03 | [6 empty] | 0 | 27946.5199 | [5 empty] | 27946.5199
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Decon concrete floor surfaces - 1 inch deep |  |  |  | 2240.045 | 178.7 | -30% | 232.31 | 2.4199 | 0.16 | crew hr/sq. ft. | 358.4072 | Average UCF 7 & 8 - Concrete surfaces 1" deep
|  |  |  | Decon concrete wall and ceiling surfaces - 1/4 inch deep |  |  |  | 11255.8725 | 224.4 | -30% | 291.72 | 3.0388 | 0.04 | crew hr/sq. ft. | 450.2349 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 524.03 | 5.4586 |  |  | 808.6421
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Contaminated |  | 524.03 | 5.4586 | 0 | 0 | 27946.5199 | 27946.5199
| 2.12 | Remove Asbestos (Labor costs included in Undistributed costs) |  |  |  |  | A | 339.77 | 1.1 | 373.747 | 0 | 0 | 0 |  | 0 | 1995.9307 |  |  | 0 | 0 | 0 |  | 0 | 9215.7786 |  | 9215.7786
1. Productivity factors are included in the rates, unless otherwise specified.
2. Asbestos volume will be increased 30% to account for packaging inefficiencies.
3. Asbestos will be double bagged and disposed of at a controlled landfill licensed to accept ACM
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove asbestos pipe insulation |  |  | 2689 |  | 73.3313 | -30% | 95.3307 | 0.11769 | 0.11 | crew hrs/ft | 295.79 | 2009 mean, p33, 02 82 13.43 1200 with glove bags | [11 empty] | 82.1251 | /foot | 0.035452 | cu. ft./ft
|  |  | Clean | Remove asbestos tile |  |  |  | 14660 | 1462 | -30% | 1900.6 | 2.3464 | 0.003 | crew hrs/sq. ft. | 43.98 | 2009 mean, p33, 02 82 13.43 5000 | [11 empty] | 2.2398 | /sq ft | 0.12965 | cu. ft./sq.ft
|  |  | Clean | Remove carpet | [5 empty] | 0% | 0 | 0 | 0.0015 | crew hrs/sq. ft. | 0 | Productivity estimated at 2x that of VAT removal.
|  |  | Clean | Remove asbestos tile from Main floor | [5 empty] | 0% | 0 | 0 | 0.003 | crew hrs/sq. ft. | 0 | 2009 mean, p33, 02 82 13.43 5000
|  |  | Clean | Remove asbestos fire door | [5 empty] | 0% | 0 | 0 | 4 | crew hrs/comp | 0 | estimated
[11 empty] | 1995.9307 | 2.4641 |  |  | 339.77
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 1995.9307 | 2.4641 | 0 | 1232.056 | 7983.7226 | 9215.7786
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Fluorescent light ballasts, lbs |  | 0 | 0 | 0 | 0 | 0 | 0
| 2.13 | Remove systems and components (Labor costs included in Undistributed costs) | [5 empty] | 1591.3207 |  | 1591.3207 | 0 | 3535.276 | 0 | 60 | 0 | 2638.6725 | 9.6 | 0 | 0 | 188536.2691 | 720 | 0 | 0 | 12183.5002 | 3489.6 | 204929.3693 |  | 21.6932
|  |  | Assumptions: | [5 empty] | Clean | 809.3923 | [17 empty] | 8.3504 |  | 0.067919
|  |  | 1. Fluorescent lights have PCB containing ballasts | [5 empty] | LLW | 1182.2884 | [17 empty] | 12.1976 |  |  |  | 0.062637
|  |  | 2. Ballasts packaged in 55 gallon drums and disposed of as hazardous waste | [5 empty] | Hazardous | 25 | [17 empty] | 0.25792
|  |  | 3. Clean waste packaged in 30 cu. yd. containers | [5 empty] | Mixed | 0
4. Productivity factors are included in the rates, unless otherwise specified.
|  | 2.13.1 | Remove systems and components - general |  |  |  | A | 1530.391 | 1 | 1530.391 | 0 | 3535.276 |  | 60 | 0 | 2377.4615 | 9.6 |  | 0 | 188536.2691 | 720 |  | 0 | 10977.4148 | 3489.6 | 203723.2839
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | 0 - 2" pipe, clean |  |  | 12917 |  | 400.427 | 0% | 400.427 | 0.49435 | 0.013333 | crew hrs/ft | 172.2267 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 2 - 3.5" pipe, clean |  |  | 6 |  | 0.522 | 0% | 0.522 | 0.00064444 | 0.017667 | crew hrs/ft | 0.106 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Contaminated | 0 - 2" pipe, contam. |  |  | 2369 |  | 73.439 | 0% | 73.439 | 0.76499 | 0.018 | crew hrs/ft | 42.642 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
|  |  | Contaminated | 2 - 3.5" pipe, contam. |  |  | 171 |  | 14.877 | 0% | 14.877 | 0.15497 | 0.02385 | crew hrs/ft | 4.0784 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
|  |  | Contaminated | 4 - 6" pipe, contam. |  |  | 204 |  | 48.96 | 0% | 48.96 | 0.51 | 0.072 | crew hrs/ft | 14.688 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
|  |  | Clean | HVAC equipment |  | 1 |  |  | 54 | 0% | 54 | 0.066667 | 4 | crew hrs/comp | 4 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Contaminated | HVAC equipment |  | 1 |  |  | 240 | 0% | 240 | 2.5 | 7 | crew hrs/comp | 7 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | HVAC duct |  |  | 2.5 |  | 5.025 | 50% | 2.5125 | 0.0031019 | 0.06 | crew hrs/ft | 0.15 | UCF 69 - Remove Ductwork
|  |  | Clean | Miscellaneous equipment |  | 87 |  |  | 1870 | 0% | 1870 | 2.3086 | 2.5 | crew hrs/comp | 217.5 | UCF 64 - 300 to 1,000 lbs
|  |  | Contaminated | Miscellaneous equipment |  | 233 |  |  | 3158 | 0% | 3158 | 32.8958 | 4 | crew hrs/comp | 932 | UCF 64 - 300 to 1,000 lbs
|  |  | Lead | Lead bricks |  | 344 |  |  | 9.6 | 0% | 9.6 | 1.2 | 0.25 | crew hrs/comp | 86 | Estimated
|  |  | Clean | Fluorescent lights |  | 100 |  |  | 50 | 0% | 50 | 0.061728 | 0.25 | crew hrs/comp | 25 | Estimated
|  |  | Hazardous | Fluorescent light ballasts, lbs |  | 100 | 300 |  |  | 0% | 0 | 7.5 | 0.25 | crew hrs/comp | 25 | Estimated
[11 empty] | 5922.3375 | 48.4609 |  |  | 1530.391
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 2377.4615 | 2.9351 | 0 | 1467.5688 | 9509.846 | 10977.4148
|  |  |  | Contaminated |  | 3535.276 | 36.8258 | 0 | 0 | 188536.2691 | 188536.2691
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Lead | 6796.8 | 9.6 | 1.2 | 78 | 13.2 | 3398.4 | 3489.6
|  |  |  | Fluorescent light ballasts, lbs |  | 60 | 7.5 | 487.5 | 82.5 | 150 | 720
|  | 2.13.2 | Remove systems from MB |  |  |  | A | 60.9297 | 1 | 60.9297 | 0 | 0 | 0 | 0 | 0 | 261.211 |  |  | 0 | 0 | 0 |  | 0 | 1206.0854 |  | 1206.0854
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | HVAC duct |  |  | 155 |  | 92 | 50% | 46 | 0.05679 | 0.06 | crew hrs/ft | 9.3 | UCF 69 - Remove Ductwork
|  |  | Clean | HVAC equipment |  | 6 |  |  | 114 | 0% | 114 | 0.14074 | 4 | crew hrs/comp | 24 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | Miscellaneous equipment |  | 2 |  |  | 48 | 0% | 48 | 0.059259 | 2.5 | crew hrs/comp | 5 | UCF 64 - 300 to 1,000 lbs
|  |  | Clean | 0 - 2" pipe, clean |  |  | 1680 |  | 52.08 | 0% | 52.08 | 0.064296 | 0.013333 | crew hrs/ft | 22.4 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 2 - 3.5" pipe, clean |  |  | 13 |  | 1.131 | 0% | 1.131 | 0.0013963 | 0.017667 | crew hrs/ft | 0.22967 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
[11 empty] | 261.211 | 0.32248 |  |  | 60.9297
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 261.211 | 0.32248 | 0 | 161.2414 | 1044.844 | 1206.0854
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Fluorescent light ballasts, lbs |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Mercury vapor lights |  | 0 | 0 | 0 | 0 | 0 | 0
| 2.14 | Remove Ventilation (Labor costs included in Undistributed costs) | [5 empty] | 511.36 |  | 511.36 | 0 | 585.45 | 0 | 0 | 0 | 1829.5 | 0 | 0 | 0 | 31222.0485 | 0 | 0 | 0 | 8447.321 | 0 | 39669.3695
|  | 2.14.1 | Remove ventilation system from Service Floor |  |  |  | A | 104.24 | 1 | 104.24 | 0 | 308 |  |  |  | 324 |  |  | 0 | 16425.64 |  |  |  | 1496 |  | 17921.64
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | HVAC duct |  |  | 274 |  | 648 | 50% | 324 | 0.4 | 0.06 | crew hrs/ft | 16.44 | UCF 69 - Remove Ductwork
|  |  | Contaminated | HVAC duct |  |  | 615 |  | 340 | 50% | 170 | 1.7708 | 0.12 | crew hrs/ft | 73.8 | UCF 69 - Remove Ductwork
|  |  | Contaminated | HVAC equipment |  | 2 |  |  | 138 | 0% | 138 | 1.4375 | 7 | crew hrs/comp | 14 | UCF 65 - 1,000 - 10,000 lbs
[11 empty] | 632 | 3.6083 |  |  | 104.24
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 324 | 0.4 | 0 | 200 | 1296 | 1496
|  |  |  | Contaminated |  | 308 | 3.2083 | 0 | 0 | 16425.64 | 16425.64
|  | 2.14.2 | Remove systems from Main Floor |  |  |  | A | 52.32 | 1 | 52.32 | 0 | 47.5 |  |  |  | 460 |  |  | 0 | 2533.175 |  |  |  | 2123.9506 |  | 4657.1256
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | HVAC duct |  |  | 300 |  | 920 | 50% | 460 | 0.5679 | 0.06 | crew hrs/ft | 18 | UCF 69 - Remove Ductwork
|  |  | Contaminated | HVAC duct |  |  | 286 |  | 95 | 50% | 47.5 | 0.49479 | 0.12 | crew hrs/ft | 34.32 | UCF 69 - Remove Ductwork
[11 empty] | 507.5 | 1.0627 |  |  | 52.32
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 460 | 0.5679 | 0 | 283.9506 | 1840 | 2123.9506
|  |  |  | Contaminated |  | 47.5 | 0.49479 | 0 | 0 | 2533.175 | 2533.175
|  | 2.14.3 | Remove ventilation system from Fan Loft |  |  |  | A | 354.8 | 1 | 354.8 | 0 | 229.95 |  |  |  | 1045.5 |  |  | 0 | 12263.2335 |  |  |  | 4827.3704 |  | 17090.6039
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Clean | HVAC duct |  |  | 384 |  | 135 | 50% | 67.5 | 0.083333 | 0.06 | crew hrs/ft | 23.04 | UCF 69 - Remove Ductwork
|  |  | Contaminated | HVAC duct |  |  | 498 |  | 459.9 | 50% | 229.95 | 2.3953 | 0.12 | crew hrs/ft | 59.76 | UCF 69 - Remove Ductwork
|  |  | Clean | HVAC equipment |  | 68 |  |  | 978 | 0% | 978 | 1.2074 | 4 | crew hrs/comp | 272 | UCF 65 - 1,000 - 10,000 lbs
[11 empty] | 1275.45 | 3.6861 |  |  | 354.8
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 1045.5 | 1.2907 | 0 | 645.3704 | 4182 | 4827.3704
|  |  |  | Contaminated |  | 229.95 | 2.3953 | 0 | 0 | 12263.2335 | 12263.2335
| 2.15 | Drill Out Storage Tubes (Labor costs included in Undistributed costs) |  |  |  |  | A | 304 | 1 | 304 | 0 | 1349 |  |  |  | 0 |  |  | 0 | 71942.17 |  |  |  | 0 |  | 71942.17
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | Remove storage tubes |  | 19 |  |  | 1349 | 0% | 1349 | 14.0521 | 16 | crew hrs/comp | 304 | Estimated
|  |  | Clean | Excavate buried pipe |  |  | 0 |  |  | 0% | 0 | 0 | 0.01 | crew hr/cu. yd. | 0 | UCF 12 - excavate below grade structures
|  |  | Clean | Buried pipe, clean |  |  | 0 |  | 0 | 0% | 0 | 0 | 0.088667 | crew hrs/ft | 0 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, use 2/3 of duration)
|  |  | Contaminated | Excavate buried pipe |  |  | 0 |  |  | 0% | 0 | 0 | 0.01 | crew hr/cu. yd. | 0 | UCF 12 - excavate below grade structures
|  |  | Contaminated | Buried pipe, contam. |  |  | 0 |  | 0 | 0% | 0 | 0 | 0.1197 | crew hrs/ft | 0 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
[11 empty] | 1349 | 14.0521 |  |  | 304
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 1349 | 14.0521 | 0 | 0 | 71942.17 | 71942.17 | Packaged in B-25 boxes
| 2.16 | Decontaminate Structures (Labor costs included in Undistributed costs) | [5 empty] | 254.02 |  | 254.02 | 0 | 327.626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17472.2946 | 0 | 0 | 0 | 0 | 0 | 17472.2946 |  | 2.6207 |  | 0 |  | 0.0049801
Assumptions:
1. For contaminated areas, concrete will be scabbled.
2. Productivity factors are included in the rates, unless otherwise specified.
3. Scabbled concrete volume will be increased 30% to account for packaging inefficiencies.
|  | 2.16.1 | Decontaminate Service Level |  |  |  | A | 25.78 | 1 | 25.78 | 0 | 40.066 | [6 empty] | 0 | 2136.7198 | [5 empty] | 2136.7198
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Decon concrete surfaces |  |  |  | 644.5 | 30.82 | -30% | 40.066 | 0.41735 | 0.04 | crew hr/sq. ft. | 25.78 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 40.066 | 0.41735 |  |  | 25.78
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Contaminated |  | 40.066 | 0.41735 | 0 | 0 | 2136.7198 | 2136.7198
|  | 2.16.2 | Decontaminate Main Level |  |  |  | A | 5.6 | 1 | 5.6 | 0 | 14.3 | [6 empty] | 0 | 762.619 | [5 empty] | 762.619
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Decon concrete surfaces |  |  |  | 140 | 11 | -30% | 14.3 | 0.14896 | 0.04 | crew hr/sq. ft. | 5.6 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 14.3 | 0.14896 |  |  | 5.6
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Contaminated |  | 14.3 | 0.14896 | 0 | 0 | 762.619 | 762.619
|  | 2.16.3 | Decontaminate Fan Loft |  |  |  | A | 222.64 | 1 | 222.64 | 0 | 273.26 | [6 empty] | 0 | 14572.9558 | [5 empty] | 14572.9558
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Decon concrete surfaces |  |  |  | 5566 | 210.2 | -30% | 273.26 | 2.8465 | 0.04 | crew hr/sq. ft. | 222.64 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
[11 empty] | 273.26 | 2.8465 |  |  | 222.64
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Contaminated |  | 273.26 | 2.8465 | 0 | 0 | 14572.9558 | 14572.9558
| 2.17 | Final Survey of Structure (Labor costs included in Undistributed costs) |  |  |  |  | A | 320 | 1.595 | 510.4 | 0 | [7 empty] | 0 | [6 empty] | 0 |  | 5.2658
|  |  |  | Estimated Duration | 320 | hrs
| 2.18 | Demolition Readiness Review (Labor costs included in Undistributed costs) |  |  |  |  | B | 80 | 1 | 80 | 0 | [7 empty] | 0 | [6 empty] | 0
| 2.19 | Remove Hot Cells (Labor costs included in Undistributed costs) | [5 empty] | 2600.1108 |  | 2600.1108 | 0 | 1822 | 69936 | 0 | 0 | 37681.4 | 0 | 1663238.2 | 0 | 97167.26 | 505204.3636 | 0 | 0 | 287133.3592 | 0 | 2552743.1828
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
3. For building removal use 2009 Means pg 28, 02 41 19.16 1450, 70 c. f. per day. This rate assumes a crew of 4 laborers and hand tools. This rate is assumed to be doubled for demolition using an excavator, not hand tools.
4. Truck shipments are limited to 40,000 lbs.
5. Concrete density = 150lbs/cu.ft., Block density = 145lbs/cu.ft. & Magnitite Concrete = 232lbs./cu.ft.
6. Lead glass windows are assumed to weigh 6,000 lbs ea. They will be packaged in B-25 containers for transport. Each window will be disposed of as hazardous waste at $0.50 per lb.
7. Fluid in the Lead glass windows has a density of 19.2 lbs / gallon(Tech Sheets from Chemtura, 07/03/08). The fluid will be packaged in 55 gallon drums for transport. The fluid will be disposed of as hazardous waste at $0.50 per lb.
8. Magnitite concrete will by segmented into approximately 20,000 lb blocks, (6'x5') by using diamond wire saw. Blocks will be shipped to the controlled landfill, 2 blocks per shipment.
9. Diamond wire cutting is approximately $79.30/cu. ft. (see calculation). This cost includes equipment and labor, from Bluegrass.
10. Duration of duct removal equal to duration of diamond wire cutting
|  | 2.19.1 | Service Level - Diamond wire cutting |  |  |  | A | 663.936 | 1 | 663.936 | 0 |  |  |  |  | 12768 |  | 1012502.4 | 0 |  |  |  |  | 116018.56 |  | 1128520.96
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Gallons | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | Containers
|  |  | Clean | Remove magnitite concrete |  |  |  | 12768 | 2962176 | 0% | 12768 | 74.0544 | 0.052 | crew hrs/cu ft | 663.936 | See calculation for diamond wire cutting
[9 empty] | 2962176 |  | 12768 | 74.0544 |  |  | 663.936
[12 empty] | Diamond Wire | Diamond Wire
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $ | cutting $/cuft | cutting
|  |  |  | Clean | 12768 | 2962176 | 74.0544 | 0 | 37027.2 | 78991.36 | 116018.56 | 79.3 | 1012502.4
|  | 2.19.2 | Service Level |  |  |  | A | 216.7289 | 1 | 216.7289 | 0 |  | 42728 |  |  | 9573 |  | 0 | 0 |  | 288733.0909 |  |  | 56175.3792 |  | 344908.4701
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Gallons | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | Containers
|  |  | Clean | Remove concrete block |  |  |  | 337 | 48865 | 0% | 337 | 1.2216 | 50 | cu. yd./day | 1.997 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 9236 | 1385400 | 0% | 9236 | 34.635 | 50 | cu. yd./day | 54.7319 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Hazardous - L | Remove fluid from lead windows |  | 20 | 5600 | 41888 | 107520 | 0% | 41888 | 1954.9091 | 4 | hrs/window | 80
|  |  | Hazardous - W | Lead glass windows |  | 20 |  | 840 | 120000 | 0% | 840 | 12 | 4 | hrs/window | 80
[9 empty] | 1661785 |  | 9573 | 35.8566 |  |  | 216.7289
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 9573 | 1434265 | 35.8566 | 0 | 17928.3125 | 38247.0667 | 56175.3792
|  |  |  | Hazardous - L | 41888 | 107520 | 1954.9091 | 127069.0909 | 21504 | 53760 | 202333.0909
|  |  |  | Hazardous - W | 840 | 120000 | 12 | 16800 | 9600 | 60000 | 86400
|  | 2.19.3 | Main Level - Diamond wire cutting |  |  |  | A | 426.712 | 1 | 426.712 | 0 |  |  |  |  | 8206 |  | 650735.8 | 0 |  |  |  |  | 74565.1867 |  | 725300.9867
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | Containers
|  |  | Clean | Remove magnitite concrete |  |  |  | 8206 | 1903792 | 0% | 8206 | 47.5948 | 0.052 | crew hrs/cu ft | 426.712 | See calculation for diamond wire cutting
[8 empty] | 8206 | 1903792 |  | 8206 | 47.5948 |  |  | 426.712
[12 empty] | Diamond Wire | Diamond Wire
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $ | cutting $/cuft | cutting
|  |  |  | Clean | 8206 | 1903792 | 47.5948 | 0 | 23797.4 | 50767.7867 | 74565.1867 | 79.3 | 650735.8
|  | 2.19.4 | Main Level |  |  |  | A | 202.0859 | 1 | 202.0859 | 0 |  | 27208 |  |  | 7134.4 |  | 0 | 0 |  | 216471.2727 |  |  | 40374.2333 |  | 256845.5061
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | Containers
|  |  | Clean | Remove concrete block |  |  |  | 6964 | 1009780 | 0% | 6964 | 25.2445 | 50 | cu. yd./day | 41.2681 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 30 | 4500 | 0% | 30 | 0.1125 | 50 | cu. yd./day | 0.17778 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Unistrut wall |  |  |  | 108 |  | -30% | 140.4 | 0.17333 | 50 | cu. yd./day | 0.64 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Hazardous - L | Remove fluid from lead windows |  | 20 | 3600 | 26928 | 69120 | 0% | 26928 | 1256.7273 | 4 | hrs/window | 80
|  |  | Hazardous - W | Lead glass windows |  | 20 |  | 280 | 120000 | 0% | 280 | 12 | 4 | hrs/window | 80
[8 empty] | 34310 | 1203400 |  | 34342.4 | 1294.2576 |  |  | 202.0859
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 7134.4 | 1014280 | 25.5303 | 0 | 12765.1667 | 27609.0667 | 40374.2333
|  |  |  | Hazardous - L | 26928 | 69120 | 1256.7273 | 81687.2727 | 13824 | 34560 | 130071.2727
|  |  |  | Hazardous - W | 280 | 120000 | 12 | 16800 | 9600 | 60000 | 86400
|  | 2.19.5 | Remove ducts from concrete wall |  |  |  | A | 1090.648 | 1 | 1090.648 | 0 | 1822 | [6 empty] | 0 | 97167.26 | [5 empty] | 97167.26
[10 empty] | Vol. Reduc. | Adjusted | # of B-25
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Contaminated | HVAC duct |  |  |  | 1822 |  | 0% | 1822 | 18.9792 | 10 | cu. yd./day | 53.9852 | Estimated
[8 empty] | 1822 | 0 |  | 1822 | 18.9792 |  |  | 53.9852
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Contaminated | 1822 |  | 18.9792 | 0 | 0 | 97167.26 | 97167.26
| 2.2 | Remove building (Labor costs included in Undistributed costs) | [5 empty] | 487.6969 |  | 487.6969 | 0 | 0 | 0 | 0 | 0 | 106386.4263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478307.2633 | 0 | 478307.2633 |  | 5.0315 |  | 1.6171
|  | 2.20.1 | Remove Interior walls |  |  |  |  | 214.5642 |  | 214.5642 | 0 | 0 | 0 | 0 | 0 | 47070.0262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212340.6803 | 0 | 212340.6803
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
3. For building removal use 2009 Means pg 28, 02 41 19.16 1450, 70 c. f. per day. This rate assumes a crew of 4 laborers and hand tools. This rate is assumed to be doubled for demolition using an excavator, not hand tools.
|  | 2.20.1.1 | Service Level |  |  |  | A | 7.0693 | 1 | 7.0693 | 0 |  |  |  |  | 1550.8188 |  |  | 0 |  |  |  |  | 6822.7952 |  | 6822.7952
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove concrete block |  |  |  | 1032.9375 | 149775.9375 | -30% | 1342.8188 | 3.7444 | 50 | cu. yd./day | 6.1211 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 30 | 4500 | -30% | 39 | 0.1125 | 50 | cu. yd./day | 0.17778 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Unistrut wall |  |  |  | 130 |  | -30% | 169 | 0.20864 | 50 | cu. yd./day | 0.77037 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 1192.9375 | 154275.9375 |  | 1550.8188 | 4.0655 |  |  | 7.0693
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 1550.8188 | 154275.9375 | 4.0655 | 0 | 2032.7702 | 4790.025 | 6822.7952
|  | 2.20.1.2 | Main Level |  |  |  | A | 117.3379 | 1 | 117.3379 | 0 |  |  |  |  | 25741.0075 |  |  | 0 |  |  |  |  | 116398.8351 |  | 116398.8351
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove concrete block |  |  |  | 186 | 26970 | -30% | 241.8 | 0.67425 | 50 | cu. yd./day | 1.1022 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 26 | 3900 | -30% | 33.8 | 0.0975 | 50 | cu. yd./day | 0.15407 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  | 18759.5 | 2813925 | -30% | 24387.35 | 70.3481 | 50 | cu. yd./day | 111.1674 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Metal wall |  |  |  | 560.475 |  | -30% | 728.6175 | 0.89953 | 50 | cu. yd./day | 3.3213 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Unistrut wall |  |  |  | 268.8 |  | -30% | 349.44 | 0.43141 | 50 | cu. yd./day | 1.5929 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 19800.775 | 2844795 |  | 25741.0075 | 72.4508 |  |  | 117.3379
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 25741.0075 | 2844795 | 72.4508 | 0 | 36225.4051 | 80173.43 | 116398.8351
|  | 2.20.1.3 | Fan Loft |  |  |  | A | 90.157 | 1 | 90.157 | 0 |  |  |  |  | 19778.2 |  |  | 0 |  |  |  |  | 89119.05 |  | 89119.05
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove concrete block |  |  |  | 1344 | 194880 | -30% | 1747.2 | 4.872 | 50 | cu. yd./day | 7.9644 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 1640 | 246000 | -30% | 2132 | 6.15 | 50 | cu. yd./day | 9.7185 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  | 12230 | 1834500 | -30% | 15899 | 45.8625 | 50 | cu. yd./day | 72.4741 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 15214 | 2275380 |  | 19778.2 | 56.8845 |  |  | 90.157
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 19778.2 | 2275380 | 56.8845 | 0 | 28442.25 | 60676.8 | 89119.05
|  | 2.20.2 | Remove 200 MA/MB Wings |  |  |  | A | 273.1327 | 1 | 273.1327 | 0 |  |  |  |  | 59316.4 |  |  | 0 |  |  |  |  | 265966.583 |  | 265966.583
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Width | Depth | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes
|  |  | Clean | Remove brick |  |  |  | 2952 | 428040 | -30% | 3837.6 | 10.701 | 50 | cu. yd./day | 17.4933 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  | 11507 | 1668515 | -30% | 14959.1 | 41.7129 | 50 | cu. yd./day | 68.1896 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 9664 | 1449600 | -30% | 12563.2 | 36.24 | 50 | cu. yd./day | 57.2681 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  | 18159 | 2723850 | -30% | 23606.7 | 68.0962 | 50 | cu. yd./day | 107.6089 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove structural steel |  |  |  |  | 7841.5 | 0% | 0 | 0.19604 | 0.7 | crew hr/ton | 2.7445 | UCF 8 - structural steel
|  |  | Clean | Gypsum wall |  |  |  | 29 |  | -30% | 37.7 | 0.046543 | 50 | cu. yd./day | 0.17185 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove insulation |  |  |  | 1701 |  | -30% | 2211.3 | 2.73 | 50 | cu. yd./day | 10.08 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove metal deck |  |  |  | 1616 |  | -30% | 2100.8 | 2.5936 | 50 | cu. yd./day | 9.5763 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 59316.4 | 162.3163 |  |  | 273.1327
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 59316.4 | 6277846.5 | 162.3163 | 0 | 81158.143 | 184808.44 | 265966.583
| 2.17 | Final Site Survey Structure gone |  |  |  |  | A | 0 | 1 | 0 | 0 | [7 empty] | 0 | [6 empty] | 0
Schedule
[7 empty] | Work hours |  | duration, days
|  | 2.17.1 | Prepare Final Status Survey Plan |  | 0 | days = | 0 | hrs | 0 | days - 40 days in parallel with 2.16
|  | 2.17.2 | Soil Sampling |  | 0 | days = | 0 | hrs | 0 | days- in parallel with 2.17.1
|  | 2.17.3 | Direct Survey |  | 0 | days = | 0 | hrs | 0 | days
|  | 2.17.4 | Sampling Analysis |  | 0 | days = | 0 | hrs | 0 | days
|  | 2.17.5 | Prepare Final Status Survey Report |  | 0 | days = | 0 | hrs | 0 | days - three days overlap with 2.17.4
[7 empty] | 0 |  | 0
| 2.18 | Orise Site Release Confirmation
|  | Duration equal 45 days; however, this activity will occur in parallel with 2.17. The schedule duration will be 45 - 40 days = | [6 empty] | 0 | days
| 2.21 | Backfill, grade and seed (Labor costs included in Undistributed costs) |  |  |  |  | A | 44.8699 | 1 | 44.8699 | 0 | [6 empty] | 143763.5333 | 0 | [6 empty] | 143763.5333
Assumptions:
|  |  | 1. Grade and see area 104' x 93', plus 10%. | [12 empty] | Grade and seed |  | 3930.5524 | [9 empty] | 0.36944 | /sqft
|  |  | 2. Productivity factors are included in the rates, unless otherwise specified. | [12 empty] | Backfill |  | 26523.5549 | [9 empty] | 0.18282 | /cuft
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Width | Depth | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  |  | Grade |  |  |  | 10639.2 |  | 0% | 0 | 0 | 18000 | sq ft/8 hr day | 4.7285 | 2009 RS Means 31 22 16.10 0100
|  |  |  | Seed |  |  |  | 10639.2 |  | 0% | 0 | 0 | 80100 | sq ft/8 hr day | 1.0626 | 2009 RS Means 32 92 19.13 1000
|  |  |  | Backfill |  |  |  |  | 145080 | 0% | 145080 | 0 | 1100 | cu. yd./day | 39.0788 | 2009 RS Means 31 23 23.14 2000
|  |  |  | Gravel base layer | [5 empty] | 0% | 0 | 0 | 4200 | sq yd/8 hr day | 0 | 2009 RS Means 32 11 23.23 0300
|  |  |  | Pavement - binder course - 4" | [5 empty] | 0% | 0 | 0 | 10800 | sq ft/8 hr day | 0 | 2009 RS Means 32 12 16.14 0600
|  |  |  | Pavement - finish course - 2" | [5 empty] | 0% | 0 | 0 | 34000 | sq ft/8 hr day | 0 | 2009 RS Means 32 12 16.14 0900
[11 empty] | 145080 | 0 |  |  | 44.8699
|  |  |  | Waste | Area, sq. ft. | Installation, $/SF | Material, $/SY | Equipment, $/SY | Volume, cu. Ft. | Cost, $/cu. yd. | Total, $
|  |  |  | Seed and equipment | 10639.2 |  | 0.18 | 0.07 |  |  | 295.5333 | 2009 RS Means 32 92 19.13 1000
|  |  |  | Structural fill |  |  |  |  | 145080 | 26.7 | 143468 | 2009 RS Means 31 05 16.10 0600 + 0900 & 31 23 23.24 0400
143763.5333
| 2.22 | Site Demobilization (Labor costs included in Undistributed costs) | [5 empty] | 80 |  |  | 1920 | [6 empty] | 9600 | 0 | [6 empty] | 9600
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Project Manager |  | 0 | 0
|  |  | 1 | Project Safety Manager |  | 0 | 0
|  |  | 1 | Project Specialist |  | 0 | 0
|  |  | 1 | Health Physicist |  | 0 | 0
|  |  | 1 | Chief HP Tech |  | 0 | 0
|  |  | 1 | Building Maintenance |  | 0 | 0
|  |  | 1 | Secretary |  | 0 | 0
|  |  | 1 | Project Control Specialist |  | 0 | 0
|  |  | 4 | HP Tech |  | 0 | 0
|  |  | 12 | Decon Techs |  | 0 | 0
|  |  | 24 |  |  |  | 0
|  |  | Return rented equipment, including trailers |  |  | 24 | hr
|  |  | Dispose of unused material |  |  | 24 | hr
|  |  | General site cleanup |  |  | 24 | hr
|  |  | Travel home |  |  | 8
[6 empty] | 80 | hr
|  |  | Total Cost = |  | 80 | x | 0 | 0
|  |  | Travel cost = |  | 24 | x | 400 | 9600
| 2.23 | Final Project Report - Offsite |  |  |  |  | A | 240 | 1.1 | 264 | 440 | [7 empty] | 41360 | [6 empty] | 41360
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 85 | 160 | 1.1 | 29920 | 352
|  |  | Project Manager |  |  | 1 | 130 | 80 | 1.1 | 11440 | 88
[6 empty] | 3 |  | 240 |  | 41360 | 440
Crew cost - 4 crews from mobilization through final survey
| Staff |  |  | Number | Rate
| Decon Techs |  |  | 12 | 56.56 | 678.72
Crew cost - 2 crews from final survey through site demobilization
| Staff |  |  | Number | Rate
| Decon Techs |  |  | 12 | 56.56 | 678.72

## Building 4 - 2012 (hidden)
Shell floor area |  | 153106 | [12 empty] | Mixed | Clean | Lead | Materials, |  |  | Hazardous |  | Mixed | Clean | Lead |  |  |  |  | Clean | Hazardous | LLW | Mixed
Service Bldg Floor |  | 27318 | [5 empty] | Uncorrected Duration |  | Adjusted |  | LSA Waste | Hazardous | Ballast | Waste | Waste | Waste | Consumables, |  | LSA Waste | Waste | >LSA Waste | Waste | Waste | Waste |  |  | Removal |  | Waste | Waste | Waste | Waste
331A |  | 8518 |  |  |  |  | Crew | (No. of Hours) | Prod. Factor | Duration | Man-hours | Disp. Vol (cf) | Waste Vol (cf) | Volume (cf) | Volume (cf) | Volume (cf) | Volume (cf) | & Equipment | Labor Cost | Cost | Cost | Cost | Cost | Cost | Cost | Total Cost |  | Unit Rate |  | Volume | Volume | Volume | Volume
| Grand Total Building 331 | [24 empty] | 33523974.0293
| Contingency = |  | 40% | [22 empty] | 9578278.2941
1 | Total Building 331 | [24 empty] | 23945695.7352
| Argonne Oversight @ 24% | [22 empty] | 24% |  | 4634650.7875
Argonne Tax | General and Administration @ 3.8% | [22 empty] | 3.8% |  | 706955.4027
Argonne Tax | IGPP/IGPE @ 3.4% | [22 empty] | 3.4% |  | 611739.8883
Argonne Tax | LDRD On total only | [22 empty] | 8.3% |  | 1320393.4761 | On total
Argonne Tax | Material and Subcontracts Tax @ 4.8% | [22 empty] | 4.8% |  | 763601.0464 | On total
1 | Building 331 | [9 empty] | 96067.7143 | 7356.0124 | 42.38 | 7.5 | 237.9 | 301673.9784 | 193.2 | 5689285.7211 | 7340199.2857 | 1387242.694 | 984.5597 | 0 | 4466.9279 | 1400268.8546 | 85907.0912 | 15908355.1342
UNDISTRIBUTED COSTS | [10 empty] | 89325.7143 | [6 empty] | 4722397.7272 | 7154519.2857 | 0 | 0 | 0 | 0 | 0 |  | 11876917.0129
|  | Project duration = |  |  | 933 | days/7days/wk = | 133.2857 | See Project Schedule - Starts with Site Mobilization and ends with Site Demobilization
[5 empty] | 666.4286 | working days
|  | Labor cost = |  | 2026764.2857 | (Used to determine small tool costs and HP Supplies)
| 1.1 | Project Management | [8 empty] | 53314.2857 | [7 empty] | 4403760 | [6 empty] | 4403760
|  | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
|  | Project Manager |  |  | 1 | 130 | 666.4286 | 100% | 693085.7143 | 5331.4286
|  | Project Safety Manager |  |  | 1 | 100 | 666.4286 | 100% | 533142.8571 | 5331.4286
|  | Project Specialist |  |  | 1 | 85 | 666.4286 | 100% | 453171.4286 | 5331.4286
|  | Health Physicist |  |  | 1 | 120 | 666.4286 | 100% | 639771.4286 | 5331.4286
|  | Site Supervisor |  |  | 1 | 100 | 666.4286 | 100% | 533142.8571 | 5331.4286
|  | Chief HP Tech |  |  | 1 | 58 | 666.4286 | 100% | 309222.8571 | 5331.4286
|  | Secretary |  |  | 1 | 33 | 666.4286 | 100% | 175937.1429 | 5331.4286
|  | Project Control Specialist |  |  | 1 | 98 | 666.4286 | 100% | 522480 | 5331.4286
|  | HP Tech |  |  | 2 | 51 | 666.4286 | 100% | 543805.7143 | 10662.8571
[5 empty] | 10 |  |  |  | 4403760 | 53314.2857
| 1.2 | Project Management Per Diem | [16 empty] | 909675 | [6 empty] | 909675
[6 empty] | Per Diem | Number of
|  | Staff |  |  | Number | Rate, $/day | Days | Total
|  | Project Manager |  |  | 1 | 153 | 933 | 142749
|  | Project Safety Manager |  |  | 1 | 153 | 933 | 142749
|  | Project Specialist |  |  | 1 | 153 | 933 | 142749
|  | Health Physicist |  |  | 1 | 153 | 933 | 142749
|  | Site Supervisor |  |  | 1 | 153 | 933 | 142749
|  | Chief HP Tech |  |  | 1 | 70 | 933 | 65310
|  | HP Tech |  |  | 2 | 70 | 933 | 130620
[5 empty] | 8 |  |  | 909675
| 1.3 | Not Used | [8 empty] | 0 | [7 empty] | 0 | [6 empty] | 0
Asbestos Crew cost
|  | Duration | 0 | days/7days/wk = | 0 | 0 | working days | See Project Schedule
|  | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
|  | Decon Techs |  |  | 12 | 45 | 0 | 100% | 0 | 0
[5 empty] | 12 |  |  |  | 0 | 0
| 1.4 | Crew cost - 2 crews from mobilization through final survey of structures | [8 empty] | 16091.4286 | [7 empty] | 822674.2857 | [6 empty] | 822674.2857
|  | Duration | 352 | days/7days/wk = | 50.2857 | 251.4286 | working days | See Project Schedule - Starts with Site Mobilization and ends with Remove Building
|  | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
|  | Decon Techs per diem |  |  | 4 | 70 | 352 | 100% | 98560
|  | Decon Techs |  |  | 8 | 45 | 251.4286 | 100% | 724114.2857 | 16091.4286
[5 empty] | 8 |  |  |  | 822674.2857 | 16091.4286
| 1.5 | Crew cost - 2 crews from building demo through site demobilization | [8 empty] | 19920 | [7 empty] | 1018410 | [6 empty] | 1018410
|  | Duration | 581 | days/7days/wk = | 83 | 415 | working days | See Project Schedule - Starts with Remove Building and ends with Site Demobilization
|  | Staff |  |  | Number | Rate | Duration, days* | Use Factor | Cost | Man-hours
|  | Decon Techs per diem |  |  | 3 | 70 | 581 | 100% | 122010
|  | Decon Techs |  |  | 6 | 45 | 415 | 100% | 896400 | 19920
[5 empty] | 6 |  |  |  | 1018410 | 19920
| 1.6 | Equipment & Materials | [15 empty] | 4722397.7272 | [7 empty] | 4722397.7272
|  | Equipment |  |  | Quantity | Rate | Cost
|  | HEPA filter systems |  |  | 2 | 3922.22 | 7844.44
|  | Replacement filters |  |  | 24 | 522.5 | 12540
|  | Respirator |  |  | 30 | 214 | 6420
|  | Rad/Vac wet-dry high eff. vacuum |  |  | 4 | 4080 | 16320
|  | Rad/Vac wet-dry high eff. vacuum filters |  |  | 10 | 412 | 4120
|  | Reciprocating Saws |  |  | 6 | 1198.62 | 7191.72
|  | Pneumatic chipping hammers |  |  | 2 | 1217.82 | 2435.64
|  | Chipping hammer blades |  |  | 20 | 35.3 | 706
|  | Purchase an air compressor: |  |  | 4 | 1209.73 | 4838.92
|  | Jackhammer |  |  | 2 | 1102.37 | 2204.74
|  | Jackhammer Chisels |  |  | 20 | 27.42 | 548.4
|  | Safety glasses |  |  | 150 | 9.9 | 1485
|  | Fall protection - harness |  |  | 12 | 159 | 1908
|  | Fall protection - lanyard |  |  | 12 | 175 | 2100
|  | Hardhats |  |  | 40 | 30 | 1200
|  | Hard hat hearing protection |  |  | 40 | 28.6 | 1144
|  | Trailer rental |  |  | 2 | 440.5 | 27006.0125
|  | Phone and computer hook-up |  |  | 1 | 250 | 7663.4542
|  | Industrial hygiene instrumentation, calibration and hygienists - 1% of total activity $. |  |  |  |  | 58725.2241
|  | Front end loader, wheeled |  |  | 2 | 6175.7 | 344935.604
|  | Hydraulic hammer for excavator |  |  | 2 | 9539.625 | 443183.5423
|  | Excavator |  |  | 3 | 24994.55 | 1741762.3661
|  | Grapple for excavator |  |  | 1 | 2275.325 | 52852.5279
|  | Scaffolding for shell |  |  | 1 | 3101.3654 | 1528.4355
|  | Dump trucks excavation and backfill |  |  | 8 | 18638.25 | 367417.0408
|  | Rental cars |  |  | 5 | 800 | 128529.1863
|  | Water tank Trailer |  |  | 1 | 3557.95 | 53889.4409
|  | Dust Boss DB 60 |  |  | 2 | 850 | 111577.0452
|  | Dust Boss DB 60 transport |  |  | 2 | 3000 | 6000
|  | Shot Blaster |  |  | 2 | 3278.3375 | 40714.4313
|  | Floor Shaver |  |  | 2 | 8487.2 | 105404.499
|  | Wall Shaver |  |  | 2 | 15913.5 | 197633.4355
|  | Core Drill & Bits |  |  | 0 | 10609 | 0
|  | Man lift |  |  | 1 | 4931.5375 | 43585.0483
|  | Crane rental for building removal |  |  | 2 | 25477.125 | 264508.9749
4069923.1289
|  | Consumables |  | Quantity |  | Duration |  | # workers | quantity | Unit Qty | Unit Cost | Cost
|  | Coveralls |  | 2 | /man/day | 251.4286 | days | 10 | 5028.5714 | 1 | 11 | 55314.2857 | 2 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Hoods with coveralls |  | 0.5 | /man/day | 251.4286 | days | 10 | 1257.1429 | 1 | 0 | 0 | 2 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Shoe covers |  | 4 | /man/day | 251.4286 | days | 10 | 10057.1429 | 1 | 0.94 | 9453.7143 | 2 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Latex gloves |  | 4 | /man/day | 251.4286 | days | 10 | 10057.1429 | 1 | 0.94 | 9453.7143 | 2 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Rubber overshoes |  | 0.01 | /man/day | 251.4286 | days | 10 | 25.1429 | 1 | 3 | 75.4286 | 2 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Gloves |  | 0.5 | /man/day | 251.4286 | days | 10 | 1257.1429 | 1 | 1.63 | 2049.1429 | 2 crews of 4 (3 decon techs and 1 HP tech per crew. HP techs with staff)
|  | Dosimeters |  | 1 | /man/year | 0.96703 | year | 18 | 17.4066 | 1 | 200.8333 | 3495.8242
|  | TLDs |  | 1 | /man/mo | 11.6133 | month | 18 | 209.0399 | 1 | 3 | 627.1198
|  | Bioassays |  | 2 | /man/year | 0.96703 | year | 18 | 34.8132 | 1 | 250 | 8703.2967
|  | (Bioassays for aver. crew & management) | [9 empty] | 89172.5264
|  | Small Tools - 2% of total labor costs = |  |  |  | 2026764.2857 | labor costs x | 2% | = | 40535.2857
|  | HP Equipment Replacement - 5% of total labor |  |  |  | 2026764.2857 | labor costs x | 5% | = | 101338.2143
|  | DGC OH &P on equipment and materials |  |  |  | 5267857.1492 |  | 8% | = | 421428.5719
ACTIVITIES | [7 empty] | 10622.9837 |  | 11048.9037 | 6742 | 7356.0124 | 42.38 | 7.5 | 237.9 | 301673.9784 | 193.2 | 966887.9939 | 185680 | 1387242.694 | 984.5597 | 0 | 4466.9279 | 1400268.8546 | 85907.0912 | 4031438.1212
| 1.7 | Project Engineering | [5 empty] | 800 |  | 880 | 1408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133760 | 0 | 0 | 0 | 0 | 0 | 0 | 133760
|  | 1.7.1 | Procedure Development and Review - Offsite |  |  |  |  | 400 | 1.1 | 440 | 704 | [7 empty] | 66880 | [6 empty] | 66880
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 85 | 240 | 1.1 | 44880 | 528
|  |  | Project Manager |  |  | 1 | 130 | 80 | 1.1 | 11440 | 88
|  |  | Certified Health Physicst |  |  | 1 | 120 | 80 | 1.1 | 10560 | 88
[6 empty] | 4 |  | 400 |  | 66880 | 704
|  | 1.7.2 | Preparation of QA and Safety Documents - Offsite |  |  |  |  | 400 | 1.1 | 440 | 704 | [7 empty] | 66880 | [6 empty] | 66880
|  |  | Staff |  |  | Number | Rate | Duration | PLF |  | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 85 | 240 | 1.1 |  | 44880 | 528
|  |  | Project Manager |  |  | 1 | 130 | 80 | 1.1 |  | 11440 | 88
|  |  | Certified Health Physicst |  |  | 1 | 120 | 80 | 1.1 |  | 10560 | 88
[6 empty] | 4 |  | 400 |  |  | 66880 | 704
| 1.8 | Site Mobilization and General Employee Training (GET) | [5 empty] | 128 | 1 | 128 | 1854 | [6 empty] | 30600 | 0 | [6 empty] | 30600
|  | 1.8.1 | Site Mobilization |  |  |  |  | 48 |  | 48 | 864 | [6 empty] | 7200 | 0 | [6 empty] | 7200
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Project Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Safety Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Health Physicist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Chief HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Building Maintenance |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Secretary |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Control Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 2 | HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 0 | Asbestos Techs |  | 0 | 0 | With Undistributed Costs
|  |  | 8 | Decon Techs |  | 0 | 0 | With Undistributed Costs
|  |  | 18 |  |  |  | 0
|  |  | Travel to site |  |  | 8 | hr
|  |  | Receipt of material and equipment |  |  | 16 | hr
|  |  | Staging of equipment |  |  | 8 | hr
|  |  | Set up office and amenities |  |  | 12 | hr
|  |  | Familiarize staff with facility |  |  | 4 | hr
[6 empty] | 48 | hr
|  |  | Labor Cost = |  | 48 | x | 0 | 0
|  |  | Travel cost = |  | 18 | x | 400 | 7200
|  | 1.8.2 | General Employee Training |  |  |  |  | 40 | 1 | 40 | 270 | [6 empty] | 23400 | 0 | [6 empty] | 23400
(All project management, 2 HP Techs & 2 crews of 4 Decon Techs)
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Project Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Safety Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Health Physicist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Chief HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Building Maintenance |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Secretary |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Control Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 2 | HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 0 | Asbestos Techs |  | 0 | 0 | With Undistributed Costs
|  |  | 8 | Decon Techs |  | 0 | 0 | With Undistributed Costs
|  |  | 18 |  |  |  | 0
[8 empty] | Number | Test | Labor | Total
[7 empty] | Unit Cost | Required | Cost | Costs | Cost
|  |  | In-Vivo |  |  |  | 600 | 18 | 10800 |  | 10800
|  |  | In-Vitro |  |  |  | 350 | 18 | 6300 |  | 6300
|  |  | Physical @ |  | 4 | hour and | 150 | 18 | 2700 | 0 | 2700
|  |  | Resp. Tests |  | 1 | hour and | 50 | 18 | 900 | 0 | 900
|  |  | Resp Fit Tests |  | 1 | hour and | 25 | 18 | 450 | 0 | 450
|  |  | Blood Tests |  | 1 | hour and | 125 | 18 | 2250 | 0 | 2250
|  |  | OSHA recertification |  | 8 | hour |  |  |  | 0 | 0
[5 empty] | 15 |  |  |  | 23400 | 0 | 23400
|  | 1.8.3 | Site Specific Training |  |  |  |  | 40 | 1 | 40 | 720 | [7 empty] | 0 | [6 empty] | 0
(All project management, 2 HP Techs & 2 crews of 4 Decon Techs)
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Project Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Safety Manager |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Health Physicist |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Chief HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Building Maintenance |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Secretary |  | 0 | 0 | With Undistributed Costs
|  |  | 1 | Project Control Specialist |  | 0 | 0 | With Undistributed Costs
|  |  | 2 | HP Tech |  | 0 | 0 | With Undistributed Costs
|  |  | 0 | Asbestos Techs |  | 0 | 0 | With Undistributed Costs
|  |  | 8 | Decon Techs |  | 0 | 0 | With Undistributed Costs
|  |  | 18 |  |  |  | 0
| 1.9 | Site Preparation (Labor costs included in Undistributed costs) |  |  |  |  | B | 168 | 1.21 | 181.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
|  | 1.9.1 | Initial Site Survey |  |  |  | B | 16 | 1.21 | 19.36 | 0 | [7 empty] | 0 | [6 empty] | 0
|  |  |  | Estimated Duration | 16 | hrs
|  | 1.9.2 | Setup work areas |  |  |  |  | 72 |  | 81.84 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1000 | 0 | [6 empty] | 1000
|  | 1.9.2.1 | Setup boundaries, install HEPA filters & seal off ventilation openings |  |  |  | B | 24 | 1.21 | 29.04 | 0 | 0 | 0 |  |  |  |  | 1000 | 0 | [6 empty] | 1000
(estimated)
|  | 1.9.2.2 | Establish staging area |  |  |  | B | 8 | 1.1 | 8.8 | 0 | 0 | 0 | [5 empty] | 0 | [6 empty] | 0
|  | 1.9.2.3 | Setup Rad & Non-Rad Segregation/Packaging Stations |  |  |  | B | 40 | 1.1 | 44 | 0 | 0 | 0 | [5 empty] | 0 | [6 empty] | 0
|  | 1.9.3 | Decontamination Readiness Review |  |  |  | B | 80 | 1 | 80 | 0 | [7 empty] | 0 | [6 empty] | 0
| 1.1 | Disconnect all utilities to work areas. | [5 empty] | 72 |  | 87.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
|  | 1.10.3.1 | Electrical |  |  |  | B | 24 | 1.21 | 29.04 | 0 |  |  |  | 0 |  |  | 5000 | 0 | [6 empty] | 5000
(new material allowance)
|  | 1.10.3.2 | Ventilation |  |  |  | B | 8 | 1.21 | 9.68 | 0 |  |  |  | 0 |  |  | 5000 | 0 | [6 empty] | 5000
|  | 1.10.3.3 | Piping |  |  |  | B | 40 | 1.21 | 48.4 | 0 |  |  |  | 0 |  |  | 5000 | 0 | [6 empty] | 5000
| 1.11 | Equipment Removal/Decontamination (Labor costs included in Undistributed costs) | [5 empty] | 2726.7962 |  | 3012.3962 | 0 | 7200.0516 | 42.38 | 7.5 | 237.9 | 29722.539 | 193.2 | 692739.41 | 0 | 1378925.3042 | 984.5597 | 0 | 4466.9279 | 163383.6564 | 85907.0912 | 2326406.9493
Assumptions:
1. Productivity factors are included in the rates, unless otherwise specified.
|  |  | 2. All waste volumes will be increased 30% to account for packaging inefficiencies. | [7 empty] | Asbestos Total | 1026.9445 | Includes contaminated asbestos
|  |  | 3. Asbestos will be double bagged and disposed of at a controlled landfill licensed to accept ACM | [8 empty] | 789.0445 | Clean asbestos only
4. Fluorescent lights contain mercury and ballasts contain PCBs
5. Ballasts and lights packaged in 55 gallon drums and disposed of as hazardous waste
6. Clean waste packaged in 30 cu. yd. containers
7. LLW will be packaged in B25 containers.
8, Tanks less than 300 gallons will be removed in one piece. Tanks greater than 300 gallons will be sgmented.
|  | 1.11.1 | 331 Shell |  |  |  |  | 1370.1525 |  | 1465.3525 | 0 | 7158.7493 | 2.47 | 0.69853 | 237.9 | 22684.0123 | 0 | 692739.41 | 0 | 1376662.7736 | 70.7499 | 0 | 4466.9279 | 130884.7801 | 0 | 2204824.6416
[8 empty] | Clean |  | 133.3344 | [17 empty] | 1.2018 |  | 0.0093112
[8 empty] | LLW |  | 0 | [21 empty] | 0
[8 empty] | Hazardous |  | 0 | [20 empty] | 0
[8 empty] | Mixed |  | 0 | [22 empty] | 0
|  | 1.11.1.1 | Remove Miscellaneous Material |  |  |  | A | 40 | 1 | 40 | 0 |  |  |  |  | 100 |  |  | 0 |  |  |  |  | 461.7284 |  | 461.7284
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Miscellaneous equipment |  |  |  |  | 100 | 0% | 100 | 0.12346 |  | crew hrs/comp | 1 | 40 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 100 | 0.12346 |  |  |  | 40
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 100 | 0.12346 | 0 | 61.7284 | 400 | 461.7284
|  | 1.11.1.2 | Remove Asbestos & other hazardous material |  |  |  | A | 85.3562 | 1 | 85.3562 | 0 |  | 2.47 | 0.69853 | 237.9 | 12.35 | 0 |  | 0 |  | 70.7499 |  | 4466.9279 | 57.0235 | 0 | 4594.7013
[8 empty] | Clean |  | 6.7925
[8 empty] | LLW |  | 0
[8 empty] | Hazardous |  | 20.3775
[8 empty] | Mixed |  | 58.1862
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove asbestos pipe insulation | [5 empty] | -30% | 0 | 0 | 0.11 | crew hrs/ft | 1.3 | 0 | 2009 mean, p33, 02 82 13.43 1200 with glove bags
|  |  | Mixed | Remove asbestos ceiling tile |  |  |  | 2289 | 183 | -30% | 237.9 | 0.2937 | 0.008 | crew hrs/sq. ft. | 1.43 | 58.1862 | Assume 1000 sq ft per day plus two days to set up and 2 days to dismantle scaffolding. | [10 empty] | 35.0795 | /sq ft |  |  |  | 0.10393 | cu. ft./sq.ft
|  |  | Hazardous | Fluorescent light bulbs |  | 38 |  |  | 1.9 | -30% | 2.47 | 0.33592 | 0.25 | crew hrs/comp | 1.43 | 13.585 | Estimated
|  |  | Clean | Fluorescent fixtures |  | 19 |  |  | 9.5 | -30% | 12.35 | 0.015247 | 0.25 | crew hrs/comp | 1.43 | 6.7925 | Estimated
|  |  | Hazardous | Fluorescent light ballasts, lbs |  | 19 | 57 |  |  | -30% | 0 | 0.095 | 0.25 | crew hrs/comp | 1.43 | 6.7925 | Estimated
[6 empty] | 0.048093 | 0.47947 | 3 |  |  | 252.72 | 0.73987 |  |  |  | 85.3562
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 12.35 | 0.015247 | 0 | 7.6235 | 49.4 | 57.0235
|  |  |  | Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Mixed |  | 237.9 | 0.2937 | 411.1852 | 234.963 | 3820.7797 | 4466.9279
|  |  |  | Hazardous |  | 2.47 | 0.33592 | 21.8348 | 3.6951 | 9.5 | 35.0299
|  |  |  | Hazardous, ballasts | 57 | 0.69853 | 0.095 | 6.175 | 1.045 | 28.5 | 35.72
|  | 1.11.1.3 | Remove systems and components |  |  |  |  | 93.3344 |  | 93.3344 | 0 | 0 | 0 | 0 | 0 | 1325.5957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6120.6516 | 0 | 6120.6516
|  | 1.11.1.3.1 | Remove piping |  |  |  | A | 75.821 | 1 | 75.821 | 0 | 0 |  |  |  | 234.8957 |  |  | 0 | 0 |  |  |  | 1084.58 |  | 1084.58
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | 0 - 2.5" pipe, clean |  |  | 2815 |  | 50.1565 | -30% | 65.2035 | 0.080498 | 0.013333 | crew hrs/ft | 1 | 37.5333 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 3 - 4" pipe, clean |  |  | 651 |  | 46.1586 | -30% | 60.0062 | 0.074082 | 0.017667 | crew hrs/ft | 1 | 11.501 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 5 - 6" pipe, clean |  |  | 151 |  | 29.6488 | -30% | 38.5435 | 0.047585 | 0.10667 | crew hrs/ft | 1 | 16.1067 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | 8 - 14" pipe, clean |  |  | 60 |  | 32.725 | -30% | 42.5425 | 0.052522 | 0.178 | crew hrs/ft | 1 | 10.68 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | Non-asbestos insulation - removed with pipe |  |  |  |  | 22 | -30% | 28.6 | 0.035309
|  |  | Clean | Excavate buried pipe - assume 4' wide & 4' deep | [5 empty] | 0% | 0 |  | 0.01 | crew hr/cu. yd. | 1 | 0 | UCF 12 - excavate below grade structures
|  |  | Clean | Buried pipe, clean | [5 empty] | 0% | 0 | 0 | 0.10667 | crew hrs/ft | 1 | 0 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 3.)
|  |  | Contaminated | 0 - 2.5" pipe, contam. |  |  |  |  | 0 | -30% | 0 | 0 | 0.013333 | crew hrs/ft | 1.35 | 0 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Contaminated | 3 - 4" pipe, contam. |  |  |  |  | 0 | -30% | 0 | 0 | 0.017667 | crew hrs/ft | 1.35 | 0 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. )
|  |  | Contaminated | 5 - 6" pipe, contam. |  |  |  |  | 0 | -30% | 0 | 0 | 0.10667 | crew hrs/ft | 1.35 | 0 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
[11 empty] | 234.8957 | 0.28999 |  |  |  | 75.821
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 234.8957 | 0.28999 | 0 | 144.9973 | 939.5827 | 1084.58
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.11.1.3.2 | Remove large equipment |  |  |  | A | 17.5134 | 1 | 17.5134 | 0 | 0 |  |  |  | 1090.7 |  |  | 0 | 0 |  |  |  | 5036.0716 |  | 5036.0716
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove tanks, 0 - 50 gals |  | 0 |  |  | 0 | -30% | 0 | 0 | 0.6319 | crew hrs/comp | 1 | 0 | UCF 56 - Tanks <50 gals.
|  |  | Clean | Remove tanks, 50 - 300 gals |  | 0 |  |  | 0 | -30% | 0 | 0 | 1.625 | crew hrs/comp | 1 | 0 | UCF 57 - Tanks 50 - 300 gals.
|  |  | Clean | Remove tanks, 300 - 4k gals |  | 2 |  |  | 839 | -30% | 1090.7 | 1.3465 | 8.7567 | crew hrs/comp | 1 | 17.5134 | UCF 58 - Tanks 4k - 15k gals.
|  |  | Clean | Miscellaneous equipment |  | 0 |  |  | 0 | -30% | 0 | 0 | 2.5 | crew hrs/comp | 1 | 0 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 1090.7 | 1.3465 |  |  |  | 17.5134
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 1090.7 | 1.3465 | 0 | 673.2716 | 4362.8 | 5036.0716
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.11.1.4 | Decontaminate Structure |  |  |  | A | 870.1619 | 1 | 870.1619 | 0 | 6022.5493 | 0 | 0 | 0 | 19137.6667 | 0 | 692739.41 | 0 | 1316069.2276 | 0 | 0 | 0 | 114510.2952 | 0 | 2123318.9328
[8 empty] | Clean |  | 332.6808 | [17 empty] | 2.9986 |  | 0.125
[8 empty] | LLW |  | 537.6115 | [17 empty] | 4.8457 |  |  |  | 0.039336
|  | 1.11.1.4.1 | Pool |  |  |  | A | 88 | 1 | 88 | 0 | 57.2 |  |  |  | 0 |  |  | 0 | 3378.9888 |  |  |  | 0 |  | 3378.9888
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  |  | Weight, lbs | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Contaminated | Decontaminate concrete - 1/4" |  |  | 0 | 0 | 0 | -30% | 0 | 0 | 0.04 | crew hr/sq. ft. | 1 | 0 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
|  |  | Contaminated | Decon concrete surfaces - 1/2" |  |  | 6600 | 1100 | 44 | -30% | 57.2 | 0.66 | 0.08 | crew hr/sq. ft. | 1 | 88 | Average UCF 7 & 8 - Concrete surfaces 1" deep
[11 empty] | 57.2 | 0.66 |  |  |  | 88
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 57.2 | 0.66 | 0 | 0 | 3378.9888 | 3378.9888 | Packaged in B-25 boxes
|  | 1.11.1.4.2 | Reactor shield |  |  |  | A | 637.5219 | 1 | 637.5219 | 0 | 5864 |  |  | 0 | 19123 |  | 692739.41 |  | 1306745.3233 |  |  | 0 | 114442.575 |  | 2113927.3083
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Area, sq ft. | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Contaminated | Remove Magnitite concrete |  |  |  | 3225 | 748200 | 0% | 3225 | 18.705 | 0.052 | crew hrs/cu ft | 1 | 167.7 | See wire cutting calculation
|  |  | Clean | Remove heavy concrete |  |  |  | 2639 | 461825 | 0% | 2639 | 11.5456 | 0.052 | crew hrs/cu ft | 1 | 137.228 | See wire cutting calculation
|  |  | Contaminated | Remove heavy concrete |  |  |  | 2639 | 461825 | 0% | 2639 | 11.5456 | 0.052 | crew hrs/cu ft | 1 | 137.228 | See wire cutting calculation
|  |  | Clean | Remove concrete |  |  |  | 16484 | 2472600 | -30% | 21429.2 | 61.815 | 25 | cu. yd./day | 1 | 195.3659 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Using just heavy equipment but heavily reinforced.
|  |  | Clean | Remove steel liner |  |  |  |  | 0 | -30% | 0 | 0 | 0.04 | hrs/sq ft | 1 | 0 | UCF 2 - Clean free standing steel liner removal
[8 empty] | 24987 | 4144450 |  | 29932.2 | 103.6112 |  |  |  | 637.5219
[12 empty] | Diamond Wire | Diamond Wire
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $ | cutting $/cuft | cutting
|  |  |  | Clean | 16484 | 2472600 | 61.815 | 0 | 30907.5 | 65523.9 | 96431.4
|  |  |  | Heavy clean | 2639 | 461825 | 11.5456 | 0 | 5772.8125 | 12238.3625 | 18011.175 | 81.47 | 214999.33 | Cut into 40,000lb blocks, one block per shipment
|  |  |  | Heavy contam | 5864 | 1210025 | 30.2506 | 0 | 0 | 1306745.3233 | 1306745.3233 | 81.47 | 477740.08 | Cut into 40,000lb blocks, one block per shipment
|  |  |  | Mixed | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0 | Packaged in 30 cu yd containers
|  | 1.11.1.4.3 | Inside building minus shield |  |  |  | A | 144.64 | 1 | 144.64 | 0 | 101.3493 |  |  |  | 14.6667 |  |  | 0 | 5944.9155 |  |  |  | 67.7202 |  | 6012.6357
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Weight, lbs | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove metal wall |  |  |  | 14.6667 |  | 0% | 14.6667 | 0.018107 | 50 | cu. yd./day | 1 | 0.086914 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Contaminated | Remove metal wall |  |  |  | 7.3333 |  | 0% | 7.3333 | 0.076389 | 50 | cu. yd./day | 1 | 0.043457 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Contaminated | Decontaminate concrete - 1/4" |  |  | 7158 | 2386 | 47.72 | -30% | 62.036 | 0.7158 | 0.04 | crew hr/sq. ft. | 1 | 95.44 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
|  |  | Contaminated | Decon concrete surfaces - 1/2" |  |  | 3690 | 615 | 24.6 | -30% | 31.98 | 0.369 | 0.08 | crew hr/sq. ft. | 1 | 49.2 | Average UCF 7 & 8 - Concrete surfaces 1" deep
[11 empty] | 94.016 | 1.0848 |  |  |  | 144.64
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 14.6667 | 0.018107 | 0 | 9.0535 | 58.6667 | 67.7202
|  |  |  | Contaminated |  | 101.3493 | 1.1612 | 0 | 0 | 5944.9155 | 5944.9155 | Packaged in B-25 boxes
|  | 1.11.1.5. | Remove ventilation |  |  |  | A | 121.3 | 1 | 121.3 | 0 | 1136.2 |  |  |  | 2108.4 |  |  | 0 | 60593.546 |  |  |  | 9735.0815 |  | 70328.6275
[8 empty] | Clean |  | 63.74 | [17 empty] | 0.57451 |  | 0.013771
[8 empty] | LLW |  | 57.56 | [17 empty] | 0.51881 |  |  |  | 0.007421
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | HVAC equipment - < 1,000lbs |  | 7 |  |  | 148 | -30% | 192.4 | 0.23753 | 2 | crew hrs/comp | 1 | 14 | UCF 63 - < 1,000 lbs
|  |  | Clean | HVAC equipment - 1,000 - 10,000 lbs |  | 2 |  |  | 291 | -30% | 378.3 | 0.46704 | 4 | crew hrs/comp | 1 | 8 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | HVAC equipment - > 10,000 lbs |  | 1 |  |  | 844 | -30% | 1097.2 | 1.3546 | 13 | crew hrs/comp | 1 | 13 | UCF 66 > 10,000 lbs
|  |  | Contaminated | HVAC equipment - < 1,000lbs |  | 1 |  |  | 24 | -30% | 31.2 | 0.325 | 3 | crew hrs/comp | 1 | 3 | UCF 63 - < 1,000 lbs
|  |  | Contaminated | HVAC equipment - 1,000 - 10,000 lbs |  | 2 |  |  | 625 | -30% | 812.5 | 8.4635 | 7 | crew hrs/comp | 1 | 14 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Contaminated | HVAC equipment - > 10,000 lbs | [5 empty] | -30% | 0 | 0 | 20 | crew hrs/comp | 1 | 0 | UCF 66 - 1,000 - 10,000 lbs
|  |  | Contaminated | HVAC duct |  |  | 338 |  | 585 | 50% | 292.5 | 3.0469 | 0.12 | crew hrs/ft | 1 | 40.56 | UCF 69 - Remove Contaminated Ductwork
|  |  | Clean | HVAC duct |  |  | 479 |  | 881 | 50% | 440.5 | 0.54383 | 0.06 | crew hrs/ft | 1 | 28.74 | UCF 69 - Remove Ductwork
[11 empty] | 3244.6 | 14.4384 |  |  |  | 121.3
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 2108.4 | 2.603 | 0 | 1301.4815 | 8433.6 | 9735.0815
|  |  |  | Contaminated |  | 1136.2 | 11.8354 | 0 | 0 | 60593.546 | 60593.546
|  | 1.11.1.6 | Final Survey of Structure |  |  |  | A | 160 | 1.595 | 255.2 | 0 | [7 empty] | 0 | [6 empty] | 0 |  | 2.3002
|  |  |  | Estimated Duration | 160 | hrs
|  | 1.11.2 | 331 Service Building |  |  |  |  | 899.9557 |  | 995.1557 | 0 | 35.5563 | 34.71 | 6.0662 | 0 | 4134.7551 | 174.2 | 0 | 0 | 1923.0958 | 802.4626 | 0 | 0 | 19091.3383 | 77477.1712 | 99294.0679
|  | 1.11.2.1 | Remove Miscellaneous Material |  |  |  | A | 0 | 1 | 0 | 0 |  |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  | 0
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Miscellaneous equipment |  | 0 |  |  | 0 | -30% | 0 | 0 | 2.5 | crew hrs/comp | 1 | 0 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 0 | 0 |  |  |  | 0
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.11.2.2 | Remove Asbestos & other hazardous material |  |  |  | A | 373.7078 | 1 | 373.7078 | 0 |  | 34.71 | 6.0662 | 0 | 553.67 | 174.2 |  | 0 |  | 802.4626 |  | 0 | 2556.4516 | 77477.1712 | 80836.0854
[8 empty] | Clean |  | 100.9352
[8 empty] | LLW |  | 0
[8 empty] | Hazardous |  | 272.7725
[8 empty] | Mixed |  | 0
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove asbestos pipe insulation |  |  | 148.25 |  | 12.4 | -30% | 16.12 | 0.019901 | 0.11 | crew hrs/ft | 1.3 | 21.1998 | 2009 mean, p33, 02 82 13.43 1200 with glove bags | [10 empty] | 197.34 | /foot | 0.10874 | cu. ft./ft |  |  | cu. ft./sq.ft
|  |  | Clean | Remove asbestos tile |  |  |  | 5320 | 331 | -30% | 430.3 | 0.53123 | 0.003 | crew hrs/sq. ft. | 1.3 | 20.748 | 2009 mean, p33, 02 82 13.43 5000 | [10 empty] | 0.33722 | /sq ft | 0.080883 | cu. ft./sq.ft
|  |  | Hazardous | Remove lead liner |  |  |  |  | 120 | -30% | 156 | 205.556 | 8 | hrs | 1.43 | 11.44 | Estimated
|  |  | Hazardous | Remove lead shield door |  | 1 |  |  | 14 | -30% | 18.2 | 2.4752 | 8 | hrs | 1.43 | 11.44 | Estimated
|  |  | Hazardous | Fluorescent light bulbs |  | 534 |  |  | 26.7 | -30% | 34.71 | 4.7206 | 0.25 | crew hrs/comp | 1.43 | 190.905 | Estimated
|  |  | Clean | Fluorescent fixtures |  | 165 |  |  | 82.5 | -30% | 107.25 | 0.13241 | 0.25 | crew hrs/comp | 1.43 | 58.9875 | Estimated
|  |  | Hazardous | Fluorescent light ballasts, lbs |  | 165 | 495 |  |  | -30% | 0 | 0.825 | 0.25 | crew hrs/comp | 1.43 | 58.9875 | Estimated
[11 empty] | 762.58 | 214.2603 |  |  |  | 373.7078
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 553.67 | 0.68354 | 0 | 341.7716 | 2214.68 | 2556.4516
|  |  |  | Lead | 123333.6 | 174.2 | 208.0312 | 13522.028 | 2288.3432 | 61666.8 | 77477.1712
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Hazardous |  | 34.71 | 4.7206 | 306.8364 | 51.9262 | 133.5 | 492.2626
|  |  |  | Hazardous, ballasts | 495 | 6.0662 | 0.825 | 53.625 | 9.075 | 247.5 | 310.2
|  | 1.11.2.3 | Remove systems and components |  |  |  |  | 356.648 |  | 356.648 | 0 | 30.8763 | 0 | 0 | 0 | 3581.0851 | 0 | 0 | 0 | 1646.6331 | 0 | 0 | 0 | 16534.8867 | 0 | 18181.5198
[8 empty] | Clean |  | 351.734 | [17 empty] | 3.1703 |  | 0.13109
[8 empty] | LLW |  | 4.914 | [17 empty] | 0.044292 |  |  |  | 0.0011303
[8 empty] | Hazardous |  | 0 | [17 empty] | 0 |  |  | 0
[8 empty] | Mixed |  | 0 | [22 empty] | 0
|  | 1.11.2.3.1 | Remove piping |  |  |  | A | 91.808 | 1 | 91.808 | 0 | 30.8763 |  |  |  | 236.5851 |  |  | 0 | 1646.6331 |  |  |  | 1092.3805 |  | 2739.0136
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | 0 - 2.5" pipe, clean |  |  | 5165 |  | 69.1916 | -30% | 89.949 | 0.11105 | 0.013333 | crew hrs/ft | 1 | 68.8667 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 3 - 4" pipe, clean |  |  | 954 |  | 67.6371 | -30% | 87.9283 | 0.10855 | 0.017667 | crew hrs/ft | 1 | 16.854 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 5 - 6" pipe, clean |  |  | 11 |  | 2.1599 | -30% | 2.8078 | 0.0034664 | 0.10667 | crew hrs/ft | 1 | 1.1733 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | 8 - 14" pipe, clean | [5 empty] | -30% | 0 | 0 | 0.178 | crew hrs/ft | 1 | 0 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | Non-asbestos insulation - removed with pipe |  |  |  |  | 43 | -30% | 55.9 | 0.069012
|  |  | Contaminated | 0 - 2.5" pipe, contam. |  |  | 273 |  | 23.751 | -30% | 30.8763 | 0.32163 | 0.013333 | crew hrs/ft | 1.35 | 4.914 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. )
|  |  | Contaminated | 3 - 4" pipe, contam. | [5 empty] | -30% | 0 | 0 | 0.017667 | crew hrs/ft | 1.35 | 0 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. )
|  |  | Contaminated | 5 - 6" pipe, contam. | [5 empty] | -30% | 0 | 0 | 0.10667 | crew hrs/ft | 1.35 | 0 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3. )
[11 empty] | 267.4614 | 0.61371 |  |  |  | 91.808
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 236.5851 | 0.29208 | 0 | 146.0402 | 946.3404 | 1092.3805
|  |  |  | Contaminated |  | 30.8763 | 0.32163 | 0 | 0 | 1646.6331 | 1646.6331
|  | 1.11.2.3.2 | Remove ventilation |  |  |  | A | 227.34 | 1 | 227.34 | 0 | 0 |  |  |  | 3249.6 |  |  | 0 | 0 |  |  |  | 15004.3259 |  | 15004.3259
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | HVAC equipment - < 1,000lbs |  | 51 |  |  | 905 | -30% | 1176.5 | 1.4525 | 2 | crew hrs/comp | 1 | 102 | UCF 63 - < 1,000 lbs
|  |  | Clean | HVAC equipment - 1,000 - 10,000 lbs |  | 2 |  |  | 244 | -30% | 317.2 | 0.3916 | 4 | crew hrs/comp | 1 | 8 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | HVAC equipment - > 10,000 lbs |  | 1 |  |  | 576 | -30% | 748.8 | 0.92444 | 13 | crew hrs/comp | 1 | 13 | UCF 66 > 10,000 lbs
|  |  | Contaminated | HVAC equipment - < 1,000lbs | [5 empty] | -30% | 0 | 0 | 3 | crew hrs/comp | 1 | 0 | UCF 63 - < 1,000 lbs
|  |  | Contaminated | HVAC equipment - 1,000 - 10,000 lbs | [5 empty] | -30% | 0 | 0 | 7 | crew hrs/comp | 1 | 0 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Contaminated | HVAC equipment - > 10,000 lbs | [5 empty] | -30% | 0 | 0 | 20 | crew hrs/comp | 1 | 0 | UCF 66 - 1,000 - 10,000 lbs
|  |  | Contaminated | HVAC duct | [5 empty] | 50% | 0 | 0 | 0.12 | crew hrs/ft | 1 | 0 | UCF 69 - Remove Contaminated Ductwork
|  |  | Clean | HVAC duct |  |  | 1739 |  | 2014.2 | 50% | 1007.1 | 1.2433 | 0.06 | crew hrs/ft | 1 | 104.34 | UCF 69 - Remove Ductwork
[11 empty] | 3249.6 | 4.0119 |  |  |  | 227.34
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 3249.6 | 4.0119 | 0 | 2005.9259 | 12998.4 | 15004.3259
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.11.2.3.3 | Remove large equipment |  |  |  | A | 37.5 | 1 | 37.5 | 0 | 0 |  |  |  | 94.9 |  |  | 0 | 0 |  |  |  | 438.1802 |  | 438.1802
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove tanks, 0 - 50 gals | [5 empty] | -30% | 0 | 0 | 0.6319 | crew hrs/comp | 1 | 0 | UCF 56 - Tanks <50 gals.
|  |  | Clean | Remove tanks, 50 - 300 gals | [5 empty] | -30% | 0 | 0 | 1.625 | crew hrs/comp | 1 | 0 | UCF 57 - Tanks 50 - 300 gals.
|  |  | Clean | Remove tanks, 300 - 4k gals |  | 0 |  |  | 0 | -30% | 0 | 0 | 8.7567 | crew hrs/comp | 1 | 0 | UCF 58 - Tanks 4k - 15k gals.
|  |  | Contaminated | Miscellaneous equipment |  | 0 |  |  | 0 | -30% | 0 | 0 | 4 | crew hrs/comp | 1 | 0 | UCF 64 - 300 to 1,000 lbs
|  |  | Clean | Miscellaneous equipment |  | 15 |  |  | 73 | -30% | 94.9 | 0.11716 | 2.5 | crew hrs/comp | 1 | 37.5 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 94.9 | 0.11716 |  |  |  | 37.5
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 94.9 | 0.11716 | 0 | 58.5802 | 379.6 | 438.1802
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.11.2.4 | Decontaminate Structure |  |  |  | A | 9.6 | 1 | 9.6 | 0 | 4.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.4627 | 0 | 0 | 0 | 0 | 0 | 276.4627 |  | 0.48495 |  |  |  | 0.00017132
|  | 1.11.2.4.1 | Service Floor |  |  |  | A | 9.6 | 1 | 9.6 | 0 | 4.68 |  |  |  | 0 |  |  | 0 | 276.4627 |  |  |  | 0 |  | 276.4627
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  |  | Weight, lbs | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Contaminated | Decontaminate concrete - 1/4" |  |  | 0 |  |  | -30% | 0 | 0 | 0.04 | crew hr/sq. ft. | 1 | 0 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
|  |  | Contaminated | Decon concrete surfaces - 1/2" |  |  | 540 | 120 | 3.6 | -30% | 4.68 | 0.054 | 0.08 | crew hr/sq. ft. | 1 | 9.6 | Average UCF 7 & 8 - Concrete surfaces 1" deep
[11 empty] | 4.68 | 0.054 |  |  |  | 9.6
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 4.68 | 0.054 | 0 | 0 | 276.4627 | 276.4627 | Packaged in B-25 boxes
|  | 1.11.2.5 | Final Survey of Structure |  |  |  | A | 160 | 1.595 | 255.2 | 0 | [7 empty] | 0 | [6 empty] | 0 |  | 12.8917
|  |  |  | Estimated Duration | 160 | hrs
|  | 1.11.3 | 331A Reboiler |  |  |  |  | 456.688 |  | 551.888 | 0 | 5.746 | 5.2 | 0.73529 | 0 | 2903.7716 | 19 | 0 | 0 | 339.4348 | 111.3472 | 0 | 0 | 13407.5379 | 8429.92 | 22288.2399
|  | 1.11.3.1 | Remove Miscellaneous Material |  |  |  | A | 0 | 1 | 0 | 0 |  |  |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  | 0
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Miscellaneous equipment |  | 0 |  |  |  | 0% | 0 | 0 | 0 | days | 1 | 0
[11 empty] | 0 | 0 |  |  |  | 0
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.11.3.2 | Remove Asbestos & other hazardous material |  |  |  | A | 99.9024 | 1 | 99.9024 | 0 |  | 5.2 | 0.73529 | 0 | 355.6245 | 19 |  | 0 |  | 111.3472 |  | 0 | 1642.0193 | 8429.92 | 10183.2865
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove asbestos pipe insulation |  |  | 130.2 |  | 251.865 | -30% | 327.4245 | 0.40423 | 0.11 | crew hrs/ft | 1.3 | 18.6186 | 2009 mean, p33, 02 82 13.43 1200 with glove bags | [10 empty] | 197.34 | /foot | 2.5148 | cu. ft./ft
|  |  | Clean | Remove asbestos tile |  |  |  | 442 | 4 | -30% | 5.2 | 0.0064198 | 0.003 | crew hrs/sq. ft. | 1.3 | 1.7238 | 2009 mean, p33, 02 82 13.43 5000 | [10 empty] | 5.382 | /sq ft | 0.011765 | cu. ft./sq.ft
|  |  | Clean | Remove Asbestos safe door |  | 1 |  |  | 10 | 0% | 10 | 0.012346 | 4 | hrs | 1.3 | 5.2 | Estimated
|  |  | Mixed | Remove transite panels | [5 empty] | -30% | 0 | 0 | 0.008 | crew hrs/sq. ft. | 1.5 | 0 | 2009 mean, p34, 02 82 13.43 8000
|  |  | Lead | Remove lead doors |  | 2 |  |  | 19 | 0% | 19 | 22.42 | 8 | hrs/each | 1.43 | 22.88 | Estimated
|  |  | Hazardous | Mercury Switches | [5 empty] | -30% | 0 | 0 | 6 | hrs | 1.43 | 8.58 | Estimated
|  |  | Hazardous | Fluorescent light bulbs |  | 80 |  |  | 4 | -30% | 5.2 | 0.7072 | 0.25 | crew hrs/comp | 1.43 | 28.6 | Estimated
|  |  | Clean | Fluorescent fixtures |  | 20 |  |  | 10 | -30% | 13 | 0.016049 | 0.25 | crew hrs/comp | 1.43 | 7.15 | Estimated
|  |  | Hazardous - B | Fluorescent light ballasts, lbs |  | 20 | 60 |  |  | -30% | 0 | 0.1 | 0.25 | crew hrs/comp | 1.43 | 7.15 | Estimated
[11 empty] | 379.8245 | 23.6662 |  |  |  | 99.9024
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 355.6245 | 0.43904 | 0 | 219.5213 | 1422.498 | 1642.0193
|  |  |  | Lead | 13452 | 19 | 22.42 | 1457.3 | 246.62 | 6726 | 8429.92
|  |  |  | Mixed |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Hazardous |  | 5.2 | 0.7072 | 45.968 | 7.7792 | 20 | 73.7472
|  |  |  | Hazardous, ballasts | 60 | 0.73529 | 0.1 | 6.5 | 1.1 | 30 | 37.6
|  | 1.11.3.3 | Remove systems and components |  |  |  |  | 187.9456 |  | 187.9456 | 0 | 0 | 0 | 0 | 0 | 2548.1471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11765.5186 | 0 | 11765.5186
[8 empty] | Clean |  | 187.9456 | [17 empty] | 30.449 |  | 0.29915
[8 empty] | LLW |  | 0 | [17 empty] | 0 |  |  |  | 0
[8 empty] | Hazardous |  | 0 | [17 empty] | 0 |  |  | 0
[8 empty] | Mixed |  | 0 | [22 empty] | 0
|  | 1.11.3.3.1 | Remove piping |  |  |  | A | 118.5887 | 1 | 118.5887 | 0 | 0 |  |  |  | 482.5371 |  |  | 0 | 0 |  |  |  | 2228.0107 |  | 2228.0107
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | 0 - 2.5" pipe, clean |  |  | 2079 |  | 33.1995 | -30% | 43.1594 | 0.053283 | 0.013333 | crew hrs/ft | 1 | 27.72 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 3 - 4" pipe, clean |  |  | 670 |  | 57.0179 | -30% | 74.1232 | 0.09151 | 0.017667 | crew hrs/ft | 1 | 11.8367 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 5 - 6" pipe, clean | [5 empty] | -30% | 0 | 0 | 0.10667 | crew hrs/ft | 1 | 0 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | 8 - 14" pipe, clean |  |  | 444 |  | 242.165 | -30% | 314.8145 | 0.38866 | 0.178 | crew hrs/ft | 1 | 79.032 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | Non-asbestos insulation - removed with pipe |  |  |  |  | 38.8 | -30% | 50.44 | 0.062272
|  |  | Contaminated | 0 - 2.5" pipe, contam. | [5 empty] | -30% | 0 | 0 | 0.013333 | crew hrs/ft | 1.35 | 0 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Contaminated | 3 - 4" pipe, contam. | [5 empty] | -30% | 0 | 0 | 0.017667 | crew hrs/ft | 1.35 | 0 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. )
|  |  | Contaminated | 5 - 6" pipe, contam. | [5 empty] | -30% | 0 | 0 | 0.10667 | crew hrs/ft | 1.35 | 0 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3. )
|  |  | Contaminated | 8 - 16" pipe, contam. | [5 empty] | -30% | 0 | 0 | 0.178 | crew hrs/ft | 1.35 | 0 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
[11 empty] | 482.5371 | 0.59572 |  |  |  | 118.5887
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 482.5371 | 0.59572 | 0 | 297.8624 | 1930.1483 | 2228.0107
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.11.3.3.2 | Remove ventilation |  |  |  | A | 49.6 | 1 | 49.6 | 0 | 0 |  |  |  | 2028.3 |  |  | 0 | 0 |  |  |  | 9365.237 |  | 9365.237
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | HVAC equipment - < 1,000lbs |  | 4 |  |  | 199 | -30% | 258.7 | 0.31938 | 2 | crew hrs/comp | 1 | 8 | UCF 63 - < 1,000 lbs
|  |  | Clean | HVAC equipment - 1,000 - 10,000 lbs |  | 5 |  |  | 1062 | -30% | 1380.6 | 1.7044 | 4 | crew hrs/comp | 1 | 20 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Clean | HVAC equipment - > 10,000 lbs | [5 empty] | -30% | 0 | 0 | 13 | crew hrs/comp | 1 | 0 | UCF 66 > 10,000 lbs
|  |  | Contaminated | HVAC equipment - < 1,000lbs | [5 empty] | -30% | 0 | 0 | 3 | crew hrs/comp | 1 | 0 | UCF 63 - < 1,000 lbs
|  |  | Contaminated | HVAC equipment - 1,000 - 10,000 lbs |  | 0 |  |  | 0 | -30% | 0 | 0 | 7 | crew hrs/comp | 1 | 0 | UCF 65 - 1,000 - 10,000 lbs
|  |  | Contaminated | HVAC equipment - > 10,000 lbs | [5 empty] | -30% | 0 | 0 | 20 | crew hrs/comp | 1 | 0 | UCF 66 - 1,000 - 10,000 lbs
|  |  | Contaminated | HVAC duct |  |  | 0 |  | 0 | 50% | 0 | 0 | 0.12 | crew hrs/ft | 1 | 0 | UCF 69 - Remove Contaminated Ductwork
|  |  | Clean | HVAC duct |  |  | 360 |  | 778 | 50% | 389 | 0.48025 | 0.06 | crew hrs/ft | 1 | 21.6 | UCF 69 - Remove Ductwork
[11 empty] | 2028.3 | 2.5041 |  |  |  | 49.6
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 2028.3 | 2.5041 | 0 | 1252.037 | 8113.2 | 9365.237
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.11.3.3.3 | Remove large equipment |  |  |  | A | 19.7569 | 1 | 19.7569 | 0 | 0 |  |  |  | 37.31 |  |  | 0 | 0 |  |  |  | 172.2709 |  | 172.2709
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove tanks, 0 - 50 gals |  | 1 |  |  | 0.7 | -30% | 0.91 | 0.0011235 | 0.6319 | crew hrs/comp | 1 | 0.6319 | UCF 56 - Tanks <50 gals.
|  |  | Clean | Remove tanks, 50 - 300 gals |  | 1 |  |  | 7 | -30% | 9.1 | 0.011235 | 1.625 | crew hrs/comp | 1 | 1.625 | UCF 57 - Tanks 50 - 300 gals.
|  |  | Clean | Remove tanks, 300 - 4k gals | [5 empty] | -30% | 0 | 0 | 8.7567 | crew hrs/comp | 1 | 0 | UCF 58 - Tanks 4k - 15k gals.
|  |  | Contaminated | Remove tanks, 300 - 4k gals | [5 empty] | -30% | 0 | 0 | 26.76 | crew hrs/comp | 1 | 0 | UCF 58 - Tanks 4k - 15k gals.
|  |  | Contaminated | Miscellaneous equipment | [5 empty] | -30% | 0 | 0 | 4 | crew hrs/comp | 1 | 0 | UCF 64 - 300 to 1,000 lbs
|  |  | Clean | Miscellaneous equipment |  | 7 |  |  | 21 | -30% | 27.3 | 0.033704 | 2.5 | crew hrs/comp | 1 | 17.5 | UCF 64 - 300 to 1,000 lbs
[11 empty] | 37.31 | 0.046062 |  |  |  | 19.7569
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 37.31 | 0.046062 | 0 | 23.0309 | 149.24 | 172.2709
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.11.3.4 | Decontaminate Structure |  |  |  | A | 8.84 | 1 | 8.84 | 0 | 5.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339.4348 | 0 | 0 | 0 | 0 | 0 | 339.4348 |  | 1.4322 |  |  |  | 0.00067457
|  | 1.11.3.4.1 | Service Floor |  |  |  | A | 8.84 | 1 | 8.84 | 0 | 5.746 |  |  |  | 0 |  |  | 0 | 339.4348 |  |  |  | 0 |  | 339.4348
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  |  | Weight, lbs | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Contaminated | Decontaminate concrete - 1/4" |  |  | 663 | 221 | 4.42 | -30% | 5.746 | 0.0663 | 0.04 | crew hr/sq. ft. | 1 | 8.84 | Average UCF 7 & 8 - Concrete surfaces 1/4" deep
|  |  | Contaminated | Decon concrete surfaces - 1/2" |  |  | 0 |  |  | -30% | 0 | 0 | 0.08 | crew hr/sq. ft. | 1 | 0 | Average UCF 7 & 8 - Concrete surfaces 1" deep
[11 empty] | 5.746 | 0.0663 |  |  |  | 8.84
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated |  | 5.746 | 0.0663 | 0 | 0 | 339.4348 | 339.4348 | Packaged in B-25 boxes
|  | 1.11.3.5 | Final Survey of Structure |  |  |  | A | 160 | 1.595 | 255.2 | 0 | [7 empty] | 0 | [6 empty] | 0 |  | 41.3449
|  |  |  | Estimated Duration | 160 | hrs
| 1.12 | Demolition Readiness Review (Labor costs included in Undistributed costs) |  |  |  |  | B | 80 | 1 | 80 | 0 | [7 empty] | 0 | [6 empty] | 0
| 1.13 | Remove building (Labor costs included in Undistributed costs) | [5 empty] | 5252.3013 |  | 5252.3013 | 0 | 155.9608 | 0 | 0 | 0 | 271951.4394 | 0 | 0 | 0 | 8317.3897 | 0 | 0 | 0 | 1236885.1983 | 0 | 1245202.588
Assumptions:
1. All waste will be disposed of at the local landfill - considered a controlled landfill
2. Productivity factors are included in the rates, unless otherwise specified.
3. All waste will be packaged in 30 cubic yard containers.
|  | 1.13.1 | Remove shell above grade |  |  |  |  | 1348.9041 |  | 1348.9041 | 0 | 0 | 0 | 0 | 0 | 75555.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351516.3091 | 0 | 351516.3091 |  | 12.1582 |  | 0.49348
|  | 1.13.1.1 | Shell |  |  |  | A | 1340.1752 | 1 | 1340.1752 | 0 |  |  |  |  | 73910.3 |  |  | 0 |  |  |  |  | 343956.1017 |  | 343956.1017
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Area, sq ft. | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove grating |  |  |  | 611 |  | -30% | 794.3 | 0.75432 | 50 | cu. yd./day | 1 | 3.6207 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  | 123 | 17835 | -30% | 159.9 | 0.44588 | 50 | cu. yd./day | 1 | 0.72889 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 26241 | 3936150 | -30% | 34113.3 | 98.4038 | 25 | cu. yd./day | 1 | 311.0044 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Using just heavy equipment but heavily reinforced.
|  |  | Clean | Remove concrete floor |  |  |  | 24774 | 3716100 | -30% | 32206.2 | 92.9025 | 25 | cu. yd./day | 1 | 293.6178 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Using just heavy equipment but heavily reinforced.
|  |  | Clean | Remove structural steel |  |  |  | 498 | 29910 | 0% | 498 | 0.74775 | 0.7 | crew hr/ton | 1 | 10.4685 | UCF 8 - structural steel
|  |  | Clean | Remove insulation |  |  |  | 3769 |  | -30% | 4899.7 | 6.049 | 50 | cu. yd./day | 1 | 22.3348 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove steel liner |  | 17460 |  | 953 | 466970 | -30% | 1238.9 | 11.6743 | 0.04 | hrs/sq ft | 1 | 698.4 | UCF 2 - Clean free standing steel liner removal
[11 empty] | 73910.3 | 210.9775 |  |  |  | 1340.1752
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 73910.3 | 8166965 | 210.9775 | 0 | 105488.7292 | 238467.3725 | 343956.1017
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0 | Packaged in B-25 boxes
|  | 1.13.1.2 | HVAC building and truck entrance |  |  |  | A | 8.7289 | 1 | 8.7289 | 0 |  |  |  |  | 1644.9 |  |  | 0 |  |  |  |  | 7560.2074 |  | 7560.2074
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove sand fill |  |  |  | 0 | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  | 0 | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 0 | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  | 228 | 34200 | -30% | 296.4 | 0.855 | 50 | cu. yd./day | 1 | 1.3511 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove metal wall |  |  |  | 900 |  | 0% | 900 | 1.1111 | 50 | cu. yd./day | 1 | 5.3333 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove Insulated roof panels |  |  |  | 345 |  | -30% | 448.5 | 0.5537 | 50 | cu. yd./day | 1 | 2.0444 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove insulation |  |  |  | 0 |  | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove stone |  |  |  | 0 |  | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 1473 | 34200 |  | 1644.9 | 2.5198 |  |  |  | 8.7289
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 1644.9 | 34200 | 2.5198 | 0 | 1259.9074 | 6300.3 | 7560.2074
|  | 1.13.2 | Remove Service building |  |  |  |  | 291.9748 |  | 291.9748 | 0 | 0 | 0 | 0 | 0 | 39529.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179426.2432 | 0 | 179426.2432 |  | 14.7494 |  | 1.447
|  | 1.13.2.1 | Roof |  |  |  | A | 28.2507 | 1 | 28.2507 | 0 |  |  |  |  | 4161.9 |  |  | 0 |  |  |  |  | 17590.4412 |  | 17590.4412
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove brick |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 1669 | 250350 | -30% | 2169.7 | 6.2588 | 50 | cu. yd./day | 1 | 9.8904 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove structural steel |  |  |  | 570 | 32310 | 0% | 570 | 0.80775 | 0.7 | crew hr/ton | 1 | 11.3085 | UCF 8 - structural steel
|  |  | Clean | Remove metal wall |  |  |  | 416 |  | 0% | 416 | 0.51358 | 50 | cu. yd./day | 1 | 2.4652 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove insulation |  |  |  | 573 |  | -30% | 744.9 | 0.91963 | 50 | cu. yd./day | 1 | 3.3956 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove stone |  |  |  | 201 |  | -30% | 261.3 | 0.32259 | 50 | cu. yd./day | 1 | 1.1911 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[11 empty] | 4161.9 | 8.8223 |  |  |  | 28.2507
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 4161.9 | 282660 | 8.8223 | 0 | 4411.1512 | 13179.29 | 17590.4412
|  | 1.13.2.2 | Main floor |  |  |  | A | 198.1249 | 1 | 198.1249 | 0 |  |  |  |  | 24520.3 |  |  | 0 |  |  |  |  | 113165.7148 |  | 113165.7148
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Area, sq ft | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove brick |  |  |  | 1743 | 252735 | -30% | 2265.9 | 6.3184 | 50 | cu. yd./day | 1 | 10.3289 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  | 7488 | 1085760 | -30% | 9734.4 | 27.144 | 50 | cu. yd./day | 1 | 44.3733 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  | 6904 | 1035600 | -30% | 8975.2 | 25.89 | 50 | cu. yd./day | 1 | 40.9126 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Gypsum wall |  |  |  | 953 |  | -30% | 1238.9 | 1.5295 | 50 | cu. yd./day | 1 | 5.6474 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove suspended ceiling |  |  |  | 76 |  | -30% | 98.8 | 0.12198 | 50 | cu. yd./day | 1 | 0.45037 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove structural steel |  |  |  | 1160 | 245249 | 0% | 1160 | 6.1312 | 0.7 | crew hr/ton | 1 | 85.8372 | UCF 8 - structural steel
|  |  | Clean | Remove insulation |  |  |  | 584 |  | -30% | 759.2 | 0.93728 | 50 | cu. yd./day | 1 | 3.4607 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove carpet |  |  | 4257 | 128 |  | 0% | 128 | 0.15802 | 0.0015 | crew hrs/sq. ft. | 1 | 6.3855 | Productivity estimated at 2x that of VAT removal.
|  |  | Clean | Remove tile |  |  |  | 123 |  | -30% | 159.9 | 0.19741 | 50 | cu. yd./day | 1 | 0.72889 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 19159 | 2619344 |  | 24520.3 | 68.4278 |  |  |  | 198.1249
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 24520.3 | 2619344 | 68.4278 | 0 | 34213.8988 | 78951.816 | 113165.7148
|  | 1.13.2.3 | Basement |  |  |  | A | 56.817 | 1 | 56.817 | 0 |  |  |  |  | 8920.8 |  |  | 0 |  |  |  |  | 40083.8656 |  | 40083.8656
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Area, sq ft | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove brick |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  | 5769 | 836505 | -30% | 7499.7 | 20.9126 | 50 | cu. yd./day | 1 | 34.1867 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove structural steel |  |  |  | 62 | 30380 | 0% | 62 | 0.7595 | 0.7 | crew hr/ton | 1 | 10.633 | UCF 8 - structural steel
|  |  | Clean | Remove suspended ceiling |  |  |  | 235 |  | -30% | 305.5 | 0.37716 | 50 | cu. yd./day | 1 | 1.3926 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Gypsum wall |  |  |  | 346 |  | -30% | 449.8 | 0.55531 | 50 | cu. yd./day | 1 | 2.0504 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove carpet |  |  | 4257 | 128 |  | 0% | 128 | 0.15802 | 0.0015 | crew hrs/sq. ft. | 1 | 6.3855 | Productivity estimated at 2x that of VAT removal.
|  |  | Clean | Remove grating |  |  |  | 366 |  | -30% | 475.8 | 0.58741 | 50 | cu. yd./day | 1 | 2.1689 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 6906 | 866885 |  | 8920.8 | 23.35 |  |  |  | 56.817
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 8920.8 | 866885 | 23.35 | 0 | 11675.0131 | 28408.8525 | 40083.8656
|  | 1.13.2.4 | Guard Post |  |  |  | A | 8.7822 | 1 | 8.7822 | 0 |  |  |  |  | 1926.6 |  |  | 0 |  |  |  |  | 8586.2215 |  | 8586.2215
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Area, sq ft | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove brick |  |  |  | 138 | 20010 | -30% | 179.4 | 0.50025 | 50 | cu. yd./day | 1 | 0.81778 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  | 631 | 91495 | -30% | 820.3 | 2.2874 | 50 | cu. yd./day | 1 | 3.7393 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 277 | 41550 | -30% | 360.1 | 1.0388 | 50 | cu. yd./day | 1 | 1.6415 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove structural steel | [5 empty] | 0% | 0 | 0 | 0.7 | crew hr/ton | 1 | 0 | UCF 8 - structural steel
|  |  | Clean | Remove suspended ceiling |  |  |  | 16 |  | -30% | 20.8 | 0.025679 | 50 | cu. yd./day | 1 | 0.094815 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Gypsum wall |  |  |  | 33 |  | -30% | 42.9 | 0.052963 | 50 | cu. yd./day | 1 | 0.19556 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove insulation |  |  |  | 371 |  | -30% | 482.3 | 0.59543 | 50 | cu. yd./day | 1 | 2.1985 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove stone |  |  |  | 16 |  | -30% | 20.8 | 0.025679 | 50 | cu. yd./day | 1 | 0.094815 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 1482 | 153055 |  | 1926.6 | 4.5261 |  |  |  | 8.7822
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 1926.6 | 153055 | 4.5261 | 0 | 2263.064 | 6323.1575 | 8586.2215
|  | 1.13.3 | Remove 331A |  |  |  |  | 148.568 |  | 148.568 | 0 | 0 | 0 | 0 | 0 | 14435.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64765.658 | 0 | 64765.658 |  | 24.0695 |  | 1.6947
|  | 1.13.3.1 | Basement |  |  |  | A | 6.9277 | 1 | 6.9277 | 0 |  |  |  |  | 755.7 |  |  | 0 |  |  |  |  | 3394.443 |  | 3394.443
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove brick |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  | 0 | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  | listed as covers |  | 579 | 86850 | -30% | 752.7 | 2.1713 | 25 | cu. yd./day | 1 | 6.8622 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove structural steel |  |  |  | 3 | 187 | 0% | 3 | 0.004675 | 0.7 | crew hr/ton | 1 | 0.06545 | UCF 8 - structural steel
|  |  | Clean | Remove suspended ceiling | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove grating | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove insulation | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove ceramic tile | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 582 | 87037 |  | 755.7 | 2.1759 |  |  |  | 6.9277
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 755.7 | 87037 | 2.1759 | 0 | 1087.9625 | 2306.4805 | 3394.443
|  | 1.13.3.2 | First floor |  |  |  | A | 29.1081 | 1 | 29.1081 | 0 |  |  |  |  | 6385.6 |  |  | 0 |  |  |  |  | 28901.3914 |  | 28901.3914
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove brick |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  | 3822 | 573300 | -30% | 4968.6 | 14.3325 | 50 | cu. yd./day | 1 | 22.6489 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove metal wall |  |  |  | 532 |  | -30% | 691.6 | 0.85383 | 50 | cu. yd./day | 1 | 3.1526 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove suspended ceiling | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove metal deck |  |  |  | 558 |  | -30% | 725.4 | 0.89556 | 50 | cu. yd./day | 1 | 3.3067 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Gypsum wall | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove ceramic tile | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 4912 | 573300 |  | 6385.6 | 16.0819 |  |  |  | 29.1081
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 6385.6 | 573300 | 16.0819 | 0 | 8040.9414 | 20860.45 | 28901.3914
|  | 1.13.3.3 | Vault |  |  |  | A | 98.7556 | 1 | 98.7556 | 0 |  |  |  |  | 4956.9 |  |  | 0 |  |  |  |  | 22189.05 |  | 22189.05
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove brick |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  | 600 | 87000 | -30% | 780 | 2.175 | 50 | cu. yd./day | 1 | 3.5556 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  | 3213 | 481950 | -30% | 4176.9 | 12.0488 | 10 | cu. yd./day | 1 | 95.2 | Use 2009 Means pg 29, 02 41 16.17 2500. Calculates to 3.7 cu yds per day with hand tools. Use 10 cu yds per day with heavy machines.
|  |  | Clean | Remove concrete floor |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove metal wall | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove suspended ceiling | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove metal deck | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Gypsum wall | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove ceramic tile | [5 empty] | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 3813 | 568950 |  | 4956.9 | 14.2237 |  |  |  | 98.7556
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 4956.9 | 568950 | 14.2237 | 0 | 7111.875 | 15077.175 | 22189.05
|  | 1.13.3.4 | New building/Diesel Room |  |  |  | A | 13.7766 | 1 | 13.7766 | 0 |  |  |  |  | 2337 |  |  | 0 |  |  |  |  | 10280.7736 |  | 10280.7736
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove brick |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete block |  |  |  | 352 | 51040 | -30% | 457.6 | 1.276 | 50 | cu. yd./day | 1 | 2.0859 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove concrete floor |  |  |  |  | 0 | -30% | 0 | 0 | 50 | cu. yd./day | 1 | 0 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove metal wall |  |  |  | 806 |  | -30% | 1047.8 | 1.2936 | 50 | cu. yd./day | 1 | 4.7763 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove structural steel |  |  |  | 179 | 11256 | 0% | 179 | 0.2814 | 0.7 | crew hr/ton | 1 | 3.9396 | UCF 8 - structural steel
|  |  | Clean | Remove metal deck |  |  |  | 386 |  | -30% | 501.8 | 0.61951 | 50 | cu. yd./day | 1 | 2.2874 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Gypsum wall |  |  |  | 72 |  | -30% | 93.6 | 0.11556 | 50 | cu. yd./day | 1 | 0.42667 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
|  |  | Clean | Remove insulation |  |  |  | 44 |  | -30% | 57.2 | 0.070617 | 50 | cu. yd./day | 1 | 0.26074 | Use 2009 Means pg 26, 02 41 13.33 4320, 25 c. y. per day. Assume x 2 using just heavy equipment
[8 empty] | 1839 | 62296 |  | 2337 | 3.6567 |  |  |  | 13.7766
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 2337 | 62296 | 3.6567 | 0 | 1828.3296 | 8452.444 | 10280.7736
|  | 1.13.4 | Remove buried pipe |  |  |  | A | 266.2919 | 1 | 266.2919 | 0 | 155.9608 | 0 | 0 | 0 | 2008.0394 | 0 | 0 | 0 | 8317.3897 | 0 | 0 | 0 | 9271.688 | 0 | 17589.0778
[8 empty] | Clean |  | 185.3553 | [17 empty] | 170.7546 | /foot of pipe | 1.3405
[8 empty] | LLW |  | 80.9365 | [17 empty] | 271.0982 | /foot of pipe |  |  | 0.37855
|  | 1.13.4.1 | Remove piping |  |  |  | A | 266.2919 | 1 | 266.2919 | 0 | 155.9608 |  |  |  | 2008.0394 |  |  | 0 | 8317.3897 |  |  |  | 9271.688 |  | 17589.0778
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  | 1498 | Clean | 0 - 2.5" pipe, clean |  |  | 120 |  | 2.618 | -30% | 3.4034 | 0.0042017 | 0.013333 | crew hrs/ft | 1 | 1.6 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 3 - 4" pipe, clean |  |  | 406 |  | 35.4303 | -30% | 46.0593 | 0.056863 | 0.017667 | crew hrs/ft | 1 | 7.1727 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Clean | 5 - 6" pipe, clean |  |  | 160 |  | 31.416 | -30% | 40.8408 | 0.050421 | 0.10667 | crew hrs/ft | 1 | 17.0667 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | 8 - 14" pipe, clean |  |  | 812 |  | 1459.7968 | -30% | 1897.7358 | 2.3429 | 0.178 | crew hrs/ft | 1 | 144.536 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Clean | Remove asbestos pipe insulation |  |  | 0 |  | 0 | -30% | 0 | 0 | 0.11 | crew hrs/ft | 1.3 | 0 | 2009 mean, p33, 02 82 13.43 1200 with glove bags
|  |  | Clean | Excavate buried pipe - assume 4' wide & 10' deep |  |  | 1498 |  |  | 0% | 0 |  | 0.01 | crew hr/cu. yd. | 1 | 14.98 | UCF 12 - excavate below grade structures
|  |  | Clean | Buried pipe, clean (from 331 shell inventory) |  |  | 0 |  | 20 | 0% | 20 | 0.024691 | 0.10667 | crew hrs/ft | 1 | 0 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 3.)
|  | 412 | Contaminated | 0 - 2.5" pipe, contam. |  |  |  |  | 0 | -30% | 0 | 0 | 0.013333 | crew hrs/ft | 1.35 | 0 | 2009 mean, p441, 22 05 5.10 2000 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3.)
|  |  | Contaminated | 3 - 4" pipe, contam. |  |  | 59 |  | 5.1487 | -30% | 6.6934 | 0.069722 | 0.017667 | crew hrs/ft | 1.35 | 1.4071 | 2009 mean, p441, 22 05 5.10 2050 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. )
|  |  | Contaminated | 5 - 6" pipe, contam. |  |  | 55 |  | 10.7993 | -30% | 14.039 | 0.14624 | 0.10667 | crew hrs/ft | 1.35 | 7.92 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
|  |  | Contaminated | 8 - 16" pipe, contam. |  |  | 298 |  | 104.0219 | -30% | 135.2284 | 1.4086 | 0.178 | crew hrs/ft | 1.35 | 71.6094 | 2009 mean, p441, 22 05 5.10 2100 (Means uses a crew of 2, we have a crew of 3; therefore, multiply by 2/3.)
[11 empty] | 2164.0002 | 4.1037 |  |  |  | 266.2919
|  |  |  | Waste | Weight, lbs | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 2008.0394 | 2.4791 | 0 | 1239.5305 | 8032.1575 | 9271.688
|  |  |  | Contaminated |  | 155.9608 | 1.6246 | 0 | 0 | 8317.3897 | 8317.3897
|  | 1.13.5 | Excavate outside structures |  |  |  | A | 351.3081 | 1 | 351.3081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.51111 | /cuft
|  | 1.13.5.1 | Excavate |  |  |  | A | 351.3081 | 1 | 351.3081 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Excavate buried tunnel |  |  |  | 6230 |  | 0% | 0 |  | 0.01 | crew hr/cu. yd. | 1 | 2.3074 | 2011 RS Means 31 23 16.13 1320
|  |  | Clean | Excavate shell |  |  |  | 942302 |  | 0% | 0 |  | 0.01 | crew hr/cu. yd. | 1 | 349.0007 | 2011 RS Means 31 23 16.13 1320
[8 empty] | 948532 | 0 |  | 0 | 0 |  |  |  | 351.3081
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.13.6 | Remove foundations and shell below grade |  |  |  |  | 2845.2543 |  | 2845.2543 | 0 | 0 | 0 | 0 | 0 | 140423.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 631905.3 | 0 | 631905.3 |  | 27.9615 | /cuft
|  | 1.13.6.1 | 331 Service building |  |  |  | A | 789.758 | 1 | 789.758 | 0 |  |  |  |  | 46442.5 |  |  | 0 |  |  |  |  | 208991.25 |  | 208991.25
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove concrete |  |  |  | 8513 | 1276950 | -30% | 11066.9 | 31.9237 | 10 | cu. yd./day | 1 | 252.237 | Use 2009 Means pg 29, 02 41 16.17 2500. Calculates to 3.7 cu yds per day with hand tools. Use 10 cu yds per day with heavy machines.
|  |  | Clean | Remove concrete floor |  |  |  | 27212 | 4081800 | -30% | 35375.6 | 102.045 | 15 | cu. yd./day | 1 | 537.521 | Use 2009 Means pg 29, 02 41 16.17 0440. Calculates to 5.6 cu yds per day with hand tools. Use 15 cu yds per day with heavy machines.
[8 empty] | 35725 | 5358750 |  | 46442.5 | 133.9688 |  |  |  | 789.758
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 46442.5 | 5358750 | 133.9688 | 0 | 66984.375 | 142006.875 | 208991.25
|  | 1.13.6.2 | 331A |  |  |  | A | 217.3136 | 1 | 217.3136 | 0 |  |  |  |  | 12156.3 |  |  | 0 |  |  |  |  | 54703.35 |  | 54703.35
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove concrete |  |  |  | 3301 | 495150 | -30% | 4291.3 | 12.3788 | 10 | cu. yd./day | 1 | 97.8074 | Use 2009 Means pg 29, 02 41 16.17 2500. Calculates to 3.7 cu yds per day with hand tools. Use 10 cu yds per day with heavy machines.
|  |  | Clean | Remove concrete floor |  |  |  | 6050 | 907500 | -30% | 7865 | 22.6875 | 15 | cu. yd./day | 1 | 119.5062 | Use 2009 Means pg 29, 02 41 16.17 0440. Calculates to 5.6 cu yds per day with hand tools. Use 15 cu yds per day with heavy machines.
[8 empty] | 9351 | 1402650 |  | 12156.3 | 35.0662 |  |  |  | 217.3136
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 12156.3 | 1402650 | 35.0662 | 0 | 17533.125 | 37170.225 | 54703.35
|  | 1.13.6.3 | Outside area |  |  |  | A | 191.8914 | 1 | 191.8914 | 0 |  |  |  |  | 10052.9 |  |  | 0 |  |  |  |  | 45238.05 |  | 45238.05
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove concrete |  |  |  | 3963 | 594450 | -30% | 5151.9 | 14.8613 | 10 | cu. yd./day | 1 | 117.4222 | Use 2009 Means pg 29, 02 41 16.17 2500. Calculates to 3.7 cu yds per day with hand tools. Use 10 cu yds per day with heavy machines.
|  |  | Clean | Remove concrete floor |  |  |  | 3770 | 565500 | -30% | 4901 | 14.1375 | 15 | cu. yd./day | 1 | 74.4691 | Use 2009 Means pg 29, 02 41 16.17 0440. Calculates to 5.6 cu yds per day with hand tools. Use 15 cu yds per day with heavy machines.
[8 empty] | 7733 | 1159950 |  | 10052.9 | 28.9988 |  |  |  | 191.8914
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 10052.9 | 1159950 | 28.9988 | 0 | 14499.375 | 30738.675 | 45238.05
|  | 1.13.6.4 | Tunnel |  |  |  | A | 65.1062 | 1 | 65.1062 | 0 |  |  |  |  | 3213.6 |  |  | 0 |  |  |  |  | 14461.2 |  | 14461.2
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove concrete |  |  |  | 1648 | 247200 | -30% | 2142.4 | 6.18 | 10 | cu. yd./day | 1 | 48.8296 | Use 2009 Means pg 29, 02 41 16.17 2500. Calculates to 3.7 cu yds per day with hand tools. Use 10 cu yds per day with heavy machines.
|  |  | Clean | Remove concrete floor |  |  |  | 824 | 123600 | -30% | 1071.2 | 3.09 | 15 | cu. yd./day | 1 | 16.2765 | Use 2009 Means pg 29, 02 41 16.17 0440. Calculates to 5.6 cu yds per day with hand tools. Use 15 cu yds per day with heavy machines.
[11 empty] | 3213.6 | 9.27 |  |  |  | 65.1062
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 3213.6 | 370800 | 9.27 | 0 | 4635 | 9826.2 | 14461.2
|  | 1.13.6.5 | Shell |  |  |  | A | 1581.1852 | 1 | 1581.1852 | 0 |  |  |  |  | 68558.1 |  |  | 0 |  |  |  |  | 308511.45 |  | 308511.45
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Number | Length, ft. | Volume, cu. Ft. | Weight. Lbs | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  | Clean | Remove concrete |  |  |  | 628 | 94200 | -30% | 816.4 | 2.355 | 5 | cu. yd./day | 1 | 37.2148 | Use 2009 Means pg 29, 02 41 16.17 2500. Calculates to 3.7 cu yds per day with hand tools. Use 5 cu yds per day with heavy machines. Heavily reinforced.
|  |  | Clean | Remove concrete floor |  |  |  | 52109 | 7816350 | -30% | 67741.7 | 195.4087 | 10 | cu. yd./day | 1 | 1543.9704 | Use 2009 Means pg 29, 02 41 16.17 0440. Calculates to 5.6 cu yds per day with hand tools. Use 10 cu yds per day with heavy machines. Heavily reinforced.
[8 empty] | 52737 | 7910550 |  | 68558.1 | 197.7637 |  |  |  | 1581.1852
|  |  |  | Waste | Volume | Weight, lbs | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean | 68558.1 | 7910550 | 197.7637 | 0 | 98881.875 | 209629.575 | 308511.45
| 1.14 | Final Site Survey Structure gone |  |  |  |  | A | 504 | 1 | 504 | 1512 | [6 empty] | 10000 | [7 empty] | 10000
Schedule
[7 empty] | Work hours |  | duration, days
|  | 1.14.1 | Prepare Final Status Survey Plan |  | 45 | days = | 360 | hrs | 5 | days - 40 days in parallel with 1.13
|  | 1.14.2 | Soil Sampling |  | 5 | days = | 40 | hrs | 0 | days- in parallel with 1.14.1
|  | 1.14.3 | Direct Survey |  | 3 | days = | 24 | hrs | 3 | days
|  | 1.14.4 | Sampling Analysis |  | 20 | days = | 0 | hrs | 20 | days
|  | 1.14.5 | Prepare Final Status Survey Report |  | 10 | days = | 80 | hrs | 7 | days - three days overlap with 1.14.4
[7 empty] | 504 |  | 35
|  | Sampling analysis |  | 500 | per sample x | 20 | samples = | 10000
| 1.15 | Remove contaminated soil |  |  |  |  | A | 0 | 1 | 0 | 0 | 0 | [13 empty] | 0
[10 empty] | Vol. Reduc. | Adjusted | # of
|  |  |  | Inventory |  | Number | Length, ft. | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes
|  |  | Contaminated Soil | Remove contaminated soil | [5 empty] | 0% | 0 | 0 | 0.01 | crew hr/cu. yd. | 0 | UCF 12 - excavate below grade structures
|  |  | Clean | Excavate buried pipe - assume 4' wide & 4' deep | [5 empty] | 0% | 0 | 0 | 0.01 | crew hr/cu. yd. | 0 | UCF 12 - excavate below grade structures
|  |  | Clean | Buried pipe, clean | [5 empty] | 0% | 0 | 0 | 0.088667 | crew hrs/ft | 0 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 2, we have a crew of 3; therefore, use 2/3 of duration)
|  |  | Contaminated | Excavate buried pipe - assume 4' wide & 4' deep | [5 empty] | 0% | 0 | 0 | 0.01 | crew hr/cu. yd. | 0 | UCF 12 - excavate below grade structures
|  |  | Contaminated | Buried pipe, contam. | [5 empty] | 0% | 0 | 0 | 0.1197 | crew hrs/ft | 0 | 2009 mean, p441, 22 05 5.10 2150 (Means uses a crew of 1, we have a crew of 3; therefore, duration divided by 3. times 1.35 for pc and alara)
[11 empty] | 0 | 0 |  |  | 0
|  |  |  | Waste |  | Volume | No. of containers | Container, $ | Transport, $ | Disposal, $ | Total, $
|  |  |  | Clean |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Contaminated Soil |  | 0 | 0 | 0 | 0 | 0 | 0 | Packaged in B-25 boxes
|  |  |  | Contaminated |  | 0 | 0 | 0 | 0 | 0 | 0 | Packaged in B-25 boxes
| 1.16 | Orise Site Release Confirmation
|  | Duration equal 45 days; however, this activity will occur in parallel with 1.14. The schedule duration will be 45 - 17 days = | [6 empty] | 28 | days
| 1.17 | Backfill, grade and seed (Labor costs included in Undistributed costs) |  |  |  |  | A | 491.8863 | 1 | 491.8863 | 0 | [6 empty] | 210348.5839 | 0 | [6 empty] | 210348.5839
Assumptions:
|  |  | 1. Productivity factors are included in the rates, unless otherwise specified. | [12 empty] | Grade and seed |  | 89237.9326 | [9 empty] | 0.75116 | /sqft
[16 empty] | Backfill |  | 589565.13 | [9 empty] | 0.5345 | /cuft
[10 empty] | Vol. Reduc. | Adjusted | # of 30 cu yd
|  |  |  | Inventory |  | Width | Depth | Area, sq. ft. | Volume, cu. Ft. | factor | Volume, cu. ft. | boxes |  |  | PLF
|  |  |  | Grade |  |  |  | 118800 |  | 0% | 0 | 0 | 18000 | sq ft/8 hr day | 1 | 52.8 | 2009 RS Means 31 22 16.10 0100
|  |  |  | Seed |  |  |  | 118800 |  | 0% | 0 | 0 | 80100 | sq ft/8 hr day | 1 | 11.8652 | 2009 RS Means 32 92 19.13 1000
|  |  |  | Backfill buried tunnel |  |  |  |  | 8120 | 0% | 8120 | 0 | 765 | cu. yd./day | 1 | 3.145 | 2011 RS Means 31 23 16.13 1320
|  |  |  | Backfill shell |  |  |  |  | 1094911.5 | 0% | 1094911.5 | 0 | 765 | cu. yd./day | 1 | 424.0761 | 2011 RS Means 31 23 16.13 1320
|  |  |  | Purchase new fill |  |  |  |  | 152609.5 | 0% | 152609.5 | 0
[11 empty] | 1255641 | 0 |  |  |  | 491.8863
|  |  |  | Waste | Area, sq. ft. | Installation, $/SF | Material, $/SY | Equipment, $/SY | Volume, cu. Ft. | Cost, $/cu. yd. | Total, $
|  |  |  | Seed and equipment | 118800 |  | 0.2 | 0.1 |  |  | 3960 | 2011 RS Means 32 92 19.13 1000
|  |  |  | Structural fill |  |  |  |  | 8120 | 34.67 | 10426.6815 | 2011 RS Means 31 05 16.10 0600 + 0900 & 31 23 23.24 0400
|  |  |  | Purchase new fill | 5652.2037 | cu. yds. * | 34.67 | = |  |  | 195961.9024 | 2011 RS Means 31 05 16.10 0600 + 0900 & 31 23 23.24 0400
210348.5839
| 1.18 | Site Demobilization (Labor costs included in Undistributed costs) | [5 empty] | 80 |  | 80 | 1440 | [6 empty] | 7200 | 0 | [6 empty] | 7200
|  |  | Crew |  |  | Rate, $/hr | Cost, $/hr
|  |  | 1 | Project Manager |  | 0 | 0
|  |  | 1 | Project Safety Manager |  | 0 | 0
|  |  | 1 | Project Specialist |  | 0 | 0
|  |  | 1 | Health Physicist |  | 0 | 0
|  |  | 1 | Chief HP Tech |  | 0 | 0
|  |  | 1 | Building Maintenance |  | 0 | 0
|  |  | 1 | Secretary |  | 0 | 0
|  |  | 1 | Project Control Specialist |  | 0 | 0
|  |  | 2 | HP Tech |  | 0 | 0
|  |  | 0 | Asbestos Techs |  | 0 | 0
|  |  | 8 | Decon Techs |  | 0 | 0
|  |  | 18 |  |  |  | 0
|  |  | Return rented equipment, including trailers |  |  | 24 | hr
|  |  | Dispose of unused material |  |  | 24 | hr
|  |  | General site cleanup |  |  | 24 | hr
|  |  | Travel home |  |  | 8
[6 empty] | 80 | hr
|  |  | Total Cost = |  | 80 | x | 0 | 0
|  |  | Travel cost = |  | 18 | x | 400 | 7200
| 1.19 | Final Project Report - Offsite |  |  |  |  | A | 320 | 1.1 | 352 | 528 | [7 empty] | 51920 | [6 empty] | 51920
|  |  | Staff |  |  | Number | Rate | Duration | PLF | Cost | Man-hours
|  |  | Project Specialist |  |  | 2 | 85 | 160 | 1.1 | 29920 | 352
|  |  | Project Manager |  |  | 1 | 130 | 80 | 1.1 | 11440 | 88
|  |  | Certified Health Physicst |  |  | 1 | 120 | 80 | 1.1 | 10560 | 88
[6 empty] | 4 |  | 320 |  | 51920 | 528
Crew cost - 2 crews from mobilization through final survey of structures
|  | Staff |  |  | Number | Rate
|  | Decon Techs per diem |  |  | 12 | 70 | 840
|  | Decon Techs |  |  | 12 | 45 | 540
[5 empty] | 12 |  | 1380
Crew cost - 2 crews from building demo through site demobilization
|  | Staff |  |  | Number | Rate
|  | Decon Techs per diem |  |  | 12 | 70 | 840
|  | Decon Techs |  |  | 12 | 45 | 540
[5 empty] | 12 |  | 1380
Remove systems and components
|  |  |  | Clean | [23 empty] | 8.8489 | /sq ft | 0.11333
|  |  |  | LLW | [23 empty] | 0.1877 | /sq ft |  |  | 0.0021378
|  |  |  | Hazardous | [23 empty] | 0 | /sq ft |  | 0
Mixed
|  |  |  | Remove asbestos pipe insulation | [23 empty] | 143.2532 | /foot | 1.3118 | cu. ft./ft
|  |  |  | Remove asbestos tile | [23 empty] | 2.8596 | /sq ft | 0.046324 | cu. ft./sq.ft
Decontaminate Structure
|  |  |  | Clean | [23 empty] | 2.9986 | /sq ft | 0.125
|  |  |  | LLW | [23 empty] | 2.2543 | /sq ft |  |  | 0.013394
|  |  |  | Final Survey of Structure | [23 empty] | 18.8456 | /sq ft
|  |  |  | Remove building | [23 empty] | 16.9924 | /sq ft | 1.2117
Remove buried pipe
|  |  |  | Clean | [23 empty] | 170.7546 | /foot of pipe | 1.3405
|  |  |  | LLW | [23 empty] | 271.0982 | /foot of pipe |  |  | 0.37855
|  |  |  | Excavate outside structures | [23 empty] | 0.51111 | /cuft
|  |  |  | Remove foundations and shell below grade | [23 empty] | 27.9615 | /cuft

## PWR - 2015 (hidden)
[6 empty] | Contingency | 15% | 23.84% | 25% | 12.21% | 21.95% | 10% | 37.66% | 15% | 15%
[6 empty] | Fuel Storage Only Contingency | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
[16 empty] | Subtotal |  | Total |  | Clean | Contaminated
|  | % | % | % |  |  | Staff | Craft | Equipment & |  |  | Clean | Contaminated |  |  | without |  | with | Staff | Craft | Craft
| Type | Common | Unit 1 | Unit 2 |  |  | Labor,$ | Labor,$ | Materials, $ | Packaging, $ | Transportation, $ | Disposal, $ | Disposal, $ | Energy, $ | Other, $ | Contingency, $ | Contingency, $ | Contingency, $ | Manhours | Manhours | Manhours
PERIOD 1 - U1 & U2 DECOMMISSIONING PLANNING COST:
SPENT FUEL ACTIVITIES
Modify spent fuel support systems
1 | A 50.54(bb) | 100% |  |  |  | Define systems modification | 65203.75 | [8 empty] | 65203.75 | 9800 | 75003.75 | 608
1 | A 50.54(bb) | 100% |  |  |  | Design systems modification and equipment specificatons | 155196.3192 | [8 empty] | 155196.3192 | 23300 | 178496.3192 | 1568
1 | A 50.54(bb) | 100% |  |  |  | Prepare installation procedures | 19042.4477 | [8 empty] | 19042.4477 | 2900 | 21942.4477 | 192
1 | A 50.54(bb) | 100% |  |  |  | Prepare test procedures | 19042.4477 | [8 empty] | 19042.4477 | 2900 | 21942.4477 | 192
1 | A 50.54(bb) | 100% |  |  |  | Prepare maintenance procedures | 19042.4477 | [8 empty] | 19042.4477 | 2900 | 21942.4477 | 192
Control room relocation
1 | A 50.54(bb) | 100% |  |  |  | Define control room equipment | 65203.75 | [8 empty] | 65203.75 | 9800 | 75003.75 | 608
1 | A 50.54(bb) | 100% |  |  |  | Design control room modification and equipment specificatons | 188090.75 | [8 empty] | 188090.75 | 28200 | 216290.75 | 1896
1 | A 50.54(bb) | 100% |  |  |  | Prepare installation procedures | 19042.4477 | [8 empty] | 19042.4477 | 2900 | 21942.4477 | 192
1 | A 50.54(bb) | 100% |  |  |  | Prepare test procedures | 19042.4477 | [8 empty] | 19042.4477 | 2900 | 21942.4477 | 192
1 | A 50.54(bb) | 100% |  |  |  | Prepare maintenance procedures | 19042.4477 | [8 empty] | 19042.4477 | 2900 | 21942.4477 | 192
Design spent fuel storage security modifications
1 | A 50.54(bb) | 100% |  |  |  | Define modification | 30754.4169 | [8 empty] | 30754.4169 | 4600 | 35354.4169 | 288
1 | A 50.54(bb) | 100% |  |  |  | Design modification and equipment specificatons | 107927.2346 | [8 empty] | 107927.2346 | 16200 | 124127.2346 | 1016
1 | A 50.54(bb) | 100% |  |  |  | Prepare installation procedures | 19042.4477 | [8 empty] | 19042.4477 | 2900 | 21942.4477 | 192
1 | A 50.54(bb) | 100% |  |  |  | Prepare test procedures | 19042.4477 | [8 empty] | 19042.4477 | 2900 | 21942.4477 | 192
1 | A 50.54(bb) | 100% |  |  |  | Prepare maintenance procedures | 19042.4477 | [8 empty] | 19042.4477 | 2900 | 21942.4477 | 192
1 | A 50.54(bb) | 100% |  |  | ISFSI Pad Construction |  |  | 135000000 | [7 empty] | 135000000 | 32181700 | 167181700 | 192
[5 empty] | SUBTOTAL - SPENT FUEL ACTIVITIES |  | 783758.25 | 135000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135783758.25 | 32299700 | 168083458.25 | 7904 | 0 | 0
SPENT FUEL PERIOD DEPENDENT
1 | PD 50.54(bb) | 100% |  |  |  | Utility Staff | 0 | [8 empty] | 0 | 0 | 0 | 0
1 | PD 50.54(bb) | 100% |  |  |  | Security | 0 | [8 empty] | 0 | 0 | 0 | 0
1 | PD 50.54(bb) | 100% |  |  |  | Insurance | [8 empty] | 2882842.8061 | 2882842.8061 | 432400 | 3315242.8061
1 | PD 50.54(bb) | 100% |  |  |  | O & M Budget Items |  |  | 0 | [6 empty] | 0 | 0 | 0
1 | PD 50.54(bb) | 100% |  |  |  | Permits & Fees | [8 empty] | 0 | 0 | 0 | 0
1 | PD 50.54(bb) | 100% |  |  |  | Waste Transfer and Loading |  | 0 | [7 empty] | 0 | 0 | 0
1 | PD 50.54(bb) | 100% |  |  |  | Energy | [7 empty] | 0 |  | 0 | 0 | 0
1 | PD 50.54(bb) | 100% |  |  |  | Spent Fuel Storage Maintenance Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
1 | PD 50.54(bb) | 100% |  |  |  | Small Tools |  |  | 1350000 | [6 empty] | 1350000 | 337500 | 1687500
[5 empty] | SUBTOTAL - SPENT FUEL PERIOD DEPENDENT |  | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 2882842.8061 | 4232842.8061 | 769900 | 5002742.8061 | 0 | 0 | 0
DECOMMISSIONING ACTIVITIES
Primary system decontamination
1 | A 50.75(c) | 100% |  |  |  | Define scope | 43825.9777 | [8 empty] | 43825.9777 | 6600 | 50425.9777 | 328
1 | A 50.75(c) | 100% |  |  |  | Evaluate processes | 55757.07 | [8 empty] | 55757.07 | 8400 | 64157.07 | 448
1 | A 50.75(c) | 100% |  |  |  | Prepare bid specifications and RFP | 55713.1592 | [8 empty] | 55713.1592 | 8400 | 64113.1592 | 512
1 | A 50.75(c) | 100% |  |  |  | Qualify Contractors | 15009.5692 | [8 empty] | 15009.5692 | 2300 | 17309.5692 | 112
1 | A 50.75(c) | 100% |  |  |  | Evaluate Proposals | 41198.4238 | [8 empty] | 41198.4238 | 6200 | 47398.4238 | 248
Select Decommissioning General Contractor
1 | A 50.75(c) | 100% |  |  |  | Define scope | 83634.4938 | [8 empty] | 83634.4938 | 12500 | 96134.4938 | 736
1 | A 50.75(c) | 100% |  |  |  | Prepare bid specifications and RFP | 88549.0208 | [8 empty] | 88549.0208 | 13300 | 101849.0208 | 776
1 | A 50.75(c) | 100% |  |  |  | Qualify Contractors | 23012.87 | [8 empty] | 23012.87 | 3500 | 26512.87 | 176
1 | A 50.75(c) | 100% |  |  |  | Evaluate Proposals | 41198.4238 | [8 empty] | 41198.4238 | 6200 | 47398.4238 | 248
U1 & U2 cold and dark site repowering
1 | A 50.75(c) | 100% |  |  |  | Define scope | 71703.4015 | [8 empty] | 71703.4015 | 10800 | 82503.4015 | 616
1 | A 50.75(c) | 100% |  |  |  | Design modification and equipment specificatons | 158616.8923 | [8 empty] | 158616.8923 | 23800 | 182416.8923 | 1560
1 | A 50.75(c) | 100% |  |  |  | Prepare installation procedures | 222607.4077 | [8 empty] | 222607.4077 | 33400 | 256007.4077 | 2080
1 | A 50.75(c) | 100% |  |  |  | Prepare test procedures | 19042.4477 | [8 empty] | 19042.4477 | 2900 | 21942.4477 | 192
Modify U1 & U2 containment access
1 | A 50.75(c) | 100% |  |  |  | Select new access location | 31894.8854 | [8 empty] | 31894.8854 | 4800 | 36694.8854 | 208
1 | A 50.75(c) | 100% |  |  |  | Design access and equipment specificatons | 140510.7115 | [8 empty] | 140510.7115 | 21100 | 161610.7115 | 1320
U1 & U2 Site Characterization
1 | A 50.75(c) | 100% |  |  |  | Define scope | 50168.9623 | [8 empty] | 50168.9623 | 7500 | 57668.9623 | 408
1 | A 50.75(c) | 100% |  |  |  | Prepare bid specifications and RFP | 56811.9131 | [8 empty] | 56811.9131 | 8500 | 65311.9131 | 496
1 | A 50.75(c) | 100% |  |  |  | Qualify Contractors | 23012.87 | [8 empty] | 23012.87 | 3500 | 26512.87 | 176
1 | A 50.75(c) | 100% |  |  |  | Evaluate Proposals | 41198.4238 | [8 empty] | 41198.4238 | 6200 | 47398.4238 | 248
1 | A 50.75(c) | 100% |  |  |  | Prepare procedures | 139928.8592 | [8 empty] | 139928.8592 | 21000 | 160928.8592 | 1256
ADMINISTRATIVE ACTIVITIES
1 | A 50.75(c) | 100% |  |  |  | Develop staff transition plan | 43225.74 | [8 empty] | 43225.74 | 6500 | 49725.74 | 352
1 | A 50.75(c) | 100% |  |  |  | Develop severance and retention policy | 43225.74 | [8 empty] | 43225.74 | 6500 | 49725.74 | 352
1 | A 50.75(c) | 100% |  |  |  | Prepare project administrative procedures | 46957.1092 | [8 empty] | 46957.1092 | 7000 | 53957.1092 | 488
1 | A 50.75(c) | 100% |  |  |  | Develop area based decommissioning cost estimate | 217918.5808 | [8 empty] | 217918.5808 | 32700 | 250618.5808 | 2240
1 | A 50.75(c) | 100% |  |  |  | Develop project budget and schedule controls | 63303.5654 | [8 empty] | 63303.5654 | 9500 | 72803.5654 | 648
1 | A 50.75(c) | 100% |  |  |  | Assemble plant drawings | 25275.7931 | [8 empty] | 25275.7931 | 3800 | 29075.7931 | 296
1 | A 50.75(c) | 100% |  |  |  | Define end product | 38096.1346 | [8 empty] | 38096.1346 | 5700 | 43796.1346 | 280
1 | A 50.75(c) | 100% |  |  |  | Develop technical approach and detailed project plans | 234545.5769 | [8 empty] | 234545.5769 | 35200 | 269745.5769 | 2440
LICENSING/PERMITTING DOCUMENTATION
1 | A 50.75(c) | 100% |  |  |  | Insurance exemption | 48428.1092 | [8 empty] | 48428.1092 | 7300 | 55728.1092 | 376
1 | A 50.75(c) | 100% |  |  |  | Prepare Post-Shutdown Decommissioning Activities Report | 140560.7654 | [8 empty] | 140560.7654 | 21100 | 161660.7654 | 1400
1 | A 50.75(c) | 100% |  |  |  | Prepare certification of permanent cessation of operations | 6393.7162 | [8 empty] | 6393.7162 | 1000 | 7393.7162 | 40
1 | A 50.75(c) | 100% |  |  |  | Prepare certification of permanent reactor defueling | 6393.7162 | [8 empty] | 6393.7162 | 1000 | 7393.7162 | 40
1 | A 50.75(c) | 100% |  |  |  | Prepare post-shutdown technical specification modifications | 347694.9538 | [8 empty] | 347694.9538 | 52200 | 399894.9538 | 3600
1 | A 50.75(c) | 100% |  |  |  | Update FSAR | 322716.5231 | [8 empty] | 322716.5231 | 48400 | 371116.5231 | 3360
1 | A 50.75(c) | 100% |  |  |  | Develop certified fuel handler program | 37647.5777 | [8 empty] | 37647.5777 | 5600 | 43247.5777 | 336
1 | A 50.75(c) | 100% |  |  |  | Prepare post-shutdown emergency plan | 169694.3654 | [8 empty] | 169694.3654 | 25500 | 195194.3654 | 1480
1 | A 50.75(c) | 100% |  |  |  | Prepare post-shutdown QA plan | 108471.1654 | [8 empty] | 108471.1654 | 16300 | 124771.1654 | 1000
1 | A 50.75(c) | 100% |  |  |  | Prepare post-shutdown security plan | 108471.1654 | [8 empty] | 108471.1654 | 16300 | 124771.1654 | 1000
1 | A 50.75(c) | 100% |  |  |  | Prepare post-shutdown fire protection plan | 108471.1654 | [8 empty] | 108471.1654 | 16300 | 124771.1654 | 1000
1 | A 50.75(c) | 100% |  |  |  | Prepare post-shutdown radiation protection manual | 108471.1654 | [8 empty] | 108471.1654 | 16300 | 124771.1654 | 1000
1 | A 50.75(c) | 100% |  |  |  | Prepare and submit state and local permits | 98477.1654 | [8 empty] | 98477.1654 | 14800 | 113277.1654 | 960
1 | A 50.75(c) | 100% |  |  |  | Respond to NRC questions on PSDAR | 6393.7162 | [8 empty] | 6393.7162 | 1000 | 7393.7162 | 40
1 | A 50.75(c) | 100% |  |  |  | Prepare detailed resource loaded project schedule | 267311.9462 | [8 empty] | 267311.9462 | 40100 | 307411.9462 | 2480
1 | A 50.75(c) | 100% |  |  |  | Perform 50.59 unreviewed safety questions | 97771.1246 | [8 empty] | 97771.1246 | 14700 | 112471.1246 | 736
1 | A 50.75(c) | 100% |  |  |  | Prepare activity specifications | 1807127.2308 | [8 empty] | 1807127.2308 | 271100 | 2078227.2308 | 18080
1 | A 50.75(c) | 100% |  |  |  | Prepare detailed work procedures | 1667731.75 | [8 empty] | 1667731.75 | 250200 | 1917931.75 | 16080
1 | A 50.75(c) | 100% |  |  |  | Select shipping casks and obtain permits | 25243.1077 | [8 empty] | 25243.1077 | 3800 | 29043.1077 | 240
LICENSE TERMINATION PLAN
1 | A 50.75(c) | 100% |  |  |  | General information | 1406.6892 | [8 empty] | 1406.6892 | 200 | 1606.6892 | 16
1 | A 50.75(c) | 100% |  |  |  | Site Characterization | 35465.4423 | [8 empty] | 35465.4423 | 5300 | 40765.4423 | 336
1 | A 50.75(c) | 100% |  |  |  | Identification of remaining site dismantlement activities | 35465.4423 | [8 empty] | 35465.4423 | 5300 | 40765.4423 | 336
1 | A 50.75(c) | 100% |  |  |  | Remediation Plans | 18631.3792 | [8 empty] | 18631.3792 | 2800 | 21431.3792 | 176
1 | A 50.75(c) | 100% |  |  |  | Final Radiation Survey Plan | 353367.2692 | [8 empty] | 353367.2692 | 53000 | 406367.2692 | 3620
1 | A 50.75(c) | 100% |  |  |  | Compliance with the radiological criteria for license termination | 237239.9 | [8 empty] | 237239.9 | 35600 | 272839.9 | 2440
1 | A 50.75(c) | 100% |  |  |  | Update decommissioning cost estimate | 57848.1808 | [8 empty] | 57848.1808 | 8700 | 66548.1808 | 596
1 | A 50.75(c) | 100% |  |  |  | Supplement to the environmental report | 57848.1808 | [8 empty] | 57848.1808 | 8700 | 66548.1808 | 596
1 | A 50.75(c) | 100% |  |  |  | Respond to NRC questions | 27394.95 | [8 empty] | 27394.95 | 4100 | 31494.95 | 200
1 | A 50.75(c) | 100% |  |  |  | Update LTP | 53329.0888 | [8 empty] | 53329.0888 | 8000 | 61329.0888 | 536.4
[5 empty] | SUBTOTAL - DECOMMISSIONING ACTIVITY COSTS: |  | 8477410.9749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8477410.9749 | 1272500 | 9749910.9749 | 81340.4 | 0 | 0
DECOMMISSIONING PERIOD DEPENDENT
1 | PD 50.75(c) |  | 100% | 0% |  | Utility Staff | 3974725.829 | [8 empty] | 3974725.829 | 596200 | 4570925.829 | 75575.3728
1 | PD 50.75(c) |  | 100% | 0% |  | DGC Staff | 4633240.3347 | [8 empty] | 4633240.3347 | 695000 | 5328240.3347 | 56158.92
1 | PD 50.75(c) |  | 100% | 0% |  | Security | 755208.862 | [8 empty] | 755208.862 | 113300 | 868508.862 | 29572.972
1 | PD 50.75(c) |  | 100% | 0% |  | HP Supplies |  |  | 276718.1746 | [6 empty] | 276718.1746 | 69200 | 345918.1746
1 | PD 50.75(c) |  | 100% | 0% |  | Equipment |  |  | 301421.5741 | [6 empty] | 301421.5741 | 75400 | 376821.5741
1 | PD 50.75(c) |  | 100% | 0% |  | Unit 1 Insurance | [8 empty] | 1223073.1749 | 1223073.1749 | 183500 | 1406573.1749
1 | PD 50.75(c) |  | 100% | 0% |  | Unit 2 Insurance | [8 empty] | 0 | 0 | 0 | 0
1 | PD 50.75(c) |  | 100% | 0% |  | O & M Budget Items |  |  | 156229.0025 | [6 empty] | 156229.0025 | 39100 | 195329.0025
1 | PD 50.75(c) |  | 100% | 0% |  | Permits & Fees | [8 empty] | 1995918.5768 | 1995918.5768 | 299400 | 2295318.5768
1 | PD 50.75(c) |  | 100% | 0% |  | Waste Transfer and Loading |  | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0
1 | PD 50.75(c) |  | 100% | 0% |  | Energy | [7 empty] | 3482181.3729 |  | 3482181.3729 | 522300 | 4004481.3729
1 | PD 50.75(c) |  | 100% | 0% |  | Severance | 18173407.641 | [8 empty] | 18173407.641 | 2726000 | 20899407.641
1 | PD 50.75(c) |  | 100% | 0% |  | Small Tools |  |  | 0 | [6 empty] | 0 | 0 | 0
[5 empty] | SUBTOTAL - DECOMMISSIONING PERIOD DEPENDENT |  | 27536582.6667 | 0 | 734368.7512 | 0 | 0 | 0 | 0 | 3482181.3729 | 3218991.7517 | 34972124.5425 | 5319400 | 40291524.5425 | 161307.2648 | 0 | 0
[5 empty] | TOTAL PERIOD 1 - U1 & U2 DECOMMISSIONING PLANNING COST: |  | 36797751.8916 | 135000000 | 2084368.7512 | 0 | 0 | 0 | 0 | 3482181.3729 | 6101834.5578 | 183466136.5735 | 39661500 | 223127636.5735 | 250551.6648 | 0 | 0
ACTIVITY
UNIT 1 - PERIOD 1 COSTS
[6 empty] | Unit 1 Subtotal 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 1 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNIT 2
[6 empty] | Unit 2 Subtotal 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 2 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Common
[6 empty] | Total 10 CFR 50.75(c): | 8477410.9749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8477410.9749 | 1272500 | 9749910.9749 | 81340.4 | 0 | 0
[6 empty] | Total 10 CFR 50.54(bb): | 783758.25 | 135000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135783758.25 | 32299700 | 168083458.25 | 7904 | 0 | 0
PERIOD DEPENDENT
UNIT 1 - PERIOD 1 COSTS
[6 empty] | Unit 1 Subtotal 10 CFR 50.75(c): | 27536582.6667 | 0 | 734368.7512 | 0 | 0 | 0 | 0 | 3482181.3729 | 3218991.7517 | 34972124.5425 | 5319400 | 40291524.5425 | 161307.2648 | 0 | 0
[6 empty] | Unit 1 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNIT 2
[6 empty] | Unit 2 Subtotal 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 2 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Common
[6 empty] | Total 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Total 10 CFR 50.54(bb): | 0 | 0 | 1350000 | 0 | 0 | 0 | 0 | 0 | 2882842.8061 | 4232842.8061 | 769900 | 5002742.8061 | 0 | 0 | 0
Unit 1, Unit 2 & Common
[6 empty] | Total 10 CFR 50.75(c): | 36013993.6416 | 0 | 734368.7512 | 0 | 0 | 0 | 0 | 3482181.3729 | 3218991.7517 | 43449535.5174 | 6591900 | 50041435.5174 | 242647.6648 | 0 | 0
[6 empty] | Total 10 CFR 50.54(bb): | 783758.25 | 135000000 | 1350000 | 0 | 0 | 0 | 0 | 0 | 2882842.8061 | 140016601.0561 | 33069600 | 173086201.0561 | 7904 | 0 | 0
Check
PERIOD 2 - POST-SHUTDOWN ACTIVITIES COSTS:
SPENT FUEL ACTIVITIES
2 | A 50.54(bb) | 100% |  |  | Modify Spent Fuel Cooling System |  |  | 640667.2545 | 1165000 | [6 empty] | 1805667.2545 | 444000 | 2249667.2545 |  | 9360
2 | A 50.54(bb) | 100% |  |  | Modify control room |  |  | 588868.5756 | 800000 | [6 empty] | 1388868.5756 | 340400 | 1729268.5756 |  | 9360
2 | A 50.54(bb) | 100% |  |  | Modify security system |  |  | 459341.2766 | 525000 | [6 empty] | 984341.2766 | 240700 | 1225041.2766 |  | 7280
2 | A 50.54(bb) | 100% |  |  | Puchase ISFSI casks |  |  |  | 111000000 | [6 empty] | 111000000 | 27750000 | 138750000 |  | 7280
[5 empty] | SUBTOTAL - SPENT FUEL ACTIVITIES |  | 0 | 1688877.1068 | 113490000 | 0 | 0 | 0 | 0 | 0 | 0 | 115178877.1068 | 28775100 | 143953977.1068 | 0 | 33280 | 0
SPENT FUEL PERIOD DEPENDENT
2 | PD 50.54(bb) | 100% |  |  |  | Utility Staff | 3363648.4207 | [8 empty] | 3363648.4207 | 504500 | 3868148.4207 | 68405.6498
2 | PD 50.54(bb) | 100% |  |  |  | Security | 1295527.4264 | [8 empty] | 1295527.4264 | 194300 | 1489827.4264 | 49749.5635
2 | PD 50.54(bb) | 100% |  |  |  | Insurance | [8 empty] | 1619318.1415 | 1619318.1415 | 242900 | 1862218.1415
2 | PD 50.54(bb) | 100% |  |  |  | O & M Budget Items |  |  | 0 | [6 empty] | 0 | 0 | 0
2 | PD 50.54(bb) | 100% |  |  |  | Permits & Fees | [8 empty] | 1007524.7728 | 1007524.7728 | 151100 | 1158624.7728
2 | PD 50.54(bb) | 100% |  |  |  | Waste Transfer and Loading |  | 0 | [7 empty] | 0 | 0 | 0
2 | PD 50.54(bb) | 100% |  |  |  | Energy | [7 empty] | 848474.385 |  | 848474.385 | 127300 | 975774.385
2 | PD 50.54(bb) | 100% |  |  |  | Spent Fuel Storage Maintenance Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
2 | PD 50.54(bb) | 100% |  |  |  | Small Tools |  |  | 16888.7711 | [6 empty] | 16888.7711 | 4200 | 21088.7711
[5 empty] | SUBTOTAL - SPENT FUEL PERIOD DEPENDENT |  | 4659175.8471 | 0 | 16888.7711 | 0 | 0 | 0 | 0 | 848474.385 | 2626842.9142 | 8151381.9175 | 1224300 | 9375681.9175 | 118155.2132 | 0 | 0
DECOMMISSIONING ACTIVITIES
2 | A 50.75(c) |  | 50% | 50% | Primary System Decon Unit 1 & 2 |  |  | 8902125 | 1476125 |  |  |  | 9340250 |  |  | 19718500 | 6008600 | 25727100
2 | A 50.75(c) |  | 50% | 50% | Flush & Drain Systems (PERFORMED BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0
2 | A 50.75(c) | 100% | 0% | 0% | Implement cold & dark |  |  | 773782.8763 | 1600000 | [6 empty] | 2373782.8763 | 584500 | 2958282.8763 |  | 11520
2 | A 50.75(c) |  | 100% | 0% | Modify U1 Containment Access |  |  | 351391.1973 | 525000 | [6 empty] | 876391.1973 | 215000 | 1091391.1973 |  | 5760
2 | A 50.75(c) |  | 0% | 100% | ModifyU2 Containment Access |  |  | 351391.1973 | 525000 | [6 empty] | 876391.1973 | 215000 | 1091391.1973 |  | 5760
2 | A 50.75(c) | 100% |  |  | Historical Site Assessment |  | 331734.4204 | [8 empty] | 331734.4204 | 49800 | 381534.4204 | 4880
2 | A 50.75(c) | 100% |  |  | Vessel and internals activation analysis |  | 116901.1615 | [8 empty] | 116901.1615 | 17500 | 134401.1615 | 640
2 | A 50.75(c) | 100% |  |  | Characterization survey |  | 754270.2467 | [8 empty] | 754270.2467 | 113100 | 867370.2467 | 12880
2 | A 50.75(c) | 100% |  |  | Test special equipment and training |  |  | 947438.7488 | [7 empty] | 947438.7488 | 225900 | 1173338.7488 |  | 13440
[5 empty] | SUBTOTAL - DECOMMISSIONING ACTIVITY COSTS: |  | 1202905.8286 | 11326129.0196 | 4126125 | 0 | 0 | 0 | 9340250 | 0 | 0 | 25995409.8482 | 7429400 | 33424809.8482 | 18400 | 36480 | 0
DECOMMISSIONING PERIOD DEPENDENT
2 | PD 50.75(c) | 100% |  |  |  | Utility Staff | 15093537.2774 | [8 empty] | 15093537.2774 | 2264000 | 17357537.2774 | 300570.2793
2 | PD 50.75(c) | 100% |  |  |  | DGC Staff | 11310434.0924 | [8 empty] | 11310434.0924 | 1696600 | 13007034.0924 | 157540.2843
2 | PD 50.75(c) | 100% |  |  |  | Security | 3674302.4041 | [8 empty] | 3674302.4041 | 551100 | 4225402.4041 | 149248.6904
2 | PD 50.75(c) | 100% |  |  |  | HP Supplies |  |  | 929325.515 | [6 empty] | 929325.515 | 232300 | 1161625.515
2 | PD 50.75(c) | 100% |  |  |  | Equipment |  |  | 1286079.6497 | [6 empty] | 1286079.6497 | 321500 | 1607579.6497
2 | PD 50.75(c) | 100% |  |  |  | Unit 1 Insurance | [8 empty] | 385787.3793 | 385787.3793 | 57900 | 443687.3793
2 | PD 50.75(c) | 100% |  |  |  | Unit 2 Insurance | [8 empty] | 385787.3793 | 385787.3793 | 57900 | 443687.3793
2 | PD 50.75(c) | 100% |  |  |  | O & M Budget Items |  |  | 11459322.8856 | [6 empty] | 11459322.8856 | 2864800 | 14324122.8856
2 | PD 50.75(c) | 100% |  |  |  | Permits & Fees | [8 empty] | 2440339.7547 | 2440339.7547 | 366100 | 2806439.7547
2 | PD 50.75(c) | 100% |  |  |  | Waste Transfer and Loading |  | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0
2 | PD 50.75(c) | 100% |  |  |  | Energy | [7 empty] | 4201784.3891 |  | 4201784.3891 | 630300 | 4832084.3891
2 | PD 50.75(c) | 100% |  |  |  | Severance | 28209800.954 | [8 empty] | 28209800.954 | 4231500 | 32441300.954
2 | PD 50.75(c) | 100% |  |  |  | Small Tools |  |  | 226522.5804 | [6 empty] | 226522.5804 | 56600 | 283122.5804
[5 empty] | SUBTOTAL - DECOMMISSIONING PERIOD DEPENDENT |  | 58288074.7279 | 0 | 13901250.6307 | 0 | 0 | 0 | 0 | 4201784.3891 | 3211914.5132 | 79603024.2608 | 13330600 | 92933624.2608 | 607359.254 | 0 | 0
[5 empty] | TOTAL PERIOD 2 - POST-SHUTDOWN ACTIVITIES COSTS: |  | 64150156.4036 | 13015006.1264 | 131534264.4017 | 0 | 0 | 0 | 9340250 | 5050258.7741 | 5838757.4274 | 228928693.1332 | 50759400 | 279688093.1332 | 743914.4672 | 69760 | 0
ACTIVITY
UNIT 1
[6 empty] | Unit 1 Subtotal 10 CFR 50.75(c): | 0 | 4802453.6973 | 1263062.5 | 0 | 0 | 0 | 4670125 | 0 | 0 | 10735641.1973 | 3219300 | 13954941.1973 | 0 | 5760 | 0
[6 empty] | Unit 1 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNIT 2
[6 empty] | Unit 2 Subtotal 10 CFR 50.75(c): | 0 | 4802453.6973 | 1263062.5 | 0 | 0 | 0 | 4670125 | 0 | 0 | 10735641.1973 | 3219300 | 13954941.1973 | 0 | 5760 | 0
[6 empty] | Unit 2 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Common
[6 empty] | Common Subtotal - 10 CFR 50.75(c): | 1202905.8286 | 1721221.6251 | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 4524127.4537 | 990800 | 5514927.4537 | 18400 | 24960 | 0
[6 empty] | Common Subtotal - 10 CFR 50.54(bb): | 0 | 1688877.1068 | 113490000 | 0 | 0 | 0 | 0 | 0 | 0 | 115178877.1068 | 28775100 | 143953977.1068 | 0 | 33280 | 0
PERIOD DEPENDENT
UNIT 1
[6 empty] | Unit 1 Subtotal 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 1 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNIT 2
[6 empty] | Unit 2 Subtotal 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 2 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Common
[6 empty] | Common Subtotal - 10 CFR 50.75(c): | 58288074.7279 | 0 | 13901250.6307 | 0 | 0 | 0 | 0 | 4201784.3891 | 3211914.5132 | 79603024.2608 | 13330600 | 92933624.2608 | 607359.254 | 0 | 0
[6 empty] | Common Subtotal - 10 CFR 50.54(bb): | 4659175.8471 | 0 | 16888.7711 | 0 | 0 | 0 | 0 | 848474.385 | 2626842.9142 | 8151381.9175 | 1224300 | 9375681.9175 | 118155.2132 | 0 | 0
Unit 1, Unit 2 & Common
[6 empty] | Total 10 CFR 50.75(c): | 59490980.5565 | 11326129.0196 | 18027375.6307 | 0 | 0 | 0 | 9340250 | 4201784.3891 | 3211914.5132 | 105598434.109 | 20760000 | 126358434.109 | 625759.254 | 36480 | 0
[6 empty] | Total 10 CFR 50.54(bb): | 4659175.8471 | 1688877.1068 | 113506888.7711 | 0 | 0 | 0 | 0 | 848474.385 | 2626842.9142 | 123330259.0242 | 29999400 | 153329659.0242 | 118155.2132 | 33280 | 0
Check
PERIOD 3 VESSEL AND INTERNALS REMOVAL COSTS:
SPENT FUEL ACTIVITIES
3 | A 50.54(bb) | 100% |  |  | Purcahse ISFSI Casks |  |  |  | 111000000 | [6 empty] | 111000000 | 27750000 | 138750000
[5 empty] | SUBTOTAL - SPENT FUEL ACTIVITIES |  | 0 | 0 | 111000000 | 0 | 0 | 0 | 0 | 0 | 0 | 111000000 | 27750000 | 138750000 | 0 | 0 | 0
SPENT FUEL PERIOD DEPENDENT
3 | PD 50.54(bb) | 100% |  |  |  | Utility Staff | 11892899.7732 | [8 empty] | 11892899.7732 | 1783900 | 13676799.7732 | 241862.8331
3 | PD 50.54(bb) | 100% |  |  |  | Security | 3644479.1906 | [8 empty] | 3644479.1906 | 546700 | 4191179.1906 | 234533.6563
3 | PD 50.54(bb) | 100% |  |  |  | Insurance | [8 empty] | 5725446.286 | 5725446.286 | 858800 | 6584246.286
3 | PD 50.54(bb) | 100% |  |  |  | O & M Budget Items |  |  | 0 | [6 empty] | 0 | 0 | 0
3 | PD 50.54(bb) | 100% |  |  |  | Permits & Fees | [8 empty] | 3562319.7322 | 3562319.7322 | 534300 | 4096619.7322
3 | PD 50.54(bb) | 100% |  |  |  | Waste Transfer and Loading |  | 0 | [7 empty] | 0 | 0 | 0
3 | PD 50.54(bb) | 100% |  |  |  | Energy | [7 empty] | 1939299.3261 |  | 1939299.3261 | 290900 | 2230199.3261
3 | PD 50.54(bb) | 100% |  |  |  | Spent Fuel Storage Maintenance Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
3 | PD 50.54(bb) | 100% |  |  |  | Small Tools |  |  | 0 | [6 empty] | 0 | 0 | 0
[5 empty] | SUBTOTAL - SPENT FUEL PERIOD DEPENDENT |  | 15537378.9638 | 0 | 0 | 0 | 0 | 0 | 0 | 1939299.3261 | 9287766.0182 | 26764444.3081 | 4014600 | 30779044.3081 | 476396.4894 | 0 | 0
DECOMMISSIONING ACTIVITIES
[5 empty] | UNIT 1 |  |  | Floor area requiring lighting = |  |  | 165610 | ft^2 | for U1 & U2 Containments and Auxiliary Bldg:
[8 empty] | Floor area requiring lighting = |  |  | 599810 | ft^2 | for all of the buildings on site:
3 | A 50.75(c) |  | 100% |  | Install all reactor operating floor contamination control envelopes (CCEs), support structures, rigging, internals work platforms and process equipment (BY UTILITY STAFF)
[16 empty] | 0 | 0 | 0 |  |  |  | Utility Staff
3 | A 50.75(c) |  | 100% |  | Finalize Residual Radiation Inventory (WITH SITE CHARACTERIZATION) | [10 empty] | 0 | 0 | 0
3 | A 50.75(c) |  | 100% |  | Finalize Internals and Vessel Segmenting Details (WITH ACTIVATION ANALYSIS) | [10 empty] | 0 | 0 | 0
3 | A 50.75(c) |  | 100% |  | Remove, pack, ship and bury Unit 1 Pressurizer |  |  | 1064197.4239 | 0 | 800 | 71767.96 |  | 933410.4 |  |  | 2070175.7839 | 621000 | 2691175.7839 |  |  | 19407.07
3 | A 50.75(c) |  | 100% |  | Decon, remove, package, ship and bury Unit 1 steam generators |  |  | 4340246.0222 | 1532266.6667 | 12800 | 823395.36 |  | 12599366.4 |  |  | 19308074.4489 | 6344800 | 25652874.4489 |  |  | 79162.68
3 | A 50.75(c) |  | 100% |  | Remove Unit 1 equipment hatch closure (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Utility Staff
3 | A 50.75(c) |  | 100% |  | Remove Unit 1 control rod drive and reactor cavity missile shieldS (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Utility Staff
3 | A 50.75(c) |  | 100% |  | Remove Unit 1 CRD mechanisms and cables, air ducts, and reactor vessel head (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Utility Staff
3 | A 50.75(c) |  | 100% |  | Remove, segment, package and bury Unit 1 vessel & vessel head insulation |  |  | 182000 |  |  |  |  | 364625 |  |  | 546625 | 180700 | 727325
3 | A 50.75(c) |  | 100% |  | Prepare Unit 1 vessel head for shipment as its own container (WITH VESSEL REMOVAL) | [10 empty] | 0 | 0 | 0
3 | A 50.75(c) |  | 100% |  | Decontaminate and clean up Unit 1 plant areas (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Utility Staff
3 | A 50.75(c) |  | 100% |  | Process liquid and solid radioactive wastes (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Utility Staff
3 | A 50.75(c) |  | 100% |  | Decon, remove, package, ship and dispose of Unit 1 contaminated systems |  |  | 13812807.0188 | 1164895.5033 | 91336.9152 | 600073.9224 |  | 5142874.5718 |  |  | 20811987.9315 | 5663600 | 26475587.9315 |  |  | 270641.7567 |  | Contaminated systems | 45.764 | /sqft
3 | A Greenfield |  | 100% |  | Remove, package, ship and dispose of Unit 1 clean systems |  |  | 14574158.3201 | 1244671.2283 | 0 | 182235.7793 | 1043487.886 |  |  |  | 17044553.2137 | 3929700 | 20974253.2137 |  | 284076.5961 |  |  | Clean systems | 48.3728 | /sqft
3 | A 50.75(c) |  | 100% |  | Install Unit 1 water cleanup system in fuel transfer canal (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Vessel Removal
3 | A 50.75(c) |  | 100% |  | Segment, package and ship Unit 1 internals as radioactive waste |  |  | 2605134.5996 | 526564.5 | 90000 | 5022524.1 |  | 38003376.0594 |  |  | 46247599.259 | 16177800 | 62425399.259 |  |  | 47360 |  | Decon Structures | 65.2117 | /sqft
3 | A 50.75(c) |  | 100% |  | Decontaminate internals work platform and store (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Vessel Removal
3 | A 50.75(c) |  | 100% |  | Install Unit 1 vessel support structure (WITH VESSEL REMOVAL) | [10 empty] | 0 | 0 | 0 |  |  |  | Vessel Removal
3 | A 50.75(c) |  | 100% |  | Segment and process Unit 1 reactor vessel and associated equipment as LLW |  |  | 2701810.0535 | 148186.5 | 24000 | 2339069.9685 |  | 14901904.8567 |  |  | 20114971.3787 | 6809400 | 26924371.3787 |  |  | 49100
3 | A 50.75(c) |  | 100% |  | Decontaminate reactor vessel platform and store | [10 empty] | 0 | 0 | 0 |  |  |  | Vessel Removal
3 | A 50.75(c) |  | 100% |  | Decontaminate Unit 1 reactor building |  |  | 2529029.6116 | 513797.7889 | 294709.561 | 1795461.6327 |  | 9297096.1137 |  |  | 14430094.708 | 4662600 | 19092694.708 |  |  | 43847.106
UNIT 2
3 | A 50.75(c) |  |  | 100% | Finalize Residual Radiation Inventory (WITH SITE CHARACTERIZATION) | [10 empty] | 0 | 0 | 0
3 | A 50.75(c) |  |  | 100% | Finalize Internals and Vessel Segmenting Details (WITH ACTIVATION ANALYSIS) | [10 empty] | 0 | 0 | 0
3 | A 50.75(c) |  |  | 100% | Revise Integrated Work Sequence and Schedule |  | 53462.3892 | [8 empty] | 53462.3892 | 8000 | 61462.3892
3 | A 50.75(c) |  |  | 100% | Transfer all reactor operating floor CCEs support structures, rigging, internals | [10 empty] | 0 | 0 | 0
[5 empty] | work platforms and process equipment to position and install (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Utility Staff
3 | A 50.75(c) |  |  | 100% | Remove Unit 2 equipment hatch closure (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Utility Staff
3 | A 50.75(c) |  |  | 100% | Remove Unit 2 CRD missile and reactor cavity missile shields (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Utility Staff
3 | A 50.75(c) |  |  | 100% | Remove Unit 2 CRD mechanisms and cables, air ducts, and reactor vessel head (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Utility Staff
3 | A 50.75(c) |  |  | 100% | Remove, segment, package and bury Unit 2 vessel & vessel head insulation |  |  | 182000 |  |  |  |  | 364625 |  |  | 546625 | 180700 | 727325
3 | A 50.75(c) |  |  | 100% | Prepare Unit 2 vessel head for shipment as its own container (WITH VESSEL REMOVAL) | [10 empty] | 0 | 0 | 0
3 | A 50.75(c) |  |  | 100% | Decontaminate and clean up Unit 2 plant areas (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Utility Staff
3 | A 50.75(c) |  |  | 100% | Process liquid and solid radioactive wastes (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Utility Staff
3 | A 50.75(c) |  |  | 100% | Install Unit 2 water cleanup system in fuel transfer canal (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Vessel Removal
3 | A 50.75(c) |  |  | 100% | Segment, package and ship Unit 2 internals as radioactive waste |  |  | 2605134.5996 | 526564.5 | 90000 | 5022524.1 |  | 38003376.0594 |  |  | 46247599.259 | 16177800 | 62425399.259 |  |  | 47360
3 | A 50.75(c) |  |  | 100% | Decontaminate internals work platform and process as LLW (BY UTILITY STAFF) | [10 empty] | 0 | 0 | 0 |  |  |  | Vessel Removal
3 | A 50.75(c) |  |  | 100% | Install Unit 2 vessel support structure (WITH VESSEL REMOVAL) | [10 empty] | 0 | 0 | 0 |  |  |  | Vessel Removal
3 | A 50.75(c) |  |  | 100% | Segment and process Unit 2 reactor vessel and associated equipment as LLW |  |  | 2701810.0535 | 148186.5 | 24000 | 2339069.9685 |  | 14901904.8567 |  |  | 20114971.3787 | 6809400 | 26924371.3787 |  |  | 49100
3 | A 50.75(c) |  |  | 100% | Decon reactor vessel cutting equipment and work platform; package and process as LLW (WITH VESSEL REMOVAL) | [10 empty] | 0 | 0 | 0 |  |  |  | Vessel Removal
3 | A 50.75(c) |  |  | 100% | Decon, remove, package, ship and bury Unit 2 steam generators |  |  | 4340246.0222 | 1532266.6667 | 12800 | 823395.36 |  | 12599366.4 |  |  | 19308074.4489 | 6344800 | 25652874.4489 |  |  | 79162.68
3 | A 50.75(c) |  |  | 100% | Remove, pack, ship and bury Unit 2 Pressurizer |  |  | 1064197.4239 | 0 | 800 | 71767.96 |  | 933410.4 |  |  | 2070175.7839 | 621000 | 2691175.7839 |  |  | 19407.07
3 | A 50.75(c) | 100% |  |  | Decontaminate Radioactive Material Building |  |  | 71103.6117 | 40555.9 | 620.8803 | 10773.5146 |  | 414819.4294 |  |  | 537873.336 | 185700 | 723573.336 |  |  | 1437.9093
3 | A Greenfield | 100% |  |  | Remove non-essential structures |  |  | 2477040.2486 | 892899.5936 | 0 | 331138.3216 | 2179243.035 |  |  |  | 5880321.1988 | 1104300 | 6984621.1988 |  | 42221.1207
[5 empty] | SUBTOTAL - DECOMMISSIONING ACTIVITY COSTS: |  | 53462.3892 | 55250915.0091 | 8270855.3474 | 641867.3565 | 19433197.9476 | 3222730.921 | 148460155.5471 | 0 | 0 | 235333184.518 | 75821300 | 311154484.518 | 0 | 326297.7169 | 705986.2719
DECOMMISSIONING PERIOD DEPENDENT
3 | PD 50.75(c) | 100% |  |  |  | Utility Staff | 39164015.4818 | [8 empty] | 39164015.4818 | 5874600 | 45038615.4818 | 703600.969
3 | PD 50.75(c) | 100% |  |  |  | DGC Staff | 46406897.4178 | [8 empty] | 46406897.4178 | 6961000 | 53367897.4178 | 652296.7317
3 | PD 50.75(c) | 100% |  |  |  | Security | 5905496.1511 | [8 empty] | 5905496.1511 | 885800 | 6791296.1511 | 234533.6563
3 | PD 50.75(c) | 100% |  |  |  | HP Supplies |  |  | 10971688.5306 | [6 empty] | 10971688.5306 | 2742900 | 13714588.5306
3 | PD 50.75(c) | 100% |  |  |  | Equipment |  |  | 7116149.5419 | [6 empty] | 7116149.5419 | 1779000 | 8895149.5419
3 | PD 50.75(c) | 100% |  |  |  | Unit 1 Insurance | [8 empty] | 1364033.9481 | 1364033.9481 | 204600 | 1568633.9481
3 | PD 50.75(c) | 100% |  |  |  | Unit 2 Insurance | [8 empty] | 1364033.9481 | 1364033.9481 | 204600 | 1568633.9481
3 | PD 50.75(c) | 100% |  |  |  | O & M Budget Items |  |  | 27219510.0458 | [6 empty] | 27219510.0458 | 6804900 | 34024410.0458
3 | PD 50.75(c) | 100% |  |  |  | Permits & Fees | [8 empty] | 7910024.308 | 7910024.308 | 1186500 | 9096524.308
3 | PD 50.75(c) | 100% |  |  |  | Waste Transfer and Loading |  | 9400235.1406 | [7 empty] | 9400235.1406 | 2240900 | 11641135.1406 |  |  | 183261.1324
3 | PD 50.75(c) | 100% |  |  |  | Energy | [7 empty] | 12282973.7323 |  | 12282973.7323 | 1842400 | 14125373.7323
3 | PD 50.75(c) | 100% |  |  |  | Severance | 2229959.0344 | [8 empty] | 2229959.0344 | 334500 | 2564459.0344
3 | PD 50.75(c) | 100% |  |  |  | Small Tools |  |  | 1293023.003 | [6 empty] | 1293023.003 | 323300 | 1616323.003
[5 empty] | SUBTOTAL - DECOMMISSIONING PERIOD DEPENDENT |  | 93706368.0851 | 9400235.1406 | 46600371.1213 | 0 | 0 | 0 | 0 | 12282973.7323 | 10638092.2042 | 172628040.2834 | 31385000 | 204013040.2834 | 1590431.357 | 0 | 183261.1324
[5 empty] | TOTAL PERIOD 3 VESSEL AND INTERNALS REMOVAL COSTS: |  | 109297209.4381 | 64651150.1497 | 165871226.4687 | 641867.3565 | 19433197.9476 | 3222730.921 | 148460155.5471 | 14222273.0584 | 19925858.2224 | 545725669.1095 | 138970900 | 684696569.1095 | 2066827.8465 | 326297.7169 | 889247.4043
ACTIVITY
UNIT 1
[6 empty] | Unit 1 Subtotal 10 CFR 50.75(c): | 0 | 27235224.7296 | 3885710.9589 | 513646.4763 | 10652292.9435 | 0 | 81242653.4016 | 0 | 0 | 123529528.5099 | 40459900 | 163989428.5099 | 0 | 0 | 509518.6127
[6 empty] | Unit 1 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 1 Subtotal Greenfield: | 0 | 14574158.3201 | 1244671.2283 | 0 | 182235.7793 | 1043487.886 | 0 | 0 | 0 | 17044553.2137 | 3929700 | 20974253.2137 | 0 | 284076.5961 | 0
UNIT 2
[6 empty] | Unit 2 Subtotal 10 CFR 50.75(c): | 53462.3892 | 10893388.0991 | 2207017.6667 | 127600 | 8256757.3885 | 0 | 66802682.7161 | 0 | 0 | 88340908.2596 | 30141700 | 118482608.2596 | 0 | 0 | 195029.75
[6 empty] | Unit 2 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 2 Subtotal Greenfield: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Common
[6 empty] | Total 10 CFR 50.75(c): | 0 | 71103.6117 | 40555.9 | 620.8803 | 10773.5146 | 0 | 414819.4294 | 0 | 0 | 537873.336 | 185700 | 723573.336 | 0 | 0 | 1437.9093
[6 empty] | Total 10 CFR 50.54(bb): | 0 | 0 | 111000000 | 0 | 0 | 0 | 0 | 0 | 0 | 111000000 | 27750000 | 138750000 | 0 | 0 | 0
[6 empty] | Total Greenfield | 0 | 2477040.2486 | 892899.5936 | 0 | 331138.3216 | 2179243.035 | 0 | 0 | 0 | 5880321.1988 | 1104300 | 6984621.1988 | 0 | 42221.1207 | 0
PERIOID DEPENDENT
UNIT 1
[6 empty] | Unit 1 Subtotal 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 1 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNIT 2
[6 empty] | Unit 2 Subtotal 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 2 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Common
[6 empty] | Total 10 CFR 50.75(c): | 93706368.0851 | 9400235.1406 | 46600371.1213 | 0 | 0 | 0 | 0 | 12282973.7323 | 10638092.2042 | 172628040.2834 | 31385000 | 204013040.2834 | 1590431.357 | 0 | 183261.1324
[6 empty] | Total 10 CFR 50.54(bb): | 15537378.9638 | 0 | 0 | 0 | 0 | 0 | 0 | 1939299.3261 | 9287766.0182 | 26764444.3081 | 4014600 | 30779044.3081 | 476396.4894 | 0 | 0
Unit 1, Unit 2 & Common
[6 empty] | Total 10 CFR 50.75(c): | 93759830.4744 | 47599951.581 | 52733655.6468 | 641867.3565 | 18919823.8467 | 0 | 148460155.5471 | 12282973.7323 | 10638092.2042 | 385036350.3889 | 102172300 | 487208650.3889 | 1590431.357 | 0 | 889247.4043
[6 empty] | Total 10 CFR 50.54(bb): | 15537378.9638 | 0 | 111000000 | 0 | 0 | 0 | 0 | 1939299.3261 | 9287766.0182 | 137764444.3081 | 31764600 | 169529044.3081 | 476396.4894 | 0 | 0
[6 empty] | Total Greenfield | 0 | 17051198.5687 | 2137570.8219 | 0 | 513374.1009 | 3222730.921 | 0 | 0 | 0 | 22924874.4125 | 5034000 | 27958874.4125 | 0 | 326297.7169 | 0
Check
PERIOD 4 DECONTAMINATE BALANCE OF SITE COSTS:
SPENT FUEL ACTIVITIES
[5 empty] | SUBTOTAL - SPENT FUEL ACTIVITIES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPENT FUEL PERIOD DEPENDENT
4 | PD 50.54(bb) | 100% |  |  |  | Utility Staff | 10617670.4269 | [8 empty] | 10617670.4269 | 1592700 | 12210370.4269 | 215928.823
4 | PD 50.54(bb) | 100% |  |  |  | Security | 3253695.8741 | [8 empty] | 3253695.8741 | 488100 | 3741795.8741 | 130865.9533
4 | PD 50.54(bb) | 100% |  |  |  | Insurance | [8 empty] | 5111528.9686 | 5111528.9686 | 766700 | 5878228.9686
4 | PD 50.54(bb) | 100% |  |  |  | O & M Budget Items |  |  | 0 | [6 empty] | 0 | 0 | 0
4 | PD 50.54(bb) | 100% |  |  |  | Permits & Fees | [8 empty] | 3180346.0546 | 3180346.0546 | 477100 | 3657446.0546
4 | PD 50.54(bb) | 100% |  |  |  | Waste Transfer and Loading |  | 0 | [7 empty] | 0 | 0 | 0
4 | PD 50.54(bb) | 100% |  |  |  | Energy | [7 empty] | 1731355.8086 |  | 1731355.8086 | 259700 | 1991055.8086
4 | PD 50.54(bb) | 100% |  |  |  | Spent Fuel Storage Maintenance Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
4 | PD 50.54(bb) | 100% |  |  |  | Small Tools |  |  | 0 | [6 empty] | 0 | 0 | 0
[5 empty] | SUBTOTAL - SPENT FUEL PERIOD DEPENDENT |  | 13871366.301 | 0 | 0 | 0 | 0 | 0 | 0 | 1731355.8086 | 8291875.0233 | 23894597.1329 | 3584300 | 27478897.1329 | 346794.7764 | 0 | 0
DECOMMISSIONING ACTIVITIES
4 | A 50.75(c) |  |  | 100% | Decon, remove, package, ship and dispose of Unit 2 contaminated systems |  |  | 13636891.5682 | 1131353.0369 | 84468.5967 | 554325.364 |  | 4704253.058 |  |  | 20111291.6238 | 5437200 | 25548491.6238 |  |  | 267187.9605
4 | A Greenfield |  |  | 100% | Remove, package, ship and dispose of Unit 2 clean systems |  |  | 14440360.3486 | 1221481.7866 | 0 | 186260.182 | 1069978.9135 |  |  |  | 16918081.2308 | 3895600 | 20813681.2308 |  | 281382.1939
4 | A 50.75(c) |  |  | 100% | Decon Unit 2 Reactor Building |  |  | 2529029.6116 | 513797.7889 | 294709.561 | 1795461.6327 |  | 9297096.1137 |  |  | 14430094.708 | 4662600 | 19092694.708 |  |  | 43847.106
4 | A 50.75(c) | 100% |  |  | Remove Spent fuel storage racks |  |  | 2561342.1101 | 50369.7125 | 8347.6732 | 45037.784 |  | 1555797.6 |  |  | 4220894.8799 | 1220000 | 5440894.8799 |  |  | 49873.6
4 | A 50.75(c) | 100% |  |  | Decon Auxiliary Building |  |  | 5741650.1093 | 1291150.4164 | 521466.146 | 3162576.3366 |  | 11365733.4098 |  |  | 22082576.4181 | 6729600 | 28812176.4181 |  |  | 101851.0262
4 | A 50.75(c) | 100% |  |  | Perform final radiological survey of all structures |  |  | 1904750 | 35583.3333 | [6 empty] | 1940333.3333 | 463000 | 2403333.3333 |  |  |  |  | 3.1756 | /sqft
4 | A 50.75(c) | 100% |  |  | Perform final survey of the site |  |  | 10033000 | 229125 | [6 empty] | 10262125 | 2449000 | 12711125
4 | A 50.75(c) | 100% |  |  | Obtain NRC approval | [10 empty] | 0 | 0 | 0 |  |  |  |  | 6.9796 | 1437480 | sqft | 33 acre site
4 | A 50.75(c) | 100% |  |  | Prepare final report of dismantling program |  | 51018.2423 | [8 empty] | 51018.2423 | 7700 | 58718.2423 | 456
[5 empty] | SUBTOTAL - DECOMMISSIONING ACTIVITY COSTS: |  | 51018.2423 | 50847023.7478 | 4472861.0748 | 908991.977 | 5743661.2992 | 1069978.9135 | 26922880.1815 | 0 | 0 | 90016415.4361 | 24864700 | 114881115.4361 | 456 | 281382.1939 | 462759.6927
DECOMMISSIONING PERIOD DEPENDENT
4 | PD 50.75(c) | 100% |  |  |  | Utility Staff | 28677111.478 | [8 empty] | 28677111.478 | 4301600 | 32978711.478 | 510377.218
4 | PD 50.75(c) | 100% |  |  |  | DGC Staff | 35702441.6817 | [8 empty] | 35702441.6817 | 5355400 | 41057841.6817 | 497290.6227
4 | PD 50.75(c) | 100% |  |  |  | Security | 5272272.7876 | [8 empty] | 5272272.7876 | 790800 | 6063072.7876 | 209385.5254
4 | PD 50.75(c) | 100% |  |  |  | HP Supplies |  |  | 7925608.1249 | [6 empty] | 7925608.1249 | 1981400 | 9907008.1249
4 | PD 50.75(c) | 100% |  |  |  | Equipment |  |  | 8097070.2515 | [6 empty] | 8097070.2515 | 2024300 | 10121370.2515
4 | PD 50.75(c) | 100% |  |  |  | Unit 1 Insurance | [8 empty] | 1217773.8977 | 1217773.8977 | 182700 | 1400473.8977
4 | PD 50.75(c) | 100% |  |  |  | Unit 2 Insurance | [8 empty] | 1217773.8977 | 1217773.8977 | 182700 | 1400473.8977
4 | PD 50.75(c) | 100% |  |  |  | O & M Budget Items |  |  | 13489788.5971 | [6 empty] | 13489788.5971 | 3372400 | 16862188.5971
4 | PD 50.75(c) | 100% |  |  |  | Permits & Fees | [8 empty] | 5964162.218 | 5964162.218 | 894600 | 6858762.218
4 | PD 50.75(c) | 100% |  |  |  | Waste Transfer and Loading |  | 8392284.5195 | [7 empty] | 8392284.5195 | 2000600 | 10392884.5195 |  |  | 163610.7546
4 | PD 50.75(c) | 100% |  |  |  | Energy | [7 empty] | 10400066.0135 |  | 10400066.0135 | 1560000 | 11960066.0135
4 | PD 50.75(c) | 100% |  |  |  | Severance | 819168.6249 | [8 empty] | 819168.6249 | 122900 | 942068.6249
4 | PD 50.75(c) | 100% |  |  |  | Small Tools |  |  | 1184786.1653 | [6 empty] | 1184786.1653 | 296200 | 1480986.1653
[5 empty] | SUBTOTAL - DECOMMISSIONING PERIOD DEPENDENT |  | 70470994.5722 | 8392284.5195 | 30697253.1388 | 0 | 0 | 0 | 0 | 10400066.0135 | 8399710.0134 | 128360308.2574 | 23065600 | 151425908.2574 | 1217053.3661 | 0 | 163610.7546
[5 empty] | TOTAL PERIOD 4 DECONTAMINATE BALANCE OF SITE COSTS: |  | 84393379.1155 | 59239308.2673 | 35170114.2135 | 908991.977 | 5743661.2992 | 1069978.9135 | 26922880.1815 | 12131421.8222 | 16691585.0367 | 242271320.8264 | 51514600 | 293785920.8264 | 1564304.1425 | 281382.1939 | 626370.4472
ACTIVITY
UNIT 1
[6 empty] | Unit 1 Subtotal 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 1 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 1 Subtotal Greenfield: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNIT 2
[6 empty] | Unit 2 Subtotal 10 CFR 50.75(c): | 0 | 16165921.1798 | 1645150.8258 | 379178.1578 | 2349786.9966 | 0 | 14001349.1717 | 0 | 0 | 34541386.3317 | 10099800 | 44641186.3317 | 0 | 0 | 311035.0665
[6 empty] | Unit 2 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 2 Subtotal Greenfield: | 0 | 14440360.3486 | 1221481.7866 | 0 | 186260.182 | 1069978.9135 | 0 | 0 | 0 | 16918081.2308 | 3895600 | 20813681.2308 | 0 | 281382.1939 | 0
Common
[6 empty] | Common Subtotal 10 CFR 50.75(c): | 51018.2423 | 20240742.2194 | 1606228.4623 | 529813.8192 | 3207614.1206 | 0 | 12921531.0098 | 0 | 0 | 38556947.8736 | 10869300 | 49426247.8736 | 456 | 0 | 151724.6262
[6 empty] | Common Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Common Subtotal Greenfield: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PERIOD DEPENDENT
UNIT 1
[6 empty] | Unit 1 Subtotal 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 1 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNIT 2
[6 empty] | Unit 2 Subtotal 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 2 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Common
[6 empty] | Common Subtotal 10 CFR 50.75(c): | 70470994.5722 | 8392284.5195 | 30697253.1388 | 0 | 0 | 0 | 0 | 10400066.0135 | 8399710.0134 | 128360308.2574 | 23065600 | 151425908.2574 | 1217053.3661 | 0 | 163610.7546
[6 empty] | Common Subtotal 10 CFR 50.54(bb): | 13871366.301 | 0 | 0 | 0 | 0 | 0 | 0 | 1731355.8086 | 8291875.0233 | 23894597.1329 | 3584300 | 27478897.1329 | 346794.7764 | 0 | 0
Unit 1, Unit 2 & Common
[6 empty] | Total 10 CFR 50.75(c): | 70522012.8145 | 44798947.9186 | 33948632.4269 | 908991.977 | 5557401.1173 | 0 | 26922880.1815 | 10400066.0135 | 8399710.0134 | 201458642.4628 | 44034700 | 245493342.4628 | 1217509.3661 | 0 | 626370.4472
[6 empty] | Total 10 CFR 50.54(bb): | 13871366.301 | 0 | 0 | 0 | 0 | 0 | 0 | 1731355.8086 | 8291875.0233 | 23894597.1329 | 3584300 | 27478897.1329 | 346794.7764 | 0 | 0
[6 empty] | Total Greenfield | 0 | 14440360.3486 | 1221481.7866 | 0 | 186260.182 | 1069978.9135 | 0 | 0 | 0 | 16918081.2308 | 3895600 | 20813681.2308 | 0 | 281382.1939 | 0
PERIOD 5 - CLEAN STRUCTURE DEMOLITION COSTS:
SPENT FUEL ACTIVITIES
[5 empty] | SUBTOTAL - SPENT FUEL ACTIVITIES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPENT FUEL PERIOD DEPENDENT
5 | PD 50.54(bb) | 100% |  |  |  | Utility Staff | 2534302.8449 | [8 empty] | 2534302.8449 | 380100 | 2914402.8449 | 44551.6566
5 | PD 50.54(bb) | 100% |  |  |  | Security | 1142375.6514 | [8 empty] | 1142375.6514 | 171400 | 1313775.6514 | 40643.6166
5 | PD 50.54(bb) | 100% |  |  |  | HP Supplies |  |  | 109483.6508 | [6 empty] | 109483.6508 | 27400 | 136883.6508 | 40643.6166
5 | PD 50.54(bb) | 100% |  |  |  | Equipment |  |  | 0 | [6 empty] | 0 | 0 | 0
5 | PD 50.54(bb) | 100% |  |  |  | Insurance | [8 empty] | 300624.2471 | 300624.2471 | 45100 | 345724.2471
5 | PD 50.54(bb) | 100% |  |  |  | O & M Budget Items |  |  | 0 | [6 empty] | 0 | 0 | 0
5 | PD 50.54(bb) | 100% |  |  |  | Permits & Fees | [8 empty] | 654923.8261 | 654923.8261 | 98200 | 753123.8261
5 | PD 50.54(bb) | 100% |  |  |  | Waste Transfer and Loading |  | 0 | [7 empty] | 0 | 0 | 0
5 | PD 50.54(bb) | 100% |  |  |  | Energy | [7 empty] | 25365.063 |  | 25365.063 | 3800 | 29165.063
5 | PD 50.54(bb) | 100% |  |  |  | Spent Fuel Storage Maintenance Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
5 | PD 50.54(bb) | 100% |  |  |  | Small Tools |  |  | 0 | [6 empty] | 0 | 0 | 0
[5 empty] | SUBTOTAL - SPENT FUEL PERIOD DEPENDENT |  | 3676678.4963 | 0 | 109483.6508 | 0 | 0 | 0 | 0 | 25365.063 | 955548.0732 | 4767075.2833 | 726000 | 5493075.2833 | 125838.8898 | 0 | 0
DECOMMISSIONING ACTIVITIES
5 | A Greenfield |  | 100% |  | Remove Unit 1 reactor building |  |  | 6713605.1988 | 4046917.4177 | 0 | 1919484.6034 | 12635196.5625 |  |  |  | 25315203.7824 | 4297000 | 29612203.7824 |  | 109446.9635 |  |  | Remove structures | 47.9351
5 | A Greenfield |  |  | 100% | Remove Unit 2 reactor building |  |  | 6713605.1988 | 4046917.4177 | 0 | 1919484.6034 | 12635196.5625 |  |  |  | 25315203.7824 | 4297000 | 29612203.7824 |  | 109446.9635
5 | A Greenfield | 100% |  |  | Remove Auxiliary Building |  |  | 5492727.5965 | 3843180.8718 | 0 | 1107077.7668 | 7287448.5 |  |  |  | 17730434.7351 | 3241900 | 20972334.7351 |  | 86778.0562
5 | A Greenfield | 100% |  |  | Remove Turbine Building. |  |  | 3926953.1011 | 3659567.4909 | 0 | 1090599.6823 | 7178979.885 |  |  |  | 15856100.1593 | 2808300 | 18664400.1593 |  | 64508.0728
5 | A Greenfield | 100% |  |  | Remove Intake Structures |  |  | 787930.1463 | 1334758.6522 | 0 | 159893.7175 | 1052516.1525 |  |  |  | 3335098.6686 | 661900 | 3996998.6686 |  | 13109.7832
5 | A Greenfield | 100% |  |  | Remove Electrical Transformers |  |  | 419246.7256 | 16504.2922 | 0 | 61525.8544 | 405000 |  |  |  | 902276.8722 | 158100 | 1060376.8722 |  | 8296.9947
5 | A Greenfield |  | 100% |  | Removal of Unit 1 Turbine Generator |  |  | 155208.9005 | 9273.3492 | 0 | 6836.206 | 45000 |  |  |  | 216318.4557 | 45300 | 261618.4557 |  | 2696.637
5 | A Greenfield |  | 100% |  | Removal of Unit 1 Main Condenser |  |  | 1349630.3729 | 9682.5181 | 0 | 75022.9862 | 493846.2 |  |  |  | 1928182.0772 | 390000 | 2318182.0772 |  | 21580.376
5 | A Greenfield |  |  | 100% | Removal of Unit 2 Turbine Generator |  |  | 155208.9005 | 9273.3492 | 0 | 6836.206 | 45000 |  |  |  | 216318.4557 | 45300 | 261618.4557 |  | 2696.637
5 | A Greenfield |  |  | 100% | Removal of Unit 2 Main Condenser |  |  | 1349630.3729 | 9682.5181 | 0 | 75022.9862 | 493846.2 |  |  |  | 1928182.0772 | 390000 | 2318182.0772 |  | 21580.376
5 | A Greenfield | 100% |  |  | Remove of Standby Diesel Generators |  |  | 30929.4389 | 7482.8054 | 0 | 2050.8618 | 13500 |  |  |  | 53963.1061 | 11000 | 64963.1061 |  | 532.3336
5 | A Greenfield | 100% |  |  | Remove Office building |  |  | 237595.3052 | 211978.6294 | 0 | 56128.4988 | 369471.375 |  |  |  | 875173.8084 | 158900 | 1034073.8084 |  | 4105.044
5 | A Greenfield | 100% |  |  | Remove Service building |  |  | 500049.9131 | 303307.688 | 0 | 176317.7652 | 1160629.065 |  |  |  | 2140304.4313 | 349800 | 2490104.4313 |  | 8160.0754
5 | A Greenfield | 100% |  |  | Remove Radioactive Material Building |  |  | 919636.8424 | 219467.6161 | 0 | 159275.1092 | 1048444.1025 |  |  |  | 2346823.6702 | 413900 | 2760723.6702 |  | 14743.0569
[5 empty] | SUBTOTAL - DECOMMISSIONING ACTIVITY COSTS: |  | 0 | 28751958.0137 | 17727994.6158 | 0 | 6815556.8473 | 44864074.605 | 0 | 0 | 0 | 98159584.0818 | 17268400 | 115427984.0818 | 0 | 467681.3698 | 0
DECOMMISSIONING PERIOD DEPENDENT
5 | PD Greenfield | 100% |  |  |  | Utility Staff | 983855.4048 | [8 empty] | 983855.4048 | 147600 | 1131455.4048 | 21885.0243
5 | PD Greenfield | 100% |  |  |  | DGC Staff | 8592632.061 | [8 empty] | 8592632.061 | 1288900 | 9881532.061 | 106298.6895
5 | PD Greenfield | 100% |  |  |  | Security | 557764.2021 | [8 empty] | 557764.2021 | 83700 | 641464.2021 | 21885.0243
5 | PD Greenfield | 100% |  |  |  | HP Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
5 | PD Greenfield | 100% |  |  |  | Equipment |  |  | 3276703.7783 | [6 empty] | 3276703.7783 | 819200 | 4095903.7783
5 | PD Greenfield | 100% |  |  |  | Unit 1 Insurance | [8 empty] | 428339.7988 | 428339.7988 | 64300 | 492639.7988
5 | PD Greenfield | 100% |  |  |  | Unit 2 Insurance | [8 empty] | 428339.7988 | 428339.7988 | 64300 | 492639.7988
5 | PD Greenfield | 100% |  |  |  | O & M Budget Items |  |  | 2473264.7817 | [6 empty] | 2473264.7817 | 618300 | 3091564.7817
5 | PD Greenfield | 100% |  |  |  | Permits & Fees | [8 empty] | 306416.149 | 306416.149 | 46000 | 352416.149
5 | PD Greenfield | 100% |  |  |  | Waste Transfer and Loading |  | 2527774.6124 | [7 empty] | 2527774.6124 | 602600 | 3130374.6124 |  | 46904.5975
5 | PD Greenfield | 100% |  |  |  | Energy | [7 empty] | 414293.6164 |  | 414293.6164 | 62100 | 476393.6164
5 | PD Greenfield | 100% |  |  |  | Severance | 4084465.7824 | [8 empty] | 4084465.7824 | 612700 | 4697165.7824
5 | PD Greenfield | 100% |  |  |  | Small Tools |  |  | 625594.6525 | [6 empty] | 625594.6525 | 156400 | 781994.6525
[5 empty] | SUBTOTAL - DECOMMISSIONING PERIOD DEPENDENT |  | 14218717.4503 | 2527774.6124 | 6375563.2124 | 0 | 0 | 0 | 0 | 414293.6164 | 1163095.7465 | 24699444.6381 | 4566100 | 29265544.6381 | 150068.7381 | 46904.5975 | 0
[5 empty] | TOTAL PERIOD 5 - CLEAN STRUCTURE DEMOLITION COSTS: |  | 17895395.9466 | 31279732.6261 | 24213041.479 | 0 | 6815556.8473 | 44864074.605 | 0 | 439658.6794 | 2118643.8197 | 127626104.0032 | 22560500 | 150186604.0032 | 275907.6279 | 514585.9674 | 0
ACTIVITY
UNIT 1
[6 empty] | Unit 1 Subtotal Greenfield (g): | 0 | 8218444.4723 | 4065873.2849 | 0 | 2001343.7956 | 13174042.7625 | 0 | 0 | 0 | 27459704.3153 | 4732300 | 32192004.3153 | 0 | 133723.9765 | 0
[6 empty] | Unit 1 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNIT 2
[6 empty] | Unit 2 Subtotal Greenfield (g): | 0 | 8218444.4723 | 4065873.2849 | 0 | 2001343.7956 | 13174042.7625 | 0 | 0 | 0 | 27459704.3153 | 4732300 | 32192004.3153 | 0 | 133723.9765 | 0
[6 empty] | Unit 2 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Common
[6 empty] | Common Subtotal Greenfield (g) | 0 | 12315069.0691 | 9596248.0459 | 0 | 2812869.2561 | 18515989.08 | 0 | 0 | 0 | 43240175.4512 | 7803800 | 51043975.4512 | 0 | 200233.4169 | 0
[6 empty] | Common Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PERIOD DEPENDENT
UNIT 1
[6 empty] | Unit 1 Subtotal Greenfield (g): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 1 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNIT 2
[6 empty] | Unit 2 Subtotal Greenfield (g): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 2 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Common
[6 empty] | Common Subtotal Greenfield (g) | 14218717.4503 | 2527774.6124 | 6375563.2124 | 0 | 0 | 0 | 0 | 414293.6164 | 1163095.7465 | 24699444.6381 | 4566100 | 29265544.6381 | 150068.7381 | 46904.5975 | 0
[6 empty] | Common Subtotal 10 CFR 50.54(bb): | 3676678.4963 | 0 | 109483.6508 | 0 | 0 | 0 | 0 | 25365.063 | 955548.0732 | 4767075.2833 | 726000 | 5493075.2833 | 125838.8898 | 0 | 0
Unit 1, Unit 2 & Common
[6 empty] | Total Greenfield (g): | 14218717.4503 | 31279732.6261 | 24103557.8283 | 0 | 6815556.8473 | 44864074.605 | 0 | 414293.6164 | 1163095.7465 | 122859028.7199 | 21834500 | 144693528.7199 | 150068.7381 | 514585.9674 | 0
[6 empty] | Total 10 CFR 50.54(bb): | 3676678.4963 | 0 | 109483.6508 | 0 | 0 | 0 | 0 | 25365.063 | 955548.0732 | 4767075.2833 | 726000 | 5493075.2833 | 125838.8898 | 0 | 0
PERIOD 6 - RESTORE SITE COSTS:
SPENT FUEL ACTIVITIES
[5 empty] | SUBTOTAL - SPENT FUEL ACTIVITIES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPENT FUEL PERIOD DEPENDENT
6 | PD 50.54(bb) | 100% |  |  |  | Utility Staff | 253891.9061 | [8 empty] | 253891.9061 | 38100 | 291991.9061 | 4463.2807
6 | PD 50.54(bb) | 100% |  |  |  | Security | 114445.6481 | [8 empty] | 114445.6481 | 17200 | 131645.6481 | 4071.7649
6 | PD 50.54(bb) | 100% |  |  |  | HP Supplies |  |  | 9758.5642 | [6 empty] | 9758.5642 | 2400 | 12158.5642 | 4071.7649
6 | PD 50.54(bb) | 100% |  |  |  | Insurance | [8 empty] | 30117.1832 | 30117.1832 | 4500 | 34617.1832
6 | PD 50.54(bb) | 100% |  |  |  | Equipment |  |  | 0 | [6 empty] | 0 | 0 | 0
6 | PD 50.54(bb) | 100% |  |  |  | O & M Budget Items |  |  | 0 | [6 empty] | 0 | 0 | 0
6 | PD 50.54(bb) | 100% |  |  |  | Permits & Fees | [8 empty] | 65611.6766 | 65611.6766 | 9800 | 75411.6766
6 | PD 50.54(bb) | 100% |  |  |  | Waste Transfer and Loading |  | 0 | [7 empty] | 0 | 0 | 0
6 | PD 50.54(bb) | 100% |  |  |  | Energy | [7 empty] | 2541.1265 |  | 2541.1265 | 400 | 2941.1265
6 | PD 50.54(bb) | 100% |  |  |  | Spent Fuel Storage Maintenance Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
6 | PD 50.54(bb) | 100% |  |  |  | Small Tools |  |  | 0 | [6 empty] | 0 | 0 | 0
[5 empty] | SUBTOTAL - SPENT FUEL PERIOD DEPENDENT |  | 368337.5543 | 0 | 9758.5642 | 0 | 0 | 0 | 0 | 2541.1265 | 95728.8598 | 476366.1048 | 72400 | 548766.1048 | 12606.8105 | 0 | 0
DECOMMISSIONING ACTIVITIES
6 | A Greenfield | 100% |  |  | Backfill, grade and landscape site |  |  | 183678 | [7 empty] | 183678 | 43800 | 227478 |  | 1756.92 |  |  | 1.15 | /sqft | 159720 | sq ft
[5 empty] | SUBTOTAL - DECOMMISSIONING ACTIVITY COSTS: |  | 0 | 183678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183678 | 43800 | 227478 | 0 | 1756.92 | 0
DECOMMISSIONING PERIOD DEPENDENT
6 | PD Greenfield | 100% |  |  |  | Utility Staff | 42028.5546 | [8 empty] | 42028.5546 | 6300 | 48328.5546 | 939.638
6 | PD Greenfield | 100% |  |  |  | DGC Staff | 425069.3976 | [8 empty] | 425069.3976 | 63800 | 488869.3976 | 4698.1902
6 | PD Greenfield | 100% |  |  |  | Security | 13940.9887 | [8 empty] | 13940.9887 | 2100 | 16040.9887 | 626.4254
6 | PD Greenfield | 100% |  |  |  | HP Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
6 | PD Greenfield | 100% |  |  |  | Equipment |  |  | 119433.1387 | [6 empty] | 119433.1387 | 29900 | 149333.1387
6 | PD Greenfield | 100% |  |  |  | Unit 1 Insurance | [8 empty] | 42912.0017 | 42912.0017 | 6400 | 49312.0017
6 | PD Greenfield | 100% |  |  |  | Unit 2 Insurance | [8 empty] | 42912.0017 | 42912.0017 | 6400 | 49312.0017
6 | PD Greenfield | 100% |  |  |  | O & M Budget Items |  |  | 179282.1528 | [6 empty] | 179282.1528 | 44800 | 224082.1528
6 | PD Greenfield | 100% |  |  |  | Permits & Fees | [8 empty] | 30697.4284 | 30697.4284 | 4600 | 35297.4284
6 | PD Greenfield | 100% |  |  |  | Waste Transfer and Loading |  | 253237.8938 | [7 empty] | 253237.8938 | 60400 | 313637.8938 |  | 4699.0034
6 | PD Greenfield | 100% |  |  |  | Energy | [7 empty] | 22402.2632 |  | 22402.2632 | 3400 | 25802.2632
6 | PD Greenfield | 100% |  |  |  | Severance | 318565.5763 | [8 empty] | 318565.5763 | 47800 | 366365.5763
6 | PD Greenfield | 100% |  |  |  | Small Tools |  |  | 8738.3179 | [6 empty] | 8738.3179 | 2200 | 10938.3179
[5 empty] | SUBTOTAL - DECOMMISSIONING PERIOD DEPENDENT |  | 799604.5173 | 253237.8938 | 307453.6094 | 0 | 0 | 0 | 0 | 22402.2632 | 116521.4318 | 1499219.7154 | 278100 | 1777319.7154 | 6264.2536 | 4699.0034 | 0
[5 empty] | TOTAL PERIOD 6 - RESTORE SITE COSTS: |  | 1167942.0716 | 436915.8938 | 317212.1736 | 0 | 0 | 0 | 0 | 24943.3897 | 212250.2916 | 2159263.8202 | 394300 | 2553563.8202 | 18871.0641 | 6455.9234 | 0
ACTIVITY
UNIT 1
[6 empty] | Unit 1 Subtotal Greenfield (g): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 1 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNIT 2
[6 empty] | Unit 2 Subtotal Greenfield (g): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 2 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Common
[6 empty] | Common Subtotal Greenfield (g) | 0 | 183678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183678 | 43800 | 227478 | 0 | 1756.92 | 0
[6 empty] | Common Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PERIOD DEPENDENT
UNIT 1
[6 empty] | Unit 1 Subtotal Greenfield (g): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 1 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNIT 2
[6 empty] | Unit 2 Subtotal Greenfield (g): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Unit 2 Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Common
[6 empty] | Common Subtotal Greenfield (g) | 799604.5173 | 253237.8938 | 307453.6094 | 0 | 0 | 0 | 0 | 22402.2632 | 116521.4318 | 1499219.7154 | 278100 | 1777319.7154 | 6264.2536 | 4699.0034 | 0
[6 empty] | Common Subtotal 10 CFR 50.54(bb): | 368337.5543 | 0 | 9758.5642 | 0 | 0 | 0 | 0 | 2541.1265 | 95728.8598 | 476366.1048 | 72400 | 548766.1048 | 12606.8105 | 0 | 0
Unit 1, Unit 2 & Common
[6 empty] | Total Greenfield (g): | 799604.5173 | 436915.8938 | 307453.6094 | 0 | 0 | 0 | 0 | 22402.2632 | 116521.4318 | 1682897.7154 | 321900 | 2004797.7154 | 6264.2536 | 6455.9234 | 0
[6 empty] | Total 10 CFR 50.54(bb): | 368337.5543 | 0 | 9758.5642 | 0 | 0 | 0 | 0 | 2541.1265 | 95728.8598 | 476366.1048 | 72400 | 548766.1048 | 12606.8105 | 0 | 0
PERIOD 7 - DRY STORAGE COSTS:
SPENT FUEL ACTIVITIES
7 | A 50.54(bb) | 100% |  |  | Continue to ship fuel to repository
[5 empty] | SUBTOTAL - SPENT FUEL ACTIVITIES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPENT FUEL PERIOD DEPENDENT
7 | PD 50.54(bb) | 100% |  |  |  | Utility Staff | 1686026.9054 | [8 empty] | 1686026.9054 | 252900 | 1938926.9054 | 29639.43
7 | PD 50.54(bb) | 100% |  |  |  | Security | 760002.3368 | [8 empty] | 760002.3368 | 114000 | 874002.3368 | 27039.48
7 | PD 50.54(bb) | 100% |  |  |  | Insurance | [8 empty] | 200000 | 200000 | 20000 | 220000
7 | PD 50.54(bb) | 100% |  |  |  | O & M Budget Items |  |  | 1175365.1714 | [6 empty] | 1175365.1714 | 117500 | 1292865.1714
7 | PD 50.54(bb) | 100% |  |  |  | Permits & Fees | [8 empty] | 435709.25 | 435709.25 | 43600 | 479309.25
7 | PD 50.54(bb) | 100% |  |  |  | Waste Transfer and Loading |  | 0 | [7 empty] | 0 | 0 | 0
7 | PD 50.54(bb) | 100% |  |  |  | Energy | [7 empty] | 16874.9283 |  | 16874.9283 | 1700 | 18574.9283
7 | PD 50.54(bb) | 100% |  |  |  | Equipment |  |  | 22178.0052 | [6 empty] | 22178.0052 | 2200 | 24378.0052
7 | PD 50.54(bb) | 100% |  |  |  | HP Supplies |  |  | 58778.7827 | [6 empty] | 58778.7827 | 5900 | 64678.7827
7 | PD 50.54(bb) | 100% |  |  |  | Spent Fuel Storage Maintenance Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
7 | PD 50.54(bb) | 100% |  |  |  | Severance | 0 | [8 empty] | 0 | 0 | 0
7 | PD 50.54(bb) | 100% |  |  |  | Small Tools |  |  | 0 | [6 empty] | 0 | 0 | 0
[5 empty] | SUBTOTAL - SPENT FUEL PERIOD DEPENDENT |  | 2446029.2422 | 0 | 1256321.9593 | 0 | 0 | 0 | 0 | 16874.9283 | 635709.25 | 4354935.3798 | 557800 | 4912735.3798 | 56678.91 | 0 | 0
DECOMMISSIONING ACTIVITIES
[5 empty] | SUBTOTAL - DECOMMISSIONING ACTIVITY COSTS: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DECOMMISSIONING PERIOD DEPENDENT
7 | PD 50.75(c) | 100% |  |  |  | DGC Staff | 0 | [8 empty] | 0 | 0 | 0 | 0
7 | PD 50.75(c) | 100% |  |  |  | Severance | 0 | [8 empty] | 0 | 0 | 0
[5 empty] | SUBTOTAL - DECOMMISSIONING PERIOD DEPENDENT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | TOTAL PERIOD 7 - DRY STORAGE COSTS: |  | 2446029.2422 | 0 | 1256321.9593 | 0 | 0 | 0 | 0 | 16874.9283 | 635709.25 | 4354935.3798 | 557800 | 4912735.3798 | 56678.91
ACTIVITY
Common
[6 empty] | Common Subtotal 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Common Subtotal 10 CFR 50.54(bb): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PERIOD DEPENDENT
Common
[6 empty] | Common Subtotal 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Common Subtotal 10 CFR 50.54(bb): | 2446029.2422 | 0 | 1256321.9593 | 0 | 0 | 0 | 0 | 16874.9283 | 635709.25 | 4354935.3798 | 557800 | 4912735.3798 | 56678.91 | 0 | 0
Unit 1, Unit 2 & Common
[6 empty] | Total 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Total 10 CFR 50.54(bb): | 2446029.2422 | 0 | 1256321.9593 | 0 | 0 | 0 | 0 | 16874.9283 | 635709.25 | 4354935.3798 | 557800 | 4912735.3798 | 56678.91 | 0 | 0
PERIOD 8 - ISFSI REMOVAL COSTS:
8 | A 50.54(bb) | 100% |  |  | SPENT FUEL ACTIVITIES |  |  | 3001256.067 | 109979.5178 |  |  | 175708.14 | 25681914.1553 |  |  | 28968857.88 | 10432000 | 39400857.88 |  | 375.1894 | 54838.5653
[5 empty] | SUBTOTAL - SPENT FUEL ACTIVITIES |  | 0 | 3001256.067 | 109979.5178 | 0 | 0 | 175708.14 | 25681914.1553 | 0 | 0 | 28968857.88 | 10432000 | 39400857.88 | 0 | 375.1894 | 54838.5653
SPENT FUEL PERIOD DEPENDENT
8 | PD 50.54(bb) | 100% |  |  |  | Utility Staff | 3679010.4195 | [8 empty] | 3679010.4195 | 551900 | 4230910.4195 | 0
8 | PD 50.54(bb) | 100% |  |  |  | DGC Staff | 3784122.632 | [8 empty] | 3784122.632 | 567600 | 4351722.632 | 0
8 | PD 50.54(bb) | 100% |  |  |  | Security | 1211637.717 | [8 empty] | 1211637.717 | 181700 | 1393337.717 | 0
8 | PD 50.54(bb) | 100% |  |  |  | HP Supplies |  |  | 44629.9378 | [6 empty] | 44629.9378 | 11200 | 55829.9378 | 0
8 | PD 50.54(bb) | 100% |  |  |  | Insurance | [8 empty] | 569933.8 | 569933.8 | 85500 | 655433.8
8 | PD 50.54(bb) | 100% |  |  |  | Equipment |  |  | 1962710.547 | [6 empty] | 1962710.547 | 196300 | 2159010.547
8 | PD 50.54(bb) | 100% |  |  |  | O & M Budget Items |  |  | 906576.2 | [6 empty] | 906576.2 | 226600 | 1133176.2
8 | PD 50.54(bb) | 100% |  |  |  | Permits & Fees | [8 empty] | 869818.5 | 869818.5 | 130500 | 1000318.5
8 | PD 50.54(bb) | 100% |  |  |  | Waste Transfer and Loading |  | 1221960.2619 | [7 empty] | 1221960.2619 | 291300 | 1513260.2619
8 | PD 50.54(bb) | 100% |  |  |  | Energy | [7 empty] | 100828.5743 |  | 100828.5743 | 15100 | 115928.5743
8 | PD 50.54(bb) | 100% |  |  |  | Spent Fuel Storage Maintenance Supplies | [9 empty] | 0 | 0 | 0
8 | PD 50.54(bb) | 100% |  |  |  | Severance | 773659.2568 | [8 empty] | 773659.2568 | 116000 | 889659.2568
8 | PD 50.54(bb) | 100% |  |  |  | Small Tools |  |  | 42232.1633 | [6 empty] | 42232.1633 | 10600 | 52832.1633
[5 empty] | SUBTOTAL - SPENT FUEL PERIOD DEPENDENT |  | 9448430.0254 | 1221960.2619 | 2956148.8481 | 0 | 0 | 0 | 0 | 100828.5743 | 1439752.3 | 15167120.0096 | 2384300 | 17551420.0096 | 0 | 0 | 0
DECOMMISSIONING ACTIVITIES
[5 empty] | SUBTOTAL - DECOMMISSIONING ACTIVITY COSTS: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DECOMMISSIONING PERIOD DEPENDENT
8 | PD 50.75(c) | 100% |  |  |  | Utility Staff | 0 | [8 empty] | 0 | 0 | 0 | 0
8 | PD 50.75(c) | 100% |  |  |  | DGC Staff | 0 | [8 empty] | 0 | 0 | 0
8 | PD 50.75(c) | 100% |  |  |  | Security | 0 | [8 empty] | 0 | 0 | 0 | 0
8 | PD 50.75(c) | 100% |  |  |  | HP Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
8 | PD 50.75(c) | 100% |  |  |  | Equipment |  |  | 0 | [6 empty] | 0 | 0 | 0
8 | PD 50.75(c) | 100% |  |  |  | Unit 1 Insurance | [8 empty] | 0 | 0 | 0 | 0
8 | PD 50.75(c) | 100% |  |  |  | Unit 2 Insurance | [8 empty] | 0 | 0 | 0 | 0
8 | PD 50.75(c) | 100% |  |  |  | O & M Budget Items |  |  | 0 | [6 empty] | 0 | 0 | 0
8 | PD 50.75(c) | 100% |  |  |  | Permits & Fees | [8 empty] | 0 | 0 | 0 | 0
8 | PD 50.75(c) | 100% |  |  |  | Waste Transfer and Loading |  | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0
8 | PD 50.75(c) | 100% |  |  |  | Energy | [7 empty] | 0 |  | 0 | 0 | 0
8 | PD 50.75(c) | 100% |  |  |  | Severance | 0 | [8 empty] | 0 | 0 | 0
8 | PD 50.75(c) | 100% |  |  |  | Small Tools |  |  | 0 | [6 empty] | 0 | 0 | 0
[5 empty] | SUBTOTAL - DECOMMISSIONING PERIOD DEPENDENT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | TOTAL PERIOD 8 - ISFSI REMOVAL COSTS: |  | 9448430.0254 | 4223216.3288 | 3066128.3659 | 0 | 0 | 175708.14 | 25681914.1553 | 100828.5743 | 1439752.3 | 44135977.8896 | 12816300 | 56952277.8896 | 0 | 375.1894 | 54838.5653
ACTIVITY
Common
[6 empty] | Total 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Common Subtotal Greenfield (g) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Common Subtotal 50.54 (bb) | 0 | 3001256.067 | 109979.5178 | 0 | 0 | 175708.14 | 25681914.1553 | 0 | 0 | 28968857.88 | 10432000 | 39400857.88 | 0 | 375.1894 | 54838.5653
PERIOD DEPENDENT
Common
[6 empty] | Total 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Common Subtotal Greenfield (g) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Common Subtotal 50.54 (bb) | 9448430.0254 | 1221960.2619 | 2956148.8481 | 0 | 0 | 0 | 0 | 100828.5743 | 1439752.3 | 15167120.0096 | 2384300 | 17551420.0096 | 0 | 0 | 0
Unit 1, Unit 2 & Common
[6 empty] | Total 10 CFR 50.75(c): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Total Greenfield (g): | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Total 50.54(bb) | 9448430.0254 | 4223216.3288 | 3066128.3659 | 0 | 0 | 175708.14 | 25681914.1553 | 100828.5743 | 1439752.3 | 44135977.8896 | 12816300 | 56952277.8896 | 0 | 375.1894 | 54838.5653
PERIOD 9 COSTS:
SPENT FUEL ACTIVITIES
[16 empty] | 0 | 0 | 0
SPENT FUEL PERIOD DEPENDENT
9 | PD 50.54(bb) | 100% |  |  |  | Utility Staff | 0 | [8 empty] | 0 | 0 | 0 | 0
9 | PD 50.54(bb) | 100% |  |  |  | Security | 0 | [8 empty] | 0 | 0 | 0 | 0
9 | PD 50.54(bb) | 100% |  |  |  | Insurance | [8 empty] | 0 | 0 | 0 | 0
9 | PD 50.54(bb) | 100% |  |  |  | O & M Budget Items | [9 empty] | 0 | 0 | 0
9 | PD 50.54(bb) | 100% |  |  |  | Permits & Fees | [8 empty] | 0 | 0 | 0 | 0
9 | PD 50.54(bb) | 100% |  |  |  | Waste Transfer and Loading |  | 0 | [7 empty] | 0 | 0 | 0
9 | PD 50.54(bb) | 100% |  |  |  | Energy | [7 empty] | 0 |  | 0 | 0 | 0
9 | PD 50.54(bb) | 100% |  |  |  | Equipment |  |  | 0 | [6 empty] | 0 | 0 | 0
9 | PD 50.54(bb) | 100% |  |  |  | HP Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
9 | PD 50.54(bb) | 100% |  |  |  | Spent Fuel Storage Maintenance Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
9 | PD 50.54(bb) | 100% |  |  |  | Small Tools |  |  | 0 | [6 empty] | 0 | 0 | 0
9 | PD 50.54(bb) | 100% |  |  |  | Severance | 0 | [8 empty] | 0 | 0 | 0
[5 empty] | SUBTOTAL - SPENT FUEL PERIOD DEPENDENT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | TOTAL PERIOD 9 COSTS: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTIVITY
Common
[6 empty] | Total 50.54(bb) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PERIOD DEPENDENT
Common
[6 empty] | Total 50.54(bb) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PERIOD 10 COSTS:
SPENT FUEL ACTIVITIES
[5 empty] | SUBTOTAL - SPENT FUEL ACTIVITIES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPENT FUEL PERIOD DEPENDENT
10 | PD 50.54(bb) | 100% |  |  |  | Utility Staff | 0 | [8 empty] | 0 | 0 | 0 | 0
10 | PD 50.54(bb) | 100% |  |  |  | DGC Staff | 0 | [8 empty] | 0 | 0 | 0 | 0
10 | PD 50.54(bb) | 100% |  |  |  | Security | 0 | [8 empty] | 0 | 0 | 0 | 0
10 | PD 50.54(bb) | 100% |  |  |  | Insurance | [8 empty] | 0 | 0 | 0 | 0
10 | PD 50.54(bb) | 100% |  |  |  | O & M Budget Items | [9 empty] | 0 | 0 | 0
10 | PD 50.54(bb) | 100% |  |  |  | Permits & Fees | [8 empty] | 0 | 0 | 0 | 0
10 | PD 50.54(bb) | 100% |  |  |  | Waste Transfer and Loading |  | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0
10 | PD 50.54(bb) | 100% |  |  |  | Energy | [7 empty] | 0 |  | 0 | 0 | 0
10 | PD 50.54(bb) | 100% |  |  |  | Equipment |  |  | 0 | [6 empty] | 0 | 0 | 0
10 | PD 50.54(bb) | 100% |  |  |  | HP Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
10 | PD 50.54(bb) | 100% |  |  |  | Spent Fuel Storage Maintenance Supplies |  |  | 0 | [6 empty] | 0 | 0 | 0
10 | PD 50.54(bb) | 100% |  |  |  | Small Tools |  |  | 0 | [6 empty] | 0 | 0 | 0
10 | PD 50.54(bb) | 100% |  |  |  | Severance | 0 | [8 empty] | 0 | 0 | 0
[5 empty] | SUBTOTAL - SPENT FUEL PERIOD DEPENDENT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | TOTAL PERIOD 10 COSTS: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACTIVITY
Common
[6 empty] | Total 50.54(bb) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PERIOD DEPENDENT
Common
[6 empty] | Total 50.54(bb) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL ACTIVITY COSTS:
UNIT 1
| SUBTOTAL UNIT 1 10 CFR 50.75(C) COSTS FOR PERIODS 1 - 6 | [5 empty] | 0 | 32037678.4268 | 5148773.4589 | 513646.4763 | 10652292.9435 | 0 | 85912778.4016 | 0 | 0 | 134265169.7071 | 43679200 | 177944369.7071 | 0 | 5760 | 509518.6127
| SUBTOTAL UNIT 1 10 CFR 50.54(bb) COSTS FOR PERIODS 1 - 6 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUBTOTAL UNIT 1 GREENFIELD COSTS FOR PERIODS 1 - 6 | [5 empty] | 0 | 22792602.7924 | 5310544.5133 | 0 | 2183579.5749 | 14217530.6485 | 0 | 0 | 0 | 44504257.529 | 8662000 | 53166257.529 | 0 | 417800.5726 | 0
UNIT 2
| SUBTOTAL UNIT 2 10 CFR 50.75(C) COSTS FOR PERIODS 1 - 6 | [5 empty] | 53462.3892 | 31861762.9762 | 5115230.9925 | 506778.1578 | 10606544.3851 | 0 | 85474156.8878 | 0 | 0 | 133617935.7886 | 43460800 | 177078735.7886 | 0 | 5760 | 506064.8165
| SUBTOTAL UNIT 2 10 CFR 50.54(bb) COSTS FOR PERIODS 1 - 6 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUBTOTAL UNIT 2 GREENFIELD COSTS FOR PERIODS 1 - 6 | [5 empty] | 0 | 22658804.8209 | 5287355.0716 | 0 | 2187603.9776 | 14244021.676 | 0 | 0 | 0 | 44377785.5461 | 8627900 | 53005685.5461 | 0 | 415106.1704 | 0
COMMON
| SUBTOTAL COMMON 10 CFR 50.75(C) COSTS FOR PERIODS 1 - 6 | [5 empty] | 9731335.0458 | 22033067.4561 | 3246784.3623 | 530434.6995 | 3218387.6353 | 0 | 13336350.4392 | 0 | 0 | 52096359.6382 | 13318300 | 65414659.6382 | 100196.4 | 24960 | 153162.5355
| SUBTOTAL COMMON 10 CFR 50.54(bb) COSTS FOR PERIODS 1 - 6 | [5 empty] | 783758.25 | 136688877.1068 | 224490000 | 0 | 0 | 0 | 0 | 0 | 0 | 361962635.3568 | 88824800 | 450787435.3568 | 7904 | 33280 | 0
| SUBTOTAL COMMON GREENFIELD COSTS FOR PERIODS 1 - 6 | [5 empty] | 0 | 14975787.3177 | 10489147.6395 | 0 | 3144007.5777 | 20695232.115 | 0 | 0 | 0 | 49304174.6499 | 8951900 | 58256074.6499 | 0 | 244211.4576 | 0
TOTAL PERIOD DEPENDENT COSTS
UNIT 1
| SUBTOTAL UNIT 1 10 CFR 50.75(C) COSTS FOR PERIODS 1 - 6 | [5 empty] | 27536582.6667 | 0 | 734368.7512 | 0 | 0 | 0 | 0 | 3482181.3729 | 3218991.7517 | 34972124.5425 | 5319400 | 40291524.5425 | 161307.2648 | 0 | 0
| SUBTOTAL UNIT 1 10 CFR 50.54(bb) COSTS FOR PERIODS 1 - 6 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUBTOTAL UNIT 1 GREENFIELD COSTS FOR PERIODS 1 - 6 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UNIT 2
| SUBTOTAL UNIT 2 10 CFR 50.75(C) COSTS FOR PERIODS 1 - 6 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUBTOTAL UNIT 2 10 CFR 50.54(bb) COSTS FOR PERIODS 1 - 6 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUBTOTAL UNIT 2 GREENFIELD COSTS FOR PERIODS 1 - 6 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMMON
| SUBTOTAL COMMON 10 CFR 50.75(C) COSTS FOR PERIODS 1 - 6 | [5 empty] | 222465437.3852 | 17792519.66 | 91198874.8907 | 0 | 0 | 0 | 0 | 26884824.1349 | 22249716.7308 | 380591372.8016 | 67781200 | 448372572.8016 | 3414843.9771 | 0 | 346871.887
| SUBTOTAL COMMON 10 CFR 50.54(bb) COSTS FOR PERIODS 1 - 6 | [5 empty] | 38112937.1624 | 0 | 1486130.9861 | 0 | 0 | 0 | 0 | 4547035.7093 | 24140603.6948 | 68286707.5527 | 10391500 | 78678207.5527 | 1079792.1793 | 0 | 0
| SUBTOTAL COMMON GREENFIELD COSTS FOR PERIODS 1 - 6 | [5 empty] | 15018321.9676 | 2781012.5062 | 6683016.8218 | 0 | 0 | 0 | 0 | 436695.8796 | 1279617.1783 | 26198664.3535 | 4844200 | 31042864.3535 | 156332.9918 | 51603.6009 | 0
ANNUAL SPENT FUEL STORAGE | [6 empty] | 2446029.2422 | 0 | 1256321.9593 | 0 | 0 | 0 | 0 | 16874.9283 | 635709.25 | 4354935.3798 | 557800 | 4912735.3798 | 56678.91 | 0 | 0
UNIT 1, UNIT 2 & COMMON
| GRAND TOTAL ACTIVITY COSTS FOR PERIODS 1-6 | [5 empty] | 10568555.6851 | 283048580.897 | 259087836.038 | 1550859.3335 | 31992416.0941 | 49156784.4395 | 184723285.7286 | 0 | 0 | 820128318.2158 | 215524900 | 1035653218.2158 | 108100.4 | 1146878.2007 | 1168745.9646
| GRAND TOTAL PERIOD DEPENDENT COSTS FOR PERIODS 1-6 | [5 empty] | 303133279.1819 | 20573532.1663 | 100102391.4498 | 0 | 0 | 0 | 0 | 35350737.0967 | 50888929.3556 | 510048869.2503 | 88336300 | 598385169.2503 | 4812276.4129 | 51603.6009 | 346871.887
ANNUAL SPENT FUEL STORAGE | [6 empty] | 2446029.2422 | 0 | 1256321.9593 | 0 | 0 | 0 | 0 | 16874.9283 | 635709.25 | 4354935.3798 | 557800 | 4912735.3798 | 56678.91 | 0 | 0
GRAND TOTAL | [6 empty] | 313701834.867 | 303622113.0632 | 359190227.4878 | 1550859.3335 | 31992416.0941 | 49156784.4395 | 184723285.7286 | 35350737.0967 | 50888929.3556 | 1330177187.4661 | 303861200 | 1634038387.4661 | 4920376.8129 | 1198481.8016 | 1515617.8516
ISFSI DECONTAMINATION AND REMOVAL | [6 empty] | 9448430.0254 | 4223216.3288 | 3066128.3659 | 0 | 0 | 175708.14 | 25681914.1553 | 100828.5743 | 1439752.3 | 44135977.8896 | 12816300 | 56952277.8896 | 0 | 375.1894 | 54838.5653
CHECK
SUBTOTAL UNIT 1 DECON PROGRAM FINANCIAL PLANNING COST FOR 10 CFR 50.75(c): | [6 empty] | 27536582.6667 | 32037678.4268 | 5883142.2101 | 513646.4763 | 10652292.9435 | 0 | 85912778.4016 | 3482181.3729 | 3218991.7517 | 169237294.2496 | 48998600 | 218235894.2496 | 161307.2648 | 5760 | 509518.6127
SUBTOTAL UNIT 1 DECON PROGRAM FINANCIAL PLANNING COST FOR 10 CFR 50.54(bb): | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUBTOTAL UNIT 1 DECON PROGRAM FINANCIAL PLANNING COST FOR GRENNFIELD (g): | [6 empty] | 0 | 22792602.7924 | 5310544.5133 | 0 | 2183579.5749 | 14217530.6485 | 0 | 0 | 0 | 44504257.529 | 8662000 | 53166257.529 | 0 | 417800.5726 | 0
SUBTOTAL UNIT 2 DECON PROGRAM FINANCIAL PLANNING COST FOR 10 CFR 50.75(c): | [6 empty] | 53462.3892 | 31861762.9762 | 5115230.9925 | 506778.1578 | 10606544.3851 | 0 | 85474156.8878 | 0 | 0 | 133617935.7886 | 43460800 | 177078735.7886 | 0 | 5760 | 506064.8165
SUBTOTAL UNIT 2 DECON PROGRAM FINANCIAL PLANNING COST FOR 10 CFR 50.54(bb): | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUBTOTAL UNIT 2 DECON PROGRAM FINANCIAL PLANNING COST FOR GRENNFIELD (g): | [6 empty] | 0 | 22658804.8209 | 5287355.0716 | 0 | 2187603.9776 | 14244021.676 | 0 | 0 | 0 | 44377785.5461 | 8627900 | 53005685.5461 | 0 | 415106.1704 | 0
SUBTOTAL COMMON DECON PROGRAM FINANCIAL PLANNING COST FOR 10 CFR 50.75(c): | [6 empty] | 232196772.431 | 39825587.1162 | 94445659.253 | 530434.6995 | 3218387.6353 | 0 | 13336350.4392 | 26884824.1349 | 22249716.7308 | 432687732.4399 | 81099500 | 513787232.4399 | 3515040.3771 | 24960 | 500034.4224
SUBTOTAL COMMON DECON PROGRAM FINANCIAL PLANNING COST FOR 10 CFR 50.54(bb): | [6 empty] | 38896695.4124 | 136688877.1068 | 225976130.9861 | 0 | 0 | 0 | 0 | 4547035.7093 | 24140603.6948 | 430249342.9094 | 99216300 | 529465642.9094 | 1087696.1793 | 33280 | 0
SUBTOTAL COMMON DECON PROGRAM FINANCIAL PLANNING COST FOR GRENNFIELD (g): | [6 empty] | 15018321.9676 | 17756799.824 | 17172164.4613 | 0 | 3144007.5777 | 20695232.115 | 0 | 436695.8796 | 1279617.1783 | 75502839.0035 | 13796100 | 89298939.0035 | 156332.9918 | 295815.0586 | 0
TOTAL UNIT 1 & 2 DECON PROGRAM FINANCIAL PLANNING COST FOR 10 CFR 50.75(c): | [6 empty] | 259786817.487 | 103725028.5192 | 105444032.4555 | 1550859.3335 | 24477224.964 | 0 | 184723285.7286 | 30367005.5078 | 25468708.4825 | 735542962.4781 | 173558900 | 909101862.4781 | 3676347.6419 | 36480 | 1515617.8516
TOTAL UNIT 1 & 2 DECON PROGRAM FINANCIAL PLANNING COST FOR 10 CFR 50.54(bb): | [6 empty] | 38896695.4124 | 136688877.1068 | 225976130.9861 | 0 | 0 | 0 | 0 | 4547035.7093 | 24140603.6948 | 430249342.9094 | 99216300 | 529465642.9094 | 1087696.1793 | 33280 | 0
TOTAL UNIT 1 & 2 DECON PROGRAM FINANCIAL PLANNING COST FOR GRENNFIELD (g): | [6 empty] | 15018321.9676 | 63208207.4373 | 27770064.0462 | 0 | 7515191.1302 | 49156784.4395 | 0 | 436695.8796 | 1279617.1783 | 164384882.0786 | 31086000 | 195470882.0786 | 156332.9918 | 1128721.8016 | 0
GRAND TOTAL | [6 empty] | 313701834.867 | 303622113.0632 | 359190227.4878 | 1550859.3335 | 31992416.0941 | 49156784.4395 | 184723285.7286 | 35350737.0967 | 50888929.3556 | 1330177187.4661 | 303861200 | 1634038387.4661 | 4920376.8129 | 1198481.8016 | 1515617.8516
CHECK | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1.407%